AC 150/5370-6D

9/29/08
9/29/08

AC 150/5370-6D

Appendix 1

	[image: image3.jpg]



	
	Advisory Circular

	U.S. Department
of Transportation
Federal Aviation
Administration
	

	Subject:  Construction Progress and Inspection Report—Airport Improvement Program (AIP)
	Date:   9/29/08
Initiated by:  AAS-100
	AC No.:  150/5370-6D
Change:  


1. PURPOSE.  This advisory circular (AC) provides guidance for reporting construction progress of projects under the Airport Improvement Program (AIP).  

2. APPLICATION. The Federal Aviation Administration recommends the guidelines and standards in this AC for airport construction projects.  This AC does not constitute a regulation and in general is not mandatory. However, use of these guidelines is mandatory for construction projects funded under the Airport Improvement Program (AIP). Mandatory terms such as “must” apply only to those who undertake construction projects using AIP funds.
3. RESPONSIBILITY FOR SUPERVISION AND INSPECTION.  The airport sponsor (owner) has primary responsibility for supervision and inspection of construction work under the AIP. The FAA Airports Division/District/Field Offices are responsible for monitoring the project to ensure the terms and conditions of the grant agreement are met, to maintain a broad overview of the construction to be reasonably certain the work is accomplished in accordance with the plans and specifications, and to evaluate the adequacy of the sponsor’s construction inspection. 

4.
FAA NEED FOR INFORMATION.  In order to meet the above responsibility, the FAA needs information as to what work is in progress, completed, or planned; recent testing; and problem areas. This information is discussed at the preconstruction conference and can be obtained in a convenient manner in an appropriate timeframe through use of FAA Form 5370-1, Construction Progress and Inspection Report.  Use of this form is not mandatory.  The sponsor may prepare and use customized forms.

5. 
USE OF FAA FORM 5370-1.  FAA Form 5370-1, Construction Progress and Inspection Report (see Appendix 1), or a form that provides equivalent information, must be maintained by the sponsor’s engineer and submitted to the appropriate Airports Division/District/Field Office upon request.  If any problems, delays, or adverse conditions occur that will affect the project, the engineer should submit an interim report to the FAA.

6.  PRINCIPAL CHANGE.  FAA Form 5370-1 was reapproved through February 28, 2011, by the Office of Management and Budget. 

7.
CANCELLATION.  This AC cancels AC 150/5370-6C, Construction Progress and Inspection Report—Airport Development Aid Program, dated September 29, 2007. 

8.
COPIES OF THIS AC.  This AC can be found on the Federal Aviation Administration (FAA) website at http://www.faa.gov/airports_airtraffic/airports/resources/advisory_circulars/.
9.  
COPIES OF FAA FORM 5370-1.  This form can be found on the Federal Aviation Administration (FAA) website at http://forms.faa.gov.
[image: image1.emf]
Michael J. O’Donnell
Director of Airport Safety and Standards

This page intentionally left blank.

[image: image2.jpg]018 Approved 2120.0500
Ep vt

Perad Erding

Q CONSTRUCTION PROGRESS AND INSPECTION

REPORT
US. Depariment

of Transpartation
Federal Auiation AIRPORT GRANTPROGRAM

Adrministration

Projec Number

Aiport Name

Proet Desariton Corfracters Name

7. Rough Esimats ofPercent Completion 1o Date of Consuction Phases (noide Rers Sich a5 clarig, Gradig, arainage, Fase, suace, 1GHng, o1c]

2 Work Compieted orinProgress s Periad

3Bt Wealhr Summary s Period, inding Approimats Reiriall and Poriogs of BelowFreeaing Temperature
(O earthwork jobs, include soi condtins)

T Comrect Te 5. Sumimary of Laboratory and Fied Testing 1 Period (vate faling Tosts and avy etets. Summarize ot S0k rance ]

No Days | Lad Working
Charged Ta | Day Charged
Date. Date)

aterl (aeniRy Tale el el pay Teaucion)

& Desorbe Ariapated Work by Corfractor for N Period

7. Froblem AreasiOer Comments (Reviansta plans and ectEations spproved or denkd, delys ARCuRes, otc. and actins ahen)

SPONSOR’S INSPECTOR OR REPRESENTATIVE

e Tpedt or Prirted Name and Tiie Sigrature

FARFom 53707 (6.09) Supsrsades Previous Edon

Paparycrc Facition Aot Statamerts This orm allws the FAARD calec nformtion abaut on=rctin profcs o ansurs th tams and condiins of rat agrasments are
k.3 A 3 bresd VAT a1 th SNSRI 15 b reasonby SHTa T ok [ S4EorPISnEd i Socordanch A1 The pans and paciioTons, a1 £ e he
2dequscy of the ponsoFs conswcton nspacion. 11 estimated tat  uil3ke 3pprosimately 550 hours 1 11 ot the orm daperding o the complxiy. No assurahce of
conderualty 1 necessanyor prnidad. Tt shoud be netad that 3n agency may et conduct o sponsor, 3nd 3 prson i no rquied o espond o 3 collection of nbmaton
iieSE 1t Gplaye  curay v DM corrs number. The W sonrel mAmoer EEoe18d i T colchin of mbrmaion <3 120-1880 Lo ment oanesming he aooussy
3t burden 1d a1ggesHnE o rediing he bursen hould b drected  the FAA o 00 Inde andence . S, Wsshingian. DT 20581, Adn: mormaon Calectiont
Clsarancs Ofioer AD20





Form 5370-1, Construction Progress and Inspection Report 








































































































































































2
3 (and 4)

