## Slide 1: NAS Enterprise Architecture
Infrastructure Roadmaps-
Surveillance v17.0
Baseline
February 2023

## Slide 2: Infrastructure Roadmap Overview
What are the Infrastructure Roadmaps?
The FAA Infrastructure Roadmaps show the progression of system deployments, investments, and key decision points for major NAS acquisitions. They depict the acquisition strategy to evolve the NAS from the As-Is to the To-Be environment.
The Infrastructure Roadmaps show all Capital Investment Plan (CIP) investment projects and systems identified in the NSIP that will deliver the necessary functionality to enable OIs and BTIs.
Guidelines for Understanding the Roadmaps
The Infrastructure Roadmaps are organized by Domain (Automation, Communication, etc.) and depict projects, systems, services, decision points, and support activities.
The timeline is in calendar years and shows a 15-year outlook.
The roadmaps have swim lanes for infrastructure (white) and Support Activities (green).
The DP diamonds represent the quarter in which a decision will occur.
The Support Activity bars represent the dates that work is being performed on the activity.
The Project bars represent the dates that CIP funding is allocated to a project.
The System and Service bars represent the dates that a system or service is operational, with red lines indicating sustainment, drawdown, or convergence.
What’s new in Version 17.0?
See Appendix B: Change History for domain-specific changes.

## Slide 3: Surveillance
Objective: The Surveillance roadmap depicts the sustainment of legacy surveillance systems and the evolution towards the NextGen environment.

## Slide 4: Surveillance Roadmap (1 of 4)
Cooperative Surveillance - Broadcast Services
ADS-B In Applications
ADS-B Services & Baselines
Includes Space-Based ADS-B
IARD
1323
ADS-B In Appl - Interval Management Planning
ADS-B
ADS-R
ADS-B Interval Management
ADS-B Baseline Services Future Segments
ADS-B Enhancement
FIS-B
ADS-C
Advanced Surveillance Enhanced Procedural Separation (ASEPS)
SBS Monitor
ADS-B Out
Avionics
ADS-B In
Avionics
1213
1213
ADS-B Baseline Services Future Segments Phase 2
FID
1240
FID
1327
IARD
1348
TIS-B
ADS-B Baseline Services Future Segments Phase 3
IARD
1391
FID
1392
ADS-B In Capability Indicators
ADS-B Interval Management Phase 1A
IARD
1393
FID
1232
FID
1390
FID
1327

## Slide 5: Surveillance Roadmap (2 of 4)
Terminal and En Route Surveillance Technical Refresh Portfolio
Cooperative Avionics
Cooperative Surveillance Systems
Select # (~40) of Mode S, ATCBI-5, and ATCBI-6 systems replaced by MSBRS Phase 1A/1B
[300+ legacy cooperative systems remaining]
Interfaces
ATCBI-6
ASR-11
MODE S
Mode S Beacon Replacement System Phase 1A
ATCBI-5
WAM
MSBRS
Mode 3/A/C
Transponder
Mode S
Transponder
TCAS
ACAS X
ACAS-X
ATCBI-6 Sustainment
ACAS-X Segment 2
ATCBI-5 Sustainment 2
ATCBI-5 Sustainment 1
ASR-11 Sustainment 3
FID 806
CD-2
Mode S Beacon Replacement System Phase 1B
Mode S Beacon Replacement System Phase 2
FID 1343
ASR-11 Sustainment 4
FID 1321
1165
ADS-B Baseline Services Future Segments
ADS-B Baseline Services Future Segments Phase 2
FID
1327
Mode S Sustainment 4
ATCBI-6M

## Slide 6: Surveillance Roadmap (3 of 4)
DoD/DHS funded/FAA maintained
DoD/DHS funded/FAA maintained
Non-Cooperative Surveillance
Interfaces
ANSR to evaluate alternatives for sustaining Non-Cooperative radar service provided by ASR-8, ASR-9 and ASR-11
ASR-11
ASR-11 Sustainment 3
FID 806
ASR-9
ASR-9 Sustainment 3
CV-4400
ASR-8/CTD
ARSR-4
Common ARSR
Terminal and En Route Surveillance Technical Refresh Portfolio
Airspace Non-Cooperative Surveillance Radar (ANSR)
IARD
1236
IID
1237
FID
1238
ASR-8 Sustainment 1
ASR-9 Sustainment 4
ASR-11 Sustainment 4
X
TDX-2000

## Slide 7: Surveillance Roadmap (4 of 4)
Airport Surface Detection Equipment (ASDE) Sustainment
Support
Activities
Surface and Approach
ASDE-X
ASDE-3
ASSC
RWSL
Runway Status Lights (RWSL) Sustainment
Evaluate Impact of Wind Turbine
Interference on Radar Systems
Evaluate Impact of Wind Turbine
Interference on Radar Systems
Surface Surveillance Portfolio Sustainment
Surveillance Portfolio Analysis
Surveillance Portfolio Analysis
IARD
1236
IARD
1323
FID 1321
IARD
1236
FID 1319
FID
1327
ASDE Surface Movement Radar Replacement

## Slide 8: Surveillance Roadmap: Assumptions
Identifier | Description
SURV-01 | Backup to mitigate loss of on-board GPS positioning source for ADS-B is required: a) Retain all en route beacons (~150 monopulse systems) b) Retain limited set of terminal beacons (or WAM) based on need (Core 30 airports for resiliency, other airports based on economic analysis and ADS-B equipage rates) c) All terminal non-cooperative surveillance coverage areas are retained for safety purposes d) Selected terminal surveillance systems that will no longer be required will be divested starting in CY2020
SURV-02 | The Mode-S Beacon Replacement System (MSBRS) will replace all remaining beacon systems that are not replaced by WAM
SURV-03 | The ANSR program will determine the long-term upgrade strategy of the ASR-8, ASR-9, and ASR-11 (PSR portion) systems

## Slide 9: Surveillance Roadmap: Decision Points (1 of 1)