## Slide 1: Overall FY18 Portfolio Schedule
Milestone Complete Date Notes
AVS Strategic Guidance issued 5/29/2015
All TCRG requirements submitted 9/25/2015 (All AVS reqs. due)
AVS RED Group voting 9/25-10/16/2015
Phase I Technical Prioritization 10/20-22/2015
Top-60 list released 10/23/2015
PPT Meeting – review top-60 11/TBD/2015
REB Meeting – PPT process presentations 11/TBD/2015 (AVS R&D Manager)
Performer cost estimates submitted 12/4/2015
Phase II Budget Programming 1/12-13/2016
REB Meeting – PPT portfolio reviews 2/TBD/2016 (AVS R&D Manager)
PPT Meeting – review draft portfolio 2/TBD/2016
HF Subcommittee Review 2/TBD/2016
AVS Office/Service Level Reviews completed 2/26/2016
Performer funding review completed 2/26/2016
SAS Review 3/TBD/2016
Safety PPT review and prep for AVSMT complete 4/TBD/2016
AVSMT RE&D portfolio reviewed 4/TBD/2016
FY18 Budget Narratives 5/TBD/2016

## Slide 2: Overall FY17 Portfolio Schedule
Milestone Complete Date Notes
AVS Strategic Guidance issued 5/24/2014
All TCRG requirements submitted 9/26/2014 (All AVS reqs. due)
AVS RED Group voting 10/22/2014
Phase I Technical Prioritization 10/30/2014
Top-60 list released 10/31/2014
PPT Meeting – review top-60 11/5/2014 (tentative)
REB Meeting – PPT process presentations 11/17/2014 (AVS R&D Manager)
Performer cost estimates submitted 12/5/2014
Phase II Budget Programming 1/14/2015
REB Meeting – PPT portfolio reviews 2/2 & 2/9/2015 (AVS R&D Manager)
PPT Meeting – review draft portfolio 2/4/2015
HF Subcommittee Review 2/26/2015
AVS Office/Service Level Reviews completed 2/28/2015
Performer funding review completed 2/28/2015
SAS Review 3/24-26/2015
Safety PPT review and prep for AVSMT complete 4/TBD/2015
AVSMT RE&D portfolio reviewed 4/23/2015
FY17 Budget Narratives 5/TBD/2015 ?