## PBCS Seamless Chart
Ver. 20160217
Pacific FIRs Seamless PBCS Planning Chart |  |  |  |  | Applicable Airspace | Anchorage Oceanic FIR | Auckland FIR | Brisbane (Honiara & Nauru UTAs) | Fukuoka FIR | Manila FIR | Nadi FIR | Oakland Oceanic FIR | Port Moresby FIR | Santiago FIR | Tahiti FIR | Ujung Pandang FIR | Anchorage Domestic FIR | Anchorage Arctic FIR | Guam CERAP | Honolulu Control Facility | Los Angeles ARTCC | Mazatlan FIR | Oakland Domestic ARTCC | Seattle ARTCC | Vancouver ACC
PBCS Implementation Task List | Task Group | Task ID | TASK descriptor
| Group A | A-1 | AIP (Prescription of an RCP/RSP specification)
|  | A-2 | ANSP (PBCS policies, objectives supporting safety oversight)
|  | A-3 | Operatpr and aircraft System- PBCS policies, objectives supporting safety oversight
|  | A-4 | Regional Supplementary Procedures (Doc. 7030) for PBCS operations , if applicable
| Group B | B-1 | PBCS Implementaion Plan
|  | B-2 | Target dates for PBCS and relevant ATM operations
|  | B-3 | RCP/RSP specifications
|  | B-4 | PBCS awareness
| Group C | C-1 | Operational concepts and procedures for PBCS operations
|  | C-2 | ATC automation changes to use flight plan RCP/RSP indicators
|  | C-3 | ATC automation changes for PBCS monitoring
|  | C-4 | Confirm initial ANSP compliance with RCP/RSP specifications
| Group D | D-1 | Aircraft operator readiness
| Group E | E-1 | PBCS monitoring - post implmentation
Cmmunication Specifications & Interoperatability Standards |  |  | Normal | RCP240 | FANS1/A CPDLC
|  |  | Alternate | RCP400 | SATVOICE
|  |  |  | RCP400 | HF
Surveillance Specifications & Interoperatability Standards |  |  | Normal | RSP180 | FANS1/A ADS-C
|  |  | Alternate | RSP400 | SATVOICE
|  |  |  | RSP400 | HF
|  |  | ADS-B |  |  | X |  | X |  |  | X |  | P |  | X |  | X |  |  | X | X |  | X | X
Navigation Specifications & Applicable ATM Operations |  |  | RNAV/RNP | RNAV/RNP 10 | 50 NM Lateral Separation | X | X | X | X |  | X | X | X | X | X | X | X |  | X | X | X |  | X | X | X
[5 empty] | 50 NM Longitudinal Separation | X | X | X | X |  | X | X | X | X | X |  | X |  | X | X | X |  | X | X | X
|  |  |  | RNP 4 | 30 NM Lateral Separation | X | X | X | X |  | X | X | [6 empty] | X | X | X |  | X | X
[5 empty] | 30 NM Longitudinal Separation | X | X | X | X |  | X | X |  |  |  |  | X |  | X | X | X |  | X | X
|  |  |  | RNP2 | 30nm Climb-Descend Through
15nm VHF Lateral Separation
8NM VHF Climb-Descend Through
|  |  | 10 MINUTE Longitudinal Separation without MNT. |  |  | X | X | X | X |  | X | X |  | X |  |  | X |  | X | X | X |  | X | X | X
|  |  | RVSM |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Other ATM Operations |  |  | ADS-C CDP |  |  | P |  |  | P |  |  | P
|  |  | ADS-B ITP |  |  | P |  |  | P |  |  | X
|  |  | Tactical Lateral Offsets for Climb or Descent |  |  |  | X | X |  |  |  | X
|  |  | Tailored Arrival | [8 empty] | X
|  |  | CDO | [5 empty] | X
|  |  | UPR |  |  | X | X | X | X |  | X | X | X | X | X
|  |  | DARP | Accept |  | X | X | X | X |  | X | X |  |  | X |  |  |  | X | X | X |  | X | X
|  |  |  | Initiate |  |  | X |  | X |  | X | X |  |  | X
Note: Current status of each FIR is as of 2015.

## Agencies&contact list
Responsible Agencies for PBCS Implementation Sheet
FIR | Responsible Agency & Point Of Contact
| PBCS Monitoring Agency | En-route Monitoring Agency | State of Registory | State of Operator
Anchorage Oceanic FIR
Auckland FIR
Brisbane (Honiara & Nauru UTAs)
Fukuoka FIR | Central Repoting Agency of Japan (CRA Japan) E-mail: Tel: Web address:
Manila FIR
Nadi FIR
Oakland Oceanic FIR
Port Moresby FIR
Santiago FIR
Tahiti FIR
Ujung Pandang FIR
Anchorage Domestic FIR
Anchorage Arctic FIR
Guam CERAP
Honolulu Control Facility
Los Angeles ARTCC
Mazatlan FIR
Oakland Domestic ARTCC
Seattle ARTCC
Vancouver ACC

## Doc.9869 Appendix A
PBCS Implementation Plan -Checklist
Task ID | Task Descriptor | Task Detail | ICAO reference
Group A tasks – State/region preparation
A-1 | AIP – Prescription of an RCP/RSP specification | Prescribe the appropriate RCP/RSP specification in the AIP (or equivalent publication). If applicable, common AIP language may be based on a bilateral, multilateral or regional air navigation agreement. | PBCS Manual (Doc. 9869) Chapter 4
A-2 | ANSP – PBCS policies, objectives supporting safety oversight | Identify means to apply RCP/RSP specifications and compliance criteria for initial approval and continued compliance, including: | PBCS Manual Chapter 5 Section 5.2.1 Section 5.2.2
a) ATS provision requirements, and requirements for ATS unit’s system and CSP/SSP service agreements, if applicable;
b) flight plan requirements; and
c) monitoring, alerting and reporting requirements.
A-3 | Operator and aircraft system – PBCS policies, objectives supporting safety oversight | Identify means to determine aircraft operator eligibility requirements for PBCS operations, including requirements for operations, maintenance, aircraft system and CSP/SSP service agreements, if applicable: | PBCS Manual Chapter 5 Section 5.2.1 Section 5.2.3
a) establish State airworthiness requirements;
b) establish operational policy/procedures requirements for operational approval;
c) prepare State inspectors to perform tasks for operational approval;
d) develop plan to issue operational approval to national operators. Train pilots and, if applicable, dispatchers on PBCS operations; and
e) develop and distribute operations manuals, pilot bulletins or other appropriate documents containing PBCS policy and/or procedures.
Note.— State of the Operator identifies means for commercial air transport operations. State of Registry identifies means for general aviation operations. State of Design identifies means for design approval of the aircraft system.
A-4 | Regional Supplementary Procedures (Doc 7030) for PBCS operations, if applicable | On behalf of a region, a State may develop a proposed amendment to the Regional Supplementary Procedures (Doc 7030), if applicable. | PBCS Manual Chapter 4 Chapter 5
Group B tasks – ANSP general project development and management
B-1 | PBCS Implementation Plan | Establish PBCS implementation team and prepare a plan outlining the tasks for PBCS implementation. Include interdependencies between tasks, when each task is to be completed, lead point of contact and any coordination required. | State/region specific, this appendix serves as a guide.
B-2 | Target dates for PBCS and relevant ATM operations | Identify key target dates for implementing PBCS supporting specified ATM operation(s) and the tasks identified in the plan. | State/regions
B-3 | RCP/RSP specifications | Identify and confirm applicable RCP/RSP specifications that will be used for operational implementation of communication and surveillance capabilities supporting specified ATM operation(s). Existing RCP/RSP specifications may be appropriate for a new ATM operation predicated on RCP/RSP specifications (e.g. application of performance-based separation minimum), or when implementing an emerging technology to provide a communication or surveillance capability (e.g. SATVOICE) supporting an existing ATM operation. If a new RCP or RSP specification is needed, establish a task to coordinate with ICAO on the development of the appropriate RCP/RSP specifications for update to Doc 9869. | PBCS Manual Chapter 3 Appendix B Appendix C
B-4 | PBCS awareness | Establish means to raise awareness on PBCS implementation in a particular region or airspace through workshops and distribution of information. Establish a planning team to work with ICAO and subject matter experts to develop relevant material. | PBCS Manual GOLD (Doc. 10037) SVOM (Doc. 10038)
Group C tasks – ANSP implementation activities – ATS service provision
C-1 | Operational concepts and procedures for PBCS operations | Develop operational concepts for implementation of any ATM operation predicated on an RCP/RSP specification. Consider the following: | PBCS Manual GOLD (Doc. 10037) SVOM (Doc. 10038)
a) applicable ATM operation(s);
b) relevant interoperability requirements for communication and surveillance capabilities;
c) provision for PBCS operations and appropriate RCP/RSP specifications;
d) operating procedures for PBCS operations;
e) operator/flight/flight crew and/or ATS unit/controller contingency procedures when system degrades below that required by RCP/RSP specifications; and
f) procedures for resuming specified ATM operation(s) after system is restored to an acceptable level of performance.
C-2 | ATC automation changes to use flight plan RCP/RSP indicators | Implement changes to recognize and use flight plan RCP/RSP indicators to apply ATM operation(s) predicated on the RCP/RSP specifications only to eligible operators/aircraft, and/or adapt other system parameters, if applicable (e.g. set timer threshold values), based on different performance levels). This task should be complete prior to operational implementation of ATM operation(s) predicated on RCP/RSP specifications. | PBCS Manual Chapter 5 Section 5.4
C-3 | ATC automation changes for PBCS monitoring | Implement post-implementation monitoring capability in ATC automation. This task should be completed to obtain a sufficient sample to confirm ACP and ASP comply with RCP/RSP specifications prior to implementation of specified ATM operation(s). | PBCS Manual Chapter 5 Section 5.5 Appendix D Appendix E
C-4 | Confirm initial ANSP compliance with RCP/RSP specifications | Prior to operational implementation, confirm CPDLC and ADS-C comply with RCP/RSP specifications: | PBCS Manual Chapter 5 Section 5.2.2 Section 5.3.1 Section 5.3.2 Appendix D Appendix E
a) measure actual performance against RCP/RSP specifications for compliance to support initial approval of ATS provision, including CSP/SSP service agreement, if applicable;
b) identify any aspect of service performance that is not compliant with the RCP/RSP specifications; and
c) take appropriate action to mitigate.
Group D tasks – Aircraft operator, Aircraft type/system (airworthiness) eligibility
D-1 | Confirm initial operator and/or aircraft type/system compliance with RCP/RSP specifications | Prior to operational approval, confirm CPDLC and ADS-C aircraft equipment and operator capabilities comply with RCP/RSP specifications: | PBCS Manual Chapter 5 Section 5.2.3 Section 5.3.2 Section 5.3.3 Section 5.3.4 Appendix D Appendix E
a) measure actual performance against RCP/RSP specifications for compliance to support initial approval of operator, including aircraft system approval and CSP/SSP service agreement, if applicable;
b) identify any aspect of aircraft type/system and/or capability performance that is not compliant with the RCP/RSP specifications; and
c) take appropriate action to mitigate.
Group E tasks – All stakeholders – post-implementation monitoring
E-1 | PBCS monitoring – post-implementation | On-going post-implementation data collection, monitoring, problem reporting and tracking, analysis and corrective action. When performance falls below specified levels, or problems are reported, operational judgment may be a consideration in determining appropriate actions. | PBCS Manual Chapter 5 Section 5.5 Appendix D Appendix E RMA Manual (Doc 9937) PBHSM Manual (Doc. xxxxx)