## Slide 1: NAS Enterprise Architecture
Infrastructure Roadmaps v16.0
Baseline
February 2022

## Slide 2: Table of Contents
Section | Page
Infrastructure Roadmap Legend | 3
Aircraft Roadmaps | 6
Airport Roadmaps | 17
Airspace & Procedures Roadmaps | 26
Automation Roadmaps | 31
Communication Roadmaps | 41
Enterprise Services Roadmaps | 50
Facilities Roadmaps | 56
Human Systems Integration Roadmaps | 63
Navigation Roadmaps | 70
New Entrants Roadmaps | 78
Commercial Space | 79
Unmanned Aircraft System | 84
Safety Roadmaps | 91
Surveillance Roadmaps | 98
Weather Roadmaps | 105
Appendix A: Acronym List | 118
Appendix B: Change History | 122
Appendix C: Diagram Updates | 137

## Slide 3: Infrastructure Roadmap Overview
What are the Infrastructure Roadmaps?
The FAA Infrastructure Roadmaps show the progression of system deployments, investments, and key decision points for major NAS acquisitions. They depict the acquisition strategy to evolve the NAS from the As-Is to the To-Be environment.
The Infrastructure Roadmaps show all Capital Investment Plan (CIP) investment projects and systems identified in the NSIP that will deliver the necessary functionality to enable OIs and BTIs.
Guidelines for Understanding the Roadmaps
The Infrastructure Roadmaps are organized by Domain (Automation, Communication, etc.) and depict projects, systems, services, decision points, and support activities.
The timeline is in calendar years and shows a 15-year outlook.
The roadmaps have swim lanes for infrastructure (white) and Support Activities (green).
The DP diamonds represent the quarter in which a decision will occur.
The Support Activity bars represent the dates that work is being performed on the activity.
The Project bars represent the dates that CIP funding is allocated to a project.
The System and Service bars represent the dates that a system or service is operational, with red lines indicating sustainment, drawdown, or convergence.
What’s new in Version 16.0?
See Appendix B: Change History for domain-specific changes.
For more information, please contact:
Walter Coppeans III (walter.coppeans-iii@faa.gov).

## Slide 4: Overview of CY2022 Decision Points

## Slide 5: Overview of CY2023 Decision Points

## Slide 6: Aircraft
Objective: The Aircraft roadmap presents planned advances in Airframe and Avionics in coordination with NAS NextGen improvements.
For more information, please contact Stephen VanTrees (stephen.vantrees@faa.gov).

## Slide 7: Aircraft Roadmap (1 of 8)
GBAS Cat I
Approach Avionics
GBAS Cat II/III
Approach Avionics
SBAS (WAAS)
Avionics
ILS Cat II/III
Approach Avionics
ILS Cat I
Approach Avionics
VOR Avionics
DME Avionics
TACAN Avionics
ADF Avionics
Position, Navigation & Timing Avionics Receivers
RNP
RNP
RNP AR
RNP 0.3
RNP 10
RNAV
RNP 1
RNP 2
RNAV
GPS
Avionics
RVSM
RNP 4 30/30
RNP 1 RF
A-RNP
RNP APCH
Domestic PBN
Oceanic PBN
956
220
Position, Navigation & Timing Capabilities
Items with a green outline are components of the FAA Minimum Capability List (MCL)
RNP-to-xLS ( ILS, GLS, LPV-Related)
RNAV 2
RNAV 1

## Slide 8: Aircraft Roadmap (2 of 8)
A/G Voice
Comms
Airborne
UHF Radio
Airborne
VHF Radio
Airborne
HF Radio
SATCOM
Eqpt. & Svc.
HFDL
Airborne
SATCOM
Supplemental Use of SAT Voice
Flight
Management
FANS 1/A
Flight
FMS
FANS 1/A
FMS
HF
SATCOM DL
ADS-C
A/G Data Communications
Domestic Airspace
Legacy
Oceanic Airspace
B2 Equipage: Airborne
Data Comm Security
NGSS Eval.
Single RTA used in
flight management
Oceanic Operations - Integrated Nav, Comm, Surv and Flight Management
ACARS Eqpt. & Service of third party service plus TDLS service (ATIS, PDC msg.)
ACARS Eqpt. & Service of third party (TWIP, MDCRS, AOC msg)
FANS 1/A Eqpt. & Service (FANS CPDLC & FANS ADS msg)
FANS-1/A VDL-2 PTL
Items with a green outline are components of the FAA Minimum Capability List (MCL)
FANS 1/A VDL2
Equipage: Airborne
NEXCOM Phase 2
NEXCOM Phase 3
FID
1223

## Slide 9: Aircraft Roadmap (3 of 8)
Safety Enhancements
ADS-B In
Avionics
Surveillance
Mode 3/A/C
Mode S
Transponder
ADS-B Out
Avionics
TIS-B
TCAS
TAWS
ELT
FIM
ITP
TSAA
ADS-B In
CAVS
ACAS X – Segment 1
ACAS-X
FIS-B
ASSAP
CDTI
TEST
ACAS-X – Segment 2
1213
Items with a green outline are components of the FAA Minimum Capability List (MCL)

## Slide 10: Aircraft Roadmap (4 of 8)
Auto-Pilot
Auto-Throttle
Moving Map
CDTI
HUD
EFVS
MDCRS
Weather Sensors
Low Visibility Ops
SVS
SMGCS
EFB
Displays
Controls
New Airframes
and Propulsion
SVGS
UAS
Items with a green outline are components of the FAA Minimum Capability List (MCL)

## Slide 11: Aircraft Roadmap (5 of 8)
Safety & Security
Enhancements
RTCA SC-147 TCAS &
SC-186 ADS-B PNT
Surveillance
239
AIS Data Link
RTCA
SC-206
RTCA
SC-214
DO-358B MOPS for FIS-B with UAT
DO-364A FIS-B MASPS
RTCA
SC-222
1165
DO-224E Signal-in-Space MASPS for Advanced VHF Digital Data Comm.
DO-281D MOPS for Aircraft VDL Mode 2
Companion Document to cover Ground Equipment
DO-385/ED-256 Change 2
MOPS for ACAS Xr
MOPS for ACAS sXu
DO-350B, Safety and Performance Requirements Standard for ATS Data Communications (SPR Standard)
DO-353B, Interoperability Standard for Baseline 2 ATS Data Communications, ATN Baseline 1 Accommodation (ATN Baseline 1 - Baseline 2 Interop Standard)
DO-352B, Interoperability Standard for Baseline 2 ATS Data Communications, FANS 1/A Accommodation (FANS 1/A - Baseline 2 Interop Standard)
DO-351B, Interoperability Standard for Baseline 2 ATS Data Communications (Baseline 2 Interop Standard)
DO-XXX, Verification Test Standard
ACAS sXu System Software Interface
Xr Logic Optimization

## Slide 12: Aircraft Roadmap (6 of 8)
RTCA
SC-159
RTCA
SC-227
DO-235C Updated L1 interference environment report
DO-292A Updated L5 interference environment report
DO-373A Update to GNSS dual-frequency (1575/1176 MHz) antenna MOPS for airborne equipment
GNSS(SBAS) L1/L5 MOPS GPS/Galileo/SBAS MOPS developed jointly with EUROCAE WG-62 that are intended to be usable for ETSO/ TSO production and certification of the receivers for aviation use
GNSS (SBAS) L1/L5 MOPS Update to GPS/Galileo/SBAS MOPS for dual-frequency equipment
GNSS (GBAS) L1/L5 MOPS and ICD Initial MOPS and ICD for Verification and Validation
GNSS (GBAS) L1/L5 MOPS and ICD Validated GPS/Galileo/GBAS MOPS and ICD for dual-frequency equipment
MASPS DO-236D
MOPS DO-257C
MOPS DO-283C
Navigation Equipment Using the Global Navigation Satellite System (GNSS)
Standards of Navigation Performance

## Slide 13: Aircraft Roadmap (7 of 8)
UAS
SC-228
Airworthiness
962
1168
1169
1173
Detect and Avoid (DAA)
1172
1176
Command and Control (C2)
Guidance Material & Considerations for UAS (DO-304A)
GBSS MOPS (DO-381A)
GM for Lost C2 Link UAS Behavior
GM for UAS Navigation Systems
C2 Link MOPS (Terrestrial) (DO-362B)
DAA MOPS (DO-365C)
C2 Link MOPS for Cellular Networks
C2 Link Systems MASPS (DO-377B)
Workgroups 3 & 4

## Slide 14: Aircraft Roadmap (8 of 8)
FAA System Safety Guidance: Development of Feasible Human Error Assessment Method Alternatives
1131
Human Performance
Enhanced Helicopter Vision Systems: Human Factors Examination of Heads-Up/Head-Worn Display Technologies and Concepts
1134
1043
Human Factors Assessment of Aircraft Energy State Awareness Prototype Alternatives

## Slide 15: Aircraft Roadmap: Assumptions
Identifier | Description
AC-01 | The roadmap identifies four phases CONOPs development and R&D in required areas Standards development AVS Approval ATC Procedure development Deployment. After the standards process is complete, and manufacturers have developed, integrated, fully tested and made new avionics available, aircraft, engines and fuels available, an additional 7 to 10 years is needed to achieve wide scale equipage of a new capability Different aircraft are expected to equip with different equipment. This roadmap does not currently distinguish between aircraft types.
AC-02 | The aircraft roadmap includes environment research areas and assumptions and linkage to Mission Support EA.
AC-03 | Any aircraft to include any UAS that participates in the NAS must operate in a way that is transparent to the ANSP and ATSP.
AC-04 | The Minimum Capability (MCL) items documented in the Aircraft roadmap are accurate as of the September 2019 draft of the MCL.
AC-05 | The Minimum Capabilities List (MCL) provides clear and comprehensive guidance to support equipage across all fleets operating in the National Airspace System (NAS). The MCL’s purpose is to: Define the minimum aircraft capabilities and associated equipment needed to maximize benefits from FAA investment and operational improvements Guide “forward-fit” aircraft equipage and inform operator investment decisions Maximize the return on investment for both the FAA and airspace users
AC-06 | The yellow roadmap symbol is being utilized as aircraft operational capabilities on this roadmap.

## Slide 16: Aircraft Roadmap: Decision Points (1 of 1)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 17: Airport
Objective: The Airport Roadmap identifies NextGen progression of services, procedures and systems in the airport environment.
For more information, please contact Brandon Parks (brandon.m.parks@faa.gov).

## Slide 18: Airport Roadmap (1 of 5)
NextGen DME Support for PBN Strategy
Airport Communications
Navaids – Precision/Non-Precision Approaches
FTI
X
FAA Enterprise Network Services (FENS)
FENS
TDM-to-IP Migration
FID 74
Airport
Cable Loop
Airport Cable Loop System Sustainment
Runway Visual Range (RVR) (Includes CAT I & CAT II/III)
Approach Lighting System Safety Enhancement (Includes ALS I & ALS II/III)
Instrument Landing Systems (ILS) (Includes CAT I & CAT II/III)
VOR
VOR MON Phase 2
SBAS (WAAS)
220
DME
Distance Measuring Equipment (Includes LP DME & HP DME)
VORTAC (Includes VOR & TACAN)
WAAS Phase 4B
FID 1139
ASTI
TACAN
AeroMACS
ASTI Sustainment
WAAS Ph4A/4B Transition
956
AWCS
Landing and Lighting Portfolio
DVT Sustainment
Phase 1
Phase 2
FID 1196
FID 1311
Segment 1
Segment 2
Segment 3
1071
TDM-to-IP Migration Phase 2
FTI Sustainment 2

## Slide 19: Airport Roadmap (2 of 5)
Airport Location Lights
Surveillance
VASI
REIL
LDIN
ODALS
VOT
PAPI
Replace VASI with PAPI
Runway and Taxiway Edge Lighting Systems
Land and Hold
Short Lighting Systems
Runway Centerline and Touchdown Lighting Systems
Taxiway Lighting Systems
Runway Incursion Reduction - ATDP
Airport Surface Detection Equipment (ASDE) Sustainment
PRM E-SCAN
ASDE-X
ASDE-3
ASSC
Runway Status Lights (RWSL) Sustainment
SFO Only
Surface Surveillance Portfolio Sustainment
NAVAIDS Sustainment
RWSL
SMGCS
FID 1319
FID 1319

## Slide 20: Airport Roadmap (3 of 5)
WSDS Sustainment 2
Weather Sensors
Airport Safety
Wake Sep Standards
ELVO
RSA
Runway Safety Area Phase 2
Closely Spaced Parallel Runway Operations
TDWR
WSDS
LLWAS
ASR-9 WSP
WSDS Sustainment 2
FID
650
ASWON Sustainment 2
ASWON Portfolio
JAWS
JAWS Sustainment 1
Weather
Camera (Sys Ops)
ASOS
AWOS-C
DASI
SAWS
SWS
X
FID
1109
Weather Camera Enhancement 1
TDWR Sustainment 3
Weather Camera Program Hawaii
FID
814
TDWR Sustainment 2
Wake Turbulence Re-categorization
FID
1243

## Slide 21: Airport Roadmap (4 of 5)
Control Tower Systems
EFSTS
SMA
DSP
ARMT
AEFS
TFDM Enhancement
TFDM
TFDM
TFDM Sustainment 1
TBFM Enhancement 1
TBFM Sustainment 1
TBFM Enhancement 2
FID
1007
TBFM Sustainment 2
FID 198
TDLS
NME
UIC
X
NME
X
ICMS
NME Sustainment
X
X
X
X
X
TBFM
FID 1317
TFMS
FMDS
Traffic Flow Improvements
Flow Management Improvements
Flow Management Data & Service
TFMS Sustainment 3
FMDS Enhancement 1
FID
1281
FID
1121
FID
1287
TFMS Enhancement 4

## Slide 22: Airport Roadmap (5 of 5)
X
X
ERIDS
E-IDS
IDS4
NIDS
ACE-IDS
X
E-IDS Phase 1
E-IDS Phase 2
E-IDS Phase 3
X
Control Tower Systems
E-IDS
Sustainment
STARS
Terminal Improvements
STARS Sustainment 3
STARS Sustainment 4
STARS E
STARS Sustainment 5
FID 1269
FID
1186
FID
1185
FID 1273
STARS S2
Support Activities
ATN-IP A/G Communication Standards
Development (SC-223, ICAO, AEEC)

## Slide 23: Airport Roadmap: Assumptions
Identifier | Description
APT-01 | The Airports roadmap will focus on systems and services operating and being performed airside at medium/large Airports and does not include functions/infrastructure internal to the Airport (i.e., security, ground transportation, or baggage handling, etc.).
APT-02 | This roadmap is used to provide an evolutionary overview of medium to large Airports and does not convey infrastructure or service implementation specific to an Airport.
APT-04 | Majority of this roadmap's content has been pulled from other roadmaps (i.e., Comm, Surveillance, Weather, etc.) if it is in support of Airport Airside Operations.
APT-07 | Although there are Non-Fed Navigational Aids (NAVAIDS) and facilities located as some Airports, they may not be depicted fully on the Airports Infrastructure Roadmap.
APT-08 | All FTI sub-systems will be assumed by FENS once the TDM-to-IP migration is complete.

## Slide 24: Airport Roadmap: Decision Points (1 of 2)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 25: Airport Roadmap: Decision Points (1 of 2)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 26: Airspace and Procedures
Objective: The Airspace and Procedures roadmap presents an Executive View (EV) of systems and procedures, including associated research projects, with an effect on the large-scale redesign and optimization of major airspace.
For more information, please contact Tamon Honda (Tamon.Honda@faa.gov).

## Slide 27: Airspace & Procedures Roadmap (1 of 2)
Support
Activities
Major Airspace Redesign – Advanced Technology Development and Prototyping
Dynamic Airspace
UTM
LAANC
Concept Development for Integrated NAS Design and Procedure Planning
UAS Flight Information Management
New Entrants Operational Integration
Transition to PBN Operations
Mission Support Systems Supporting Airspace & Procedures
Small UAS Implementation
En Route
Automation
Oceanic Procedures
NSIC
Space Data Integrator (SDI) Prototype Sustainment
NSIC E1
FID 1147
FID 1143
1255
SDI P1
FAA Drone Zone
TBFM
TBFM Enhancement 1
TBFM Enhancement 2
TBFM Sustainment 2
TBFM Sustainment 1
FID
1007
ADS-C
ASEPS
1329
ATOP Enhancement 1
ATOP Enhancement 2
ATOP Sustainment 3
ATOP Enhancement 3
FID
1339
ATOP
Wake Turbulence Recat
Closely Spaced Parallel Runway Ops
FID
1117
FID
1293
Notes: Alt text: This diagram covers the Transition to PBN Operations, En Route Automation. Oceanic Procedures, and New Entrants Operational Integration.

## Slide 28: Airspace & Procedures Roadmap (2 of 2)
Support
Activities
IFPA
APWS
IFPA
NAS Data Warehouse
TARGETS
AIRNAV
DADS
ASAT
CDM NET
INM
IFPA Sustainment 3
FID 1250
Aeronautical Information Services
ADX
AGIS
CTS
NAIMES
AISR
OEAAA
SAMS
FNS
USNS
CARF
TFR Bldr
SDAT
ACS
NASR
EAST
SAACE
AIMM Enhancement 2
AIMM Enhancement 1
1299
FID 1189
FID 122
FNS Sustainment
FID 1267
Dynamic Separation for Wake Mitigation
CSPR Operations – Revised Separation Standards
CSPR Operations – Paired Approach
Wake Turbulence Behavior Research
Reductions in Minimum Radar Separations (MRS)
Wake Re-Categorization Establishment and Enhancement
Notes: Alt text: This diagram represents the systems involved with Airspace and Procedures. In addition, Aeronautical Information Services is represented on this page.

## Slide 29: Airspace & Procedures Roadmap: Assumptions
Identifier | Description
A&P-01 | Airspace Modernization Assumptions Flexibility into any of the agency’s facility plans Future Airspace & NASA research funding is sufficient and provides favorable benefits System Dependencies ADS-B ERAM DataComm
A&P-02 | Integrated Arrival/Departure Airspace (Big Airspace) Assumptions Key Integrated Arrival/Departure Airspace enablers: Extension of 3 Mile Separation & Terminal Procedures Integrated arrival/departure airspace configurations Flexible sector & bi-directional routes published 5 mile lateral spacing for Required Navigation Performance (RNP) enables 5 mile lateral route spacing New voice system (NAS Voice System), leased circuits, and Air-Ground communications channels to handle transition Cost benefits are based on creating X Integrated Arrival/Departure (Big Airspace) facilities, covering X major metropolitan areas Cost analysis based on general assumptions about the concept, not on any detailed requirements or technical solutions Benefits analysis based on extrapolating results from FT simulations to other sites given traffic forecasts and historical weather patterns Sites identified where large TRACON facilities exist could accommodate additional BA operational positions with refurbishment. New buildings would be needed where no large TRACON exists.

## Slide 30: Airspace & Procedures Roadmap: Decision Points (1 of 1)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 31: Automation
Objective: The Automation Roadmap presents an Executive View (EV) of the current automation systems supporting the National Airspace System (NAS) and their enhancement, sustainment or replacement through major development programs and support activities. The Automation Roadmap is intended to convey the major automation program strategy and acquisition decision points as well as program execution through the In-Service Decision. The roadmap serves as a summary view of more detailed plans within each development program.
For more information, please contact Barry Smith (barry.smith@faa.gov).

## Slide 32: Automation Roadmap (1 of 4)
Terminal Precipitation on Glass (TPoG)
Terminal Automation
En Route Automation
Traffic Flow Automation
STARS
ERAM
EDDS
ECG
TFMS
TBFM
STARS E
FMDS
TBFM Enhancement 1
TBFM Enhancement 2
ERAM Enhancement 2
Traffic Flow Improvements
En Route Improvements
Terminal Improvements
ERAM Sustainment 3
ERAM Enhancement 3
STARS Sustainment 3
ERAM Sustainment 4
STARS Sustainment 4
STARS Sustainment 5
TBFM Sustainment 2
ERAM Sustainment 5
Flow Management Improvements
Flow Management Data & Service
TFMS Sustainment 3
FMDS Enhancement 1
SDI P1
TBFM Sustainment 1
FID
1015
IARD
1013
1181
FID
1007
FID 1079
IARD 1212
FID
1281
IID
1279
IARD
1119
FID
1121
IID
1285
FID
1287
IARD
1021
FID
1011
FID 1269
IARD 1271
FID 1273
IARD
1277
IARD
1283
ECG Sustainment
TFMS Enhancement 4
NOP
NSIC
FID 1143
1255
FID
1346
STARS S2
Notes: FMDS DP likely to move right
FMDS E1 likely to move left
FMDS IOC & FOC may shift
TFMS may request removal of IARD#1119 (AEB August 19)
Moving NOP from Automation 3 to Traffic Management (TFMS & FMDS)

## Slide 33: Automation Roadmap (2 of 4)
TDLS
EFSTS
SMA
TFDM
DSP
ARMT
AEFS
ATOP
DOTS+
MEARTS
FDPS
OFDPS
FDIO
ERIDS
E-IDS
IDS4
NIDS
ACE-IDS
TDLS
EFSTS
SMA
DSP
ARMT
AEFS
ATOP
DOTS+
MEARTS
FDPS
OFDPS
FDIO
ERIDS
E-IDS
IDS4
NIDS
ACE-IDS
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
Oceanic and Offshore Automation
Tower Automation
Information Display Systems
TFDM Enhancement
TFDM
ATOP Enhancement 1
ATOP Enhancement 2
Oceanic Improvements
Flight Data Input/Output (FDIO) Sustainment
TFDM Sustainment 1
E-IDS Sustainment
Offshore Automation
E-IDS Phase 3
E-IDS Phase 2
E-IDS Phase 1
ATOP Sustainment 3
ATOP Enhancement 3
TFDM Enhancement
TFDM
ATOP Enhancement 1
ATOP Enhancement 2
Oceanic Improvements
Flight Data Input/Output (FDIO) Sustainment
TFDM Sustainment 1
E-IDS Sustainment
Offshore Automation
E-IDS Phase 3
E-IDS Phase 2
E-IDS Phase 1
ATOP Sustainment 3
ATOP Enhancement 3
IARD
1337
FID
1339
X
X
IARD 1018
FID
1117
IARD
1116
FID 389
FID
1186
FID
1185
IARD
1289
FID
1293
1275
FID 198
IID 1019
IID
1338
FID 1347
Notes: ATOP S3 -> Extend investment to begin in FY2025 (2024 Q4 onward)
ATOP S3 -> Remove IID 1291
ATOP S3 -> Move IARD 1289 to from 2025 Q4 to 2025 Q3
ATOP S3 -> Move FID 1293 to from 2027 Q3 to 2026 Q3
ATOP E3 -> Add IARD 2026 Q3, FID 2027 Q3
Offshore Funding should extend into 2027
MEARTS disposal will be deferred until Offshore Segment 2 is scoped. Remove MEARTS fold into Offshore at this time.
FDPS should fold into Offshore in 2026 Q4 (Disposal X)
OFDPS should fold into Offshore in 2025 Q4 (Disposal X)
Offshore Automation Segment 2 needs to be added as a planned project (which Fiscal years will be funded) w/ FID.
Note: MEARTS software is embedded as a component of the ATOP System. If the MEARTS Offshore systems are retired, we’ll still have MEARTS ATOP Components.

## Slide 34: Automation Roadmap (3 of 4)
PDARS
OPSNET
OASIS
AFSS CONUS
ADX
AGIS
CTS
NAIMES
AISR
OEAAA
SAMS
RMLS
FNS
USNS
AMMS
CARF
TFR Bldr
SDAT
ACS
NASR
EAST
SAACE
Flight Services
Aeronautical Information Services
Mission Support Systems
Monitoring
Flight Information Services
Future Flight Services
AGMG
RMLS Sustainment
CSS – Flight Data
Operational Readiness Value Stream
FNS Sustainment
AIMM Enhancement 2
AIMM Enhancement 1
AMMS
FID 1267
FID 122
IARD 1295
FID 1297
IARD
1187
1299
IID 695
FID 696
FID 1075
FID 1189
IID 1074
X
X
X
X
Future Flight Services – Alaska Automation Capability (AAC)
FID 1341
IARD 1340
DVARS Phase 2
OPSNET Replacement
Notes: ACN in progress to move FNS S from 2021 Q3 to 2021 Q4
AIMM E1 will deliver enhancements to ACS in 2024 Q4.
Move CSSD to support activities. It is not an acquisition project.
Remove merge of CSSD into ACS
CSS-FD request removal of IID 1295, but would like to discuss at the Directors Review.
Change Mission Operation Support Technology to “Flight Information Services”
Move NOP to Traffic

## Slide 35: Automation Roadmap (4 of 4)
Surface Tactical Flow
Flight Object
Separation Automation System Engineering
Strategic Flow Management Application
Information Management
Advanced Methods
Common Trajectory Models
Strategic Flow Management Engineering Enhancement
Common Status and Structure Data
Notes: G-CIP for consideration in Automation Activities:
G01A.07-01 Applications in Support of Air Traffic Control Review w/ Barry, New Controller features for TBO, Recommend Add to Automation
G05A.02-10 Enterprise Concept Development Review w/ Barry, Recommend Reject from Automation
G05A.02-11 Flight Deck Collaborative Decision Making Review w/ Barry, Recommend Reject from Automation, Send to Aircraft
G01M.04-01 Initial Trajectory Based Operations (TBO) Implementation Review w/ Barry, Recommend for Procedures and Facilities

## Slide 36: Automation Roadmap: Assumptions
Identifier | Description
AUTO-01 | Net-centric Enterprise Services will replace designated existing point to point interfaces with a system based on a Service Oriented Architecture providing enhanced data exchange, enhanced flexibility, and enhanced security for FAA Operations Personnel, and airspace users within a common information environment to support NextGen Operational Improvements.
AUTO-02 | ADS-B is a necessary infrastructure element to support Trajectory Based Operations, Flexible Terminal, and High Density Terminal solution sets.
AUTO-03 | Data Communication is a necessary infrastructure element to support Trajectory Based Operations, Flexible Terminal, and High Density Terminal solution sets.
AUTO-04 | Operational Service Units will be responsible for JRC Final Investment Decisions.
AUTO-05 | Policy and standards decisions prescribing the use of hand-held devices for data messaging by General Aviation pilots and aircraft are established.
AUTO-06 | Consistent security management across Data Communication, Automation and SWIM support the evolution.
AUTO-07 | Human-system integration will be conducted during analysis, design, development, and testing of Automation programs.
AUTO-08 | Safety analysis and considerations will be included in all applicable phases of Automation analysis, design, development, and testing and platforms will provide data as required for safety monitoring and analysis.
AUTO-09 | Automation platform designs will support environmental and energy saving initiatives.

## Slide 37: Automation Roadmap: Decision Points (1 of 4)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 38: Automation Roadmap: Decision Points (2 of 4)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 39: Automation Roadmap: Decision Points (3 of 4)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 40: Automation Roadmap: Decision Points (4 of 4)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 41: Communication
Objective: The Communication Roadmap presents an Executive View (EV) of the current communication systems supporting the National Airspace System and their enhancement, sustainment or replacement through major development programs and support activities. The Communications Roadmap is intended to convey the major communication program strategy and acquisition decision points as well as program funding. The roadmap serves as a summary view of more detailed plans within each development program.
For more information, please contact Brent Phillips (brent.phillips@faa.gov).

## Slide 42: Communication Roadmap (1 of 5)
Other Communications
Telecom
FTI
FTI Sustainment 1
NADIN MSN
X
X
ATIS
RCOM
NAS RCOM Sustainment
X
X
FAA Enterprise Network Services (FENS)
IESP
ECG
ASTI
TDM-to-IP Migration
Air-Ground Media Gateway
DMN
NAS RCOM Sustainment 2
BWM
FID 74
FENS
X
FTI Sustainment 2
TDM-to-IP Migration Phase 2
RCL
X
ASTI Sustainment
LDRCL
RTIR
ECG Sustainment
FID
1336
TDM-to-IP Migration ERAM ASTERIX
FID
1342
FID 1354
IID 1353
IARD 1352
RIDS
Runway Incursion Device (RIDS)

## Slide 43: Communication Roadmap (2 of 5)
Voice Switches
Voice Recorders
Legacy Voice Switch Sustainment Portfolio
VSCS/VTABS
RDVS I/II
RDVS IIA
IVSR
X
X
VSBP
NVR
X
NAS Voice Recorder
Legacy Voice Switch Sustainment Portfolio – Voice Switching and Control System (VSCS) Sustainment
X
Voice Communications Systems – Phase 1
FID
1252
1303
Voice Communications Systems – Phase 2
DALR
ICSS Type 3/AFSS
STVS
ETVS
FID
1335
Legacy Voice Switch Sustainment Portfolio – Terminal Voice Switch Sustainment (TVSS)
CCS-W
X
CCS-W R
RDVS TR
ETVS TR
STVS TR

## Slide 44: Communication Roadmap (3 of 5)
A/G Voice
Oceanic Air-Ground
RCE Sustainment
NEXCOM Phase 2
VHF/UHF
A/G Radios v2
ETR UHF/VHF
Transceivers
VHF
Handheld
BUEC
Interference
Detection
Location
And Mitigation
Oceanic HF Voice Service
Oceanic Data Link
Service
RCF
Airport Cable
Loop
RCE
861
863
Airport Cable Loop System Sustainment
Communications Facilities Sustainment
VHF/UHF
A/G Radios v1
VHF/UHF
A/G Radios v2
NEXCOM Phase 3
RCE Sustainment 2
VHF/UHF
A/G Radios v3
X
IARD
1350
FID
1223

## Slide 45: Communication Roadmap (4 of 5)
DCIS Network Services
(S1P1 & S1P2)
Support
Activities
Data Comm Segment 2 –Advanced Services
Tower Enhancements
En Route Enhancements
FID 304
DCIS
Network
Services
(S1P1)
Data Comm Segment 3
IARD
920
IID
921
FID
922
Data Comm DCIS Network
Services (DCNS) Future
DCNS
IARD 1033
Data Comm Air Ground Internet (IP) Gateway
Data Comm Segment 1 Phase 2 (Enhanced Services)
FID 1126
Data Comm Network Service VDL2: Ground
IARD
1127
FID
1129
A/G Data Communications
ATN-IP A/G Communication Standards
Development (SC-223, ICAO, AEEC)
RTCA/EUROCAE Far-Term Data Comms
Standards (NextGen SATCOM)
Data Comm Segment 1 Phase 2 (Full Services)
Research data exchange requirements for exchange between avionics and ground systems
Data Comm
(Tower Service)
FANS
ERAM
TDLS
IPS Equipage Airborne
Data Comm Seg 1
Phase 2 (Initial
En Route Services)
ERAM (EAE 100/200/300/410/500 EAF100)
TDLS v12.6
EAF100/200/300)
IID
1128

## Slide 46: Communication Roadmap (5 of 5)
SWIM Messaging Infrastructure
NEMS
SWIM Segment 2B
SWIM Segment 2C, NEMS TR and 3rd Party
Provider Services
SWIM Segment 3
FID
1218
IARD
1216
SWIM Segment 4
FID
1221
Enhanced SWIM Cloud Service
SWIM Segment 2D
FID
1301

## Slide 47: Communication Roadmap: Assumptions
Identifier | Description
COMM-01 | FENS will become the primary ground-based Voice/Data transport system.
COMM-02 | All domestic flight safety critical A/G communications are over VHF based systems. Advisory communications (e.g. Weather, NAS Status, NOTAMS) can be supported by VHF A/G Communication or by commercial communications services through airborne access to SWIM services.
COMM-04 | Relationship between SWIM and Communications: SWIM Dataflows all leverage NAS OPS IP service and initial SWIM Segment 2 infrastructure is being implemented with FTI & FENS.
COMM-06 | ASTI (ANICS) will not be integrated into FAA Telecommunications Infrastructure contract.
COMM-07 | FIDI TR will develop IP communication protocols between automation systems (e.g. ERAM, terminal clients) which end systems will provide the investment necessary to implement required changes.
COMM-08 | JRC approved a joint IID for DataComm Segment 1 and 2 in 2008; therefore, it is projected that IID for Segment 2 will be waived.

## Slide 48: Communication Roadmap: Decision Points (1 of 2)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 49: Communication Roadmap: Decision Points (2 of 2)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 50: Enterprise Services
Objective: The Enterprise Services Roadmap presents an Executive View (EV) of the evolution of existing and planned enterprise services provided by NAS systems and programs and provides an outline of the major activities, decisions, and milestones. By definition, services are capabilities that exist as processes, applications, infrastructure, or any combination. They are implemented using design principles that support and promote enterprise-wide interoperability, sharing, standardization, federation, awareness, loose coupling, granularity, modularity, abstraction, reuse, and flexibility.
For more information, please contact Lakaisha Ajaegbulemh (lakaisha.ajaegbulemh@faa.gov).

## Slide 51: Enterprise Services Roadmap (1 of 4)
Mission Services
Support Services
NSRR
Common Status and Structure Data
CSS – Flight Data
FID 1075
SWIM Segment 2B
STDDS
SFDPS
NCR
TFM Data
TBFM Enhancement 1
TFDM
TBFM Service
TFDM Service
NEMS
SWIM Segment 2C, NEMS TR and
3rd Party Provider Services
SCDS
SWIM Segment 3
SWIM Segment 4
FID
1221
Enhanced SWIM Cloud Service
NOTAM
Distribution
Service
ACS
FNS Sustainment
AIMM Enhancement 2
CSS-Wx
CSS-Wx
AIMM Enhancement 1
FID 122
FID 1189
CSS-Wx Sustainment 1
FID 1267
Weather Enhancement 1
SWIM Segment 2D
FID
1218
FID 1247
FID
1301
FID
341

## Slide 52: Enterprise Services Roadmap (2 of 4)
SOA Core Services
Security Services
Detect/Respond/ Recover
Identify
Protect
SWIM Segment 2B
RMLS
FNS-NDS
AMMS Phase 1
FID 696
AMMS
Operational Readiness Value Stream

## Slide 53: Enterprise Services Roadmap (3 of 4)
FAA Cloud Services Contract (FCS)
FTI Services
Technical Infrastructure
All Cloud Services available
(SaaS, PaaS, IaaS)
All Cloud Services available
(SaaS, PaaS, IaaS)
Enterprise Function and Service
Co-Location
Services
NAS Government Community Cloud Services (Test and R&D Domains)
Co-Location Services (Rack, Power and Space)
for NAS Systems
Communications Infrastructure (SOA,
NESG, FNTB and FTI R&D)
NAS Program Test Platform
NextGen Testing Domain
NAS Private Cloud Services (Operational IP Domains)
Communications Infrastructure (SOA, NESG, FNTB)
NAS Program Test Platform
NAS Program Operational Services
IESP
Domain Name
Service
Network/ Precision
Time Protocol
FENS

## Slide 54: Enterprise Services Roadmap (4 of 4)
Technical Infrastructure
Support Activities
NAS Enterprise Technical Enhancements
FCS Strategic
Planning and implementation
FCS Domains
IPv6 Enhancements
TDM-IP Transition
Support Services
TDM-to-IP Migration Phase 2
Cloud Requirements and Standards for Contracted Infrastructure Services
ICAO and Other NAS Systems or Customer Requirements
NAS Programs and Systems
NAS Automation Systems
Flight Data Modernization
TDM-to-IP Migration
Enterprise Information Management (EIM)
Cloud Co-Location as A Service
Government Community Common Cloud Services
NAS Private Cloud Services
NAS Enterprise Cloud Services Guidance & Policy

## Slide 55: Enterprise Services Roadmap: Decision Points (1 of 1)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 56: Facilities
Objective: The Facilities roadmap depicts the legacy NAS Facilities and the evolution towards the NextGen Future Facilities environment.
For more information, please contact Lakaisha Ajaegbulemh (lakaisha.ajaegbulemh@faa.gov).

## Slide 57: Facilities Roadmap (1 of 4)
Remote Monitoring
ATCT
TRACONs
ARTCC
ATCT / TRACON Sustainment
              ARTCC & CCF Sustainment
Environmental Remote Monitoring System (ERMS)
Power Systems Sustainment 2
Power Systems
ARTCC Critical & Essential Power System (ACEPS) – ACEPS II Phase 1 & ACEPS II Phase 2
Engine Generators (EGs)
Power Conditioning System (PCS) / Uninterrupted Power Supply (UPS)
Electrical Line Distribution (ELD)
Alternative Energy Systems (AES)
Direct Current System (DC BUS)
Lightning Protection, Grounding, Bonding and Shielding (LPGBS)
Critical Power Distribution System (CPDS)
CCF (4)
Visual Navaids Power Cable (Vis Nav Cable)
NAS Stationary Batteries
Backup and Quality Power Infrastructure
FID
198
Facilities Sustainment Portfolio
Components/Programs Supporting Larger and Single Thread Primary and Backup Power Systems
Critical NAS Facility Backup Power System
FID
1015
FID
1011
FID
1092
Facility Realignment Implementation
Fuel Storage Tank Sustainment
Mobile Asset Sustainment

## Slide 58: Facilities Roadmap (2 of 4)
Facilities Sustainment Portfolio
ATCT/TRACON Replacement Portfolio
ATCT / TRACON Replacement
Long Range Radar (LRR) Infrastructure Sustainment
Facility Security
Risk Management
Unstaffed Infrastructure Sustainment (UIS)
Energy Management and Compliance (EMC)
Environmental Cleanup / HAZMAT
Real Property Disposition
Environmental and Occupational Safety and Health (EOSH)
FAA Employee Housing & Life Safety Shelter System Services
EOSH
FID 1103
Enterprise Facilities Sustainment
FSRM Sustainment 3
ATCT/TRACONs
Charlotte (CLT) ATCT
Greensboro (GSO) ATCT
Teterboro (TEB) ATCT
Charleston (CHS) ATCT
ATCSCC
NEMC
Anchorage (ANC) ATCT/ TRACON
FID
1224
Greenville-Spartanburg (GSP) ATCT
Grand Forks (GFK) ATCT
Unstaffed Infrastructure

## Slide 59: Facilities Roadmap (3 of 4)
NOCC/OCC
Event Manager
AF TechNet
National Test Equipment Sustainment
FTB
NAS Data Warehouse
Technical Operations
WMS/WRS
CAEG
Maintenance
Data Terminal
FPPS
EDMS

## Slide 60: Facilities Roadmap (4 of 4)
Other
WJHTC
William J. Hughes Technical Center Building and Plant Sustainment
William J. Hughes Technical Center Laboratories
MMAC
Aeronautical Center Infrastructure Sustainment
Aeronautical Center Lease
AFSS Alaska
Alaska Flight Service Facility Modernization (AFSFM)
FSS
Oceanic Center
Military ATC
Facilities
ATCSCC
NNCC
AFSS CONUS
NIEC
NEMC
FAA Depot
FPFM
NextGen Laboratories
Airport
Cable Loop
Airport Cable Loop System Sustainment
William J. Hughes Technical Center Laboratories - Flight Program Sustainment
Remote Tower
Flight Program Fleet Modernization (FPFM) Phase 1
Flight Program Fleet Modernization (FPFM) Phase 2
FID
1307
Future Flight Services

## Slide 61: Facilities Roadmap: Assumptions
Identifier | Description
FAC-01 | AJW-2 will need funding for any facilities or infrastructure projects to expand or improve a facility in preparation for a PMO program installation. Refurbish requirements at Large TRACONs and new facilities may be needed to support BA positions. AJW-2 should receive funding and requirements documentation at least 3 years in advance, preferably 4 years, to integrate the project into the Sustainment or New Investment portfolio workplan.
FAC-02 | Projects within the Facilities Sustainment Portfolio that are estimated to cost over $30 million are assigned their own FID decision point.
FAC-03 | Projects within the ATCT/ TRACON Replacement Portfolio that are estimated to cost over $100 million are assigned their own FID decision point.

## Slide 62: Facilities Roadmap: Decision Points (1 of 1)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 63: Human Systems Integration
Objective: The Human Systems Integration (HSI) Roadmap represents strategic air-ground human factors activities and their direct contributions to the evaluation, development, and evolution of NAS infrastructure. The HSI Roadmap depicts the integration of these activities with cross-cutting NAS infrastructure improvements to identify key human factors product transition points. The HSI Roadmap drives the execution of critical path activities by providing timely human factors inputs to NAS infrastructure investments and related programs.
For more information, please contact Bill Kaliardos (bill.kaliardos@faa.gov).

## Slide 64: Human Systems Integration Roadmap (1 of 3)
Human-System Safety / Human Factors Risk Assessments
Enterprise Human Factors Development
NextGen Far-Term ATC Human Error Condition Identification and Mitigation
988
Integrated System Safety Assessment (ISSA)
FAA System Safety Guidance: Development of Feasible Human Error Assessment Method Alternatives
1131
Flight Deck Information Management Baseline - Quantity and Type of Information Available to Air Carrier Pilots (visual, aural, tactile)
Hazard Enterprise Architecture Traceability (HEAT) Safety Data
Safety Management System (SMS) Executive Council/FAA Safety Collaboration Team (SCT)/Safety Data Analysis Team (SDAT)
Information Management
Flight Deck Task Management Issues and Mitigations Baseline – Next Generation Aircraft Systems, Equipment, and Operations
Oceanic HF
Voice Service
Resilient Behaviors
Human Factors Assessment of Communication Technologies and Flight Deck Procedures – Oceanic Operations
Criteria to Evaluate the Effectiveness of Training Recommendations for Use of ATC Systems that Enable TBO
Regional Integration of Time-Based Management Operations and Strategies – Traffic Manager Information Needs Analysis
ATC Evaluation Criteria for Cognitive Workload and Operational Acceptability of Trajectory Option Sets (TOS) in En Route and Terminal
Time & Workload Management
Future Systems, Equipment Operations
Human Factors SMS Support for Acquisition Programs
Human Error and Complex Systems Research
Controller/Pilot Readiness Research
Notes: Alt text: This diagram shows the human performance and capabilities as well as the human centered design projects.

## Slide 65: Human Systems Integration Roadmap (2 of 3)
FAA Order 9550.8 and AMS Policy 4.7 Compliance
Enterprise Human Factors Development
FAA Human Factors Acquisition Working Group
(HFAWG)
Human Factors Recommendations to Address the Flight Deck Impact(s) of Procedure-Based Concepts
Multiple Airport Route Separation
Performance-Based Navigation
Modern ATC Workstation Design and Layout
Human Factors Evaluation of Large ATC Displays
ERAM
Human Readiness Levels (HRL) – Initial Adaptation of Design Evaluation Criteria to Support NAS System Development and Acquisitions
Human Factors SMS Support for Acquisition Programs
Human Factors Acquisition Evaluation Support Research
Procedure Design & Use Research
Notes: Alt text: This diagram shows Support Activities for ATC Information Presentation and Management Activities and FAA Order 9550.8 & AMS Policy 4.7 Compliance

## Slide 66: Human Systems Integration Roadmap (3 of 3)
Novel Display Technologies
Human Factors Evaluation of Emerging HWD Technologies with & without EFVS – Low Visibility Approach and Landing Operations
Monocular vs. Binocular Head-Worn Displays – Initial Human Factors Evaluation During Low Visibility Operations
Novel Controls Technologies
Human Factors Evaluation of Multifunction Controls in Rotorcraft/Vertical Lift Aircraft
1136
Human Factors Evaluation of Multifunction Controls in Fixed-Wing Aircraft
SVGS
Combined Vision Systems – Initial Human Factors Evaluation During Low Visibility Operations
Human Factors Validation of Minimum CDTI Requirements - Dependent Staggered Approaches
CDTI
Avionics Displays
EFVS
HUD
Human Factors Validation of Visual Advantage Values Established for Existing EFVS Models
Enhanced Helicopter Vision Systems: Human Factors Examination of Head-Up/Head-Worn Display Technologies and Concepts
1134
Advanced Vision Systems
Connected Technologies
Anticipated Human Factors Issues with Connected Flight Deck Technologies – Information Source Differentiation
EFB
Human - Machine Interface and Interaction Research
1043
Human Factors Assessment of Aircraft Energy State Awareness Prototype Alternatives
1225
ADS-B Advanced Interval Management
(A-IM)
Notes: Alt text: This diagram shows Support Activities that cover Human System Performance Benefits and Limitations as well as Complexity Reduction and Usability

## Slide 67: Human Systems Integration Roadmap: Assumptions
Identifier | Description
HSI-01 | The execution of program- and project-specific human factors activities are not represented in the HSI Roadmap.
HSI-02 | Human factors integration points represent an identified opportunity for acquisition and procedure development programs to apply specific human factors products.
HSI-03 | Human factors integration points represent the final opportunity for acquisition and procedure development programs to apply specific human factors products.
HSI-04 | Acquisition and procedure development programs will coordinate with ANG-C1 throughout AMS and other processes to identify and address human factors opportunities.
HSI-05 | ANG-C1 will coordinate across programs to identify and address NAS-wide human factors opportunities.

## Slide 68: Human Systems Integration Roadmap Summary
Human Factors Functions | Example Infrastructure Development Influences
Human Error and Complex Systems Research User Centered Design | FAA methods to factor human behavior in system-safety/risk assessments Data to identify and evaluate effectiveness of mitigations for human factors risks Verification of human factors assumptions – e.g., system design, intended function, end-user experience FAA methods to evaluate system design and minimize occurrence of design related errors Criteria to evaluate information display, accessibility, and management based on task urgency/criticality
User Readiness Research Systems, Equipment, Operations | Criteria to determine effect of new systems, operations, and procedures to user tasks, skills, and proficiency needs Data to evaluate effectiveness of electronic/distance learning technology and methods for systems and procedures training Change management criteria to support user acceptance of air/ground capabilities and target utilization rate achievement Criteria for management of unfamiliar situations with highly automated systems and operations
Human Factors Acquisition Evaluation Support Research FAA Order 9550.8 and AMS Policy 4.7 Compliance | Apply evidence-based criteria to support the implementation of human factors tools, processes, and requirements into AMS Evaluate acquisition program requirements and SMS products for human factors Facilitate the integration of human factors with emerging NAS programs: Independent HF assessment of NextGen concepts Verify the integration of human factors with NAS programs: Independent HF ISR checklist sign-off Criteria to evaluate system design for maintainability
Procedure Design and Use Research Complexity, Operational Acceptability, Usability | Criteria to evaluate procedure design alternatives and potential impacts to usability, complexity, operational acceptability, and human performance Develop human factors methods to evaluate the documentation of procedures Verify the operational acceptability of new procedures and develop mitigations as appropriate
Human-Machine Interface and Interaction Research Systems, Displays, Controls | Provide data on the contribution of technology to human performance and safety Inform evidence-based human factors standards, guidelines, requirements, and other documentation for systems, displays, and controls Support technology design reviews, down-selection of alternatives, and response to emerging user interface and interaction issues Data on user interactions with advanced technologies – e.g., understanding of system behavior, logic, limitations, minimum system transparency needs
988
1131
1043
1134
1136

## Slide 69: Human Systems Integration Roadmap: Decision Points (1 of 1)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 70: Navigation
Objective: The Navigation roadmap depicts the establishment, sustainment and evolution of ground-based, satellite-based, and visual navigation systems which enable aircraft to determine and report their position, navigate in accordance with clearances, and efficiently transit the NAS. These systems support conventional and Performance-Based Navigation (PBN) for the NAS and will ensure safe, efficient, and resilient services.
For more information, please contact Lannie Herlihy (lannie.herlihy@faa.gov).

## Slide 71: Navigation Roadmap (1 of 3)
DVT Sustainment - Phase 2
NME
RSA
RSA Phase 2
LDIN
ODALS
VOT
X
NME
X
ICMS
Infrastructure
Safety and Enhancements
REIL
PAPI
Replace VASI with PAPI
NAVAIDS Sustainment
Visual NAVAIDS for New Qualifiers
VASI
ELVO
VORTAC (Includes VOR & TACAN)
Runway Visual Range (Includes CAT I & CAT II/III)
Approach Lighting System Safety Enhancement
Instrument Landing Systems (ILS) (Includes CAT I & CAT II/III)
Distance Measuring Equipment (Includes LP DME & HP DME)
NAVAIDS Sustainment
Replace VASI with PAPI
Visual NAVAIDS for New Qualifiers
Landing and Lighting Portfolio
IARD 1309
Items with a green outline are components of the FAA Minimum Capability List (MCL)
NME Sustainment
IARD 1313
IID 1315
FID 1317
UIC
FID 1311

## Slide 72: Navigation Roadmap (2 of 3)
DVT
VOR
LOC
NDB
TACAN
Environmental: More efficient routes using RNAV/RNP
VORTAC (Includes VOR & TACAN)
MB
RVR
Runway Visual Range (Includes CAT I & CAT II/III)
ALS
Approach Lighting System Safety Enhancement
ILS
Instrument Landing Systems (ILS) (Includes CAT I & CAT II/III)
VOR MON Phase 2
SBAS (WAAS)
WAAS Phase 4B
956
220
FID 1139
GBAS
1199
1198
1200
DME
NextGen DME Support for PBN Strategy
Distance Measuring Equipment (Includes LP DME & HP DME)
Non-Fed
Precision Approach
Cross-Environment
En Route/Terminal/Non-Precision Approach
DVT Sustainment
1227
NAVAIDS Sustainment
ILS – Congressional Add
WAAS Ph4A/4B Transition
1228
1229
1231
239
Phase 1
FID 1196
Phase 2
FID 1311
Phase IV (2014 – 2044)
Segment 1
Segment 2
Segment 3
1071
Items with a green outline are components of the FAA Minimum Capability List (MCL)
1197
VOR MON Ph 2 Implementation
DFMC H-ARAIM MOPS
H-ARAIM IOC
H-ARAIM FOC

## Slide 73: Navigation Roadmap (3 of 3)
NextGen Navigation Engineering
GPS L5 Implementation (DoD)
L2 Sunset
1201
Alternative Navigation
Alternative Timing
GPS
Non-FAA
L5 Dual Freq. FOC
Lighting

## Slide 74: Navigation Roadmap: Assumptions (1 of 2)
Identifier | Description
NAV-01 | FAA is transitioning to PBN operations as the primary capability for daily aircraft operations. PBN is comprised of RNAV and RNP routes and procedures for en route, terminal, and approach & landing operations. This will include: Transition from conventional routes and procedures defined by VOR to RNAV and RNP approaches enabled by GNSS and DME RNAV navigation as a GNSS outage backup. Expansion of Localizer Performance Vertical (LPV) approach procedures enabled by GNSS to provide vertical guidance to all qualifying airports. Enhance the DME network to expand DME RNAV coverage for en route and terminal operations as part of a resilient navigation infrastructure.
NAV-02 | NextGen implementation requires an aggressive transition to services that support Performance-Based Navigation (PBN). This requires: Navigation Strategy to be fully aligned with the FAA’s PBN Strategy, which provides: 1. Clearly defined operational needs and establishment of PBN services for airports and airspace. 2. Close collaboration with the aviation stakeholders
NAV-03 | Need to continue working closely with users and the avionics industry to support additional aircraft equipage to facilitate the transition to PBN operations throughout the NAS The PBN Strategy provides operational benefits that encourage voluntary equipage. Equipage will be in place to support transition to PBN
NAV-04 | PBN strategy includes the need for a resilient navigation infrastructure to maintain safety, security, and capacity and preclude significant economic impact during GNSS outages. This includes: Establishing a VOR MON to ensure continued en route and approach operations during GNSS disruptions for aircraft that are not equipped for DME RNAV. Providing infrastructure to enable DME RNAV aircraft to continue to their destination served by an ILS approach during GNSS disruptions. Sustain ILSs to support approach and landing operations during GNSS disruptions. Investigate alternate PNT capabilities to provide resiliency for evolving operational needs.

## Slide 75: Navigation Roadmap: Assumptions (2 of 2)
Identifier | Description
NAV-05 | FAA has no current plan to acquire Federal GBAS systems. GBAS installations will depend on individual airports’ interest and investment.
NAV-06 | Department of Defense will maintain a GPS constellation consistent with the Standard Positioning Service. Continue close coordination with DOD to ensure GPS continues to meet the PNT needs for aviation.
NAV-07 | The Navigation Roadmap provides an infrastructure strategy to support all phases of flight.
NAV-08 | At the end of CY27, the DME and VORTAC CIP will no longer be managed in the Landing and Lighting Portfolio and will be transitioned into the DVT Sustainment Program Phase 2.

## Slide 76: Navigation Roadmap: Decision Points (1 of 2)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 77: Navigation Roadmap: Decision Points (1 of 2)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 78: New Entrants
Objective: The New Entrants roadmap provides a consolidated timeline of activities and investments, both active and planned, required to integrate UAS and Commercial Space into the NAS.
For more information, please contact Mike Hritz (mike.hritz@faa.gov).

## Slide 79: New Entrants – Commercial Space
Objective: The New Entrants Commercial Space Roadmap presents an Executive View (EV) of the current systems supporting the National Airspace System (NAS) and their enhancement, sustainment or replacement through major development programs and support activities. The Commercial Space Roadmap is intended to convey the major program strategy and acquisition decision points as well as program execution through the In-Service Decision. The roadmap serves as a summary view of more detailed plans within each development program.
For more information, please contact Magda Batista-Carver (magda.batista-carver@faa.gov).

## Slide 80: New Entrants – Commercial Space Roadmap (1 of 2)
Support Activities
All SVO
Services & Infrastructure
Standards / Certification Development
Policy Assessment / Development
Operational Concept Exploration
Operational Concept Validation
Operational Research
Services
NSIC
Space Data Integrator (SDI) Prototype Sustainment
Space Integration Capabilities for the ATO
NSIC E1
FID 1147
IARD 1145
IID 1146
FID 1143
1255
SDI P1
1351
Notes: Alt text: This diagram shows NSIC and enhancements as well as secondary Support Activities.

## Slide 81: New Entrants – Commercial Space Roadmap (2 of 2)
Develop capability for display of safety/status information on launch/reentry ops to the flight deck
All SVO
Real-time Aircraft Hazard Area (AHA) Generation
Technical Demonstrations and Prototyping
Technical Opportunity Investigation
Technical Concept Validation
Concept Development
Services & Infrastructure
Launch and Reentry Vehicle Operator On-Boarding to the SDI Proof of Concept
Operator Planning Portal Assessment
Advanced Surveillance Capabilities
Research and develop capabilities to streamline coordination process
Space Integration Capabilities Space-Operator Generated Hazard Volumes Concept Demonstration/Prototyping

## Slide 82: New Entrants – Commercial Space Roadmaps: Assumptions
Identifier | Description
CS-01 | NSIC Implementation is dependent on TFMS/ ERAM/ STARS development bandwidth

## Slide 83: New Entrants – Commercial Space Roadmap: Decision Points (1 of 1)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 84: New Entrants – Unmanned Aircraft System
Objective: The Unmanned Aircraft Systems (UAS) Roadmaps provide a consolidated timeline of activities and investments, both active and planned, required to integrate UAS operations into the NAS. The current iteration of the roadmaps reflect initial pre-implementation efforts and AMS acquisitions. In the next few years, the FAA UAS community plans to coordinate with the program offices associated with impacted NAS systems and services currently identified and described in the “Integration of Civil Unmanned Aircraft Systems (UAS) in the National Airspace System (NAS) Roadmap” (July 2018). Additionally, the FAA UAS community will collaborate with applicable program offices in requirements allocations decisions, which will be reflected in future versions of this roadmap.
For more information, please contact Scott Ginsburg (scott.ginsburg@faa.gov).

## Slide 85: New Entrants – UAS Roadmap (1 of 4)
Support
Activities
ATM
UTM
Support
Activities
Small UAS Implementation
Support
Activities
UAS Flight Information Management
FAA Drone Zone
NAS Domain – Infrastructure
ETM
Support
Activities
UAS Upper Airspace
UAM
UAS Urban Air Mobility
LAANC
UAS Concept Validation and Requirements Development (CVRD)
Identify New Requirements for NAS Automation in Support of UAS in ATM Airspace
Remote ID

## Slide 86: New Entrants – UAS Roadmap (2 of 4)
NAS Domain – Infrastructure
Automation
ISS
Airspace / Procedures
Surveillance
Comm
Navigation
Airport
LAANC
These roadmap pages intend to depict potential domains that can be impacted by UAS integration. As UAS requirements are identified, allocated, and approved by governing boards, the impacted domains will be updated.

## Slide 87: New Entrants – UAS Roadmap (3 of 4)
NAS Domain – Infrastructure
Safety
Other
HSI
Facilities
Weather
Aircraft
Enterprise Services
These roadmap pages intend to depict potential domains that can be impacted by UAS integration. As UAS requirements are identified, allocated, and approved by governing boards, the impacted domains will be updated.

## Slide 88: New Entrants – UAS Roadmap (4 of 4)
Research
Standards Certification and Development
Command and Control (C2)
DAA-Surveillance
Airworthiness
UAS SC-228
962
SC-147
DAA-Φ2 MOPS
UTM USS to USS Standard
Urban Air Mobility (UAM) Concept Development
Upper Class E Traffic Management – ConOps Development
Identify and Standardize Unique UAS Airworthiness (AW) : VLOS Urban Ops, Focus Area 1
Identify and Standardize Unique UAS Airworthiness (AW) : BVLOS, Focus Area 3
Advanced Air Mobility Beyond Visual Line of Sight (BVLOS) NAS Evaluation (AAM BNE)
ETM Engineering Planning and Analysis
UPP Phase 2
Unmanned Navigation Capabilities
Unmanned Aviation System Weather (UAS-Wx)
UAS BEYOND Program

## Slide 89: New Entrants – UAS Roadmap: Assumptions
Identifier | Description
UAS-01 | The Authoritative references used to populate the CY2019 UAS roadmaps are: “Integration of Civil Unmanned Aircraft Systems (UAS) in the National Airspace System (NAS) Roadmap” (July 2018) CIP data provided by AFN and Draft CIP FY 2020 – FY2024 UAS Integration Research Plan (2017 – 2022) Other NAS Infrastructure Roadmaps UAS Stakeholder inputs
UAS-02 | Although impacted NAS systems are identified and documented in “Integration of Civil Unmanned Aircraft Systems (UAS) in the National Airspace System (NAS) Roadmap” (July 2018), requirements allocations have not been discussed and accepted by the organizations that manage the impacted systems. Upon coordination and decisions made about UAS requirements allocation, ANG-B intends to update this roadmap to depict acquisitions that will deliver UAS-related requirements in the future.
UAS-03 | Research and Development: The full scope of research and development activities are too numerous and complex to depict on this format of the roadmaps. Roadmap stakeholders are encouraged to reference pages 10, 35 and 38 of “Integration of Civil Unmanned Aircraft Systems (UAS) in the National Airspace System (NAS) Roadmap” (July 2018) to understand the full scope of FAA UAS R&D efforts.

## Slide 90: New Entrants – UAS Roadmap: Decision Points (1 of 1)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 91: Safety
Objective: The Safety Roadmap reflects various aspects of the Safety Risk Management (SRM) process that support enterprise level, concept/capability level, and system level safety. It supports the execution of safety assessments on potential safety issues that span multiple FAA organizations, through cross-cutting stakeholder collaboration, and provides FAA decision-makers with pertinent information to make risk-based decisions. The Safety Roadmap integrates SRM elements with NAS operations and system acquisition milestones through the development of key safety assessments, procedures, guidance, policy and requirements that support the NextGen Enterprise System.
For more information, please contact Chris Scott (chris.j.scott@faa.gov).

## Slide 92: Safety Roadmap (1 of 3)
Aviation Safety Information Analysis and Sharing (ASIAS)
OARS Phase 1
Support
Activities
Safety Risk Management (SMS) Executive Council/FAA Safety Collaboration Team (SCT)/ Safety Data Analysis Team (SDAT)
ASIAS v3.0
ASIAS v4.0
ASIAS
HIRMT
Integrated System Safety Assessment (ISSA)
CEDAR
FALCON II
Timelines are an approximation and are subject to change.
SSMT 2.0 Wake Vortex Safety System (WVSS)
SSMT 3.0
Near-real Time Integrated Safety Modeling Capability
General Aviation and Rotorcraft Metrics/Tools Development
Hazard Enterprise Architecture Tool (HEAT)
X
X
RSTS
X
System Safety Management Transformation (SSMT)
Automated Safety
Data Tools
Safety Tracking Systems
ATO Portal
Safety Applications
X
RAP Tools/BAR
X
Processed
Track Services
X
Business Object
OARS
OARS Phase 2
Mission Support Systems
OARS Phase 3
OARS Phase 4
OARS Ph. 4 Planning
OARS Ph. 3 Planning
SMTS
X
CV Tool
X
ARIA
SSMT 2.0 Situational Investigation Tool Kit for Analysis & Reporting (SITAR)
SSMT 2.0 Airport Surface Anomaly Investigation Capability (ASAIC)
OARS Ph. 2 Planning
ASIAS Data Fusion
SSMT 2.0 Integrated Safety Assessment Model (ISAM)

## Slide 93: Safety Roadmap (2 of 3)
Support Activities (SRM)
Support Activities
(SRM)
Safety Systems Supporting SMS
Support Activities
Support Activities
(SRM)
Integrated System-
of-Systems Model-
Based Assessment
Mid-Level Concept/Capability
Safety Assessments
AMS Safety Assessments
(Investment Analyses
Readiness Decision)
Safety Analyses to Support AMS (Safety Assessments)
(Details available upon request to ANG-B3, SSMT and ASIAS in support of AMS Safety Assessments)
Air Traffic Organization Safety Risk Management/Safety Assurance
Safety Management System (SMS) Executive Council/FAA Safety Collaboration Team (SCT)/Safety Data Analysis Team (SDAT)
Integrated System Safety Assessment (ISSA)
Hazard Enterprise Assessment Tool (HEAT) Safety Data
Human Factors SMS Support for Acquisition Programs
System Safety Management Transformation (SSMT)
OARS
Conduct and Maintain Service Level Safety Assessments
Develop and Maintain Safety Data Policy, Governance & Standards,
Risk-Based Decision Making, 8000.369B, 8040.4B and 1000.37
Far-Term NextGen Integrated SRM Planning & Analysis

## Slide 94: Safety Roadmap (3 of 3)
Support Activities
Support Activities
Enterprise Human Factors Development
Human-System Performance Risk Reduction
NextGen ATC / Tech Ops Error Management and Complex Systems
NextGen Flight Deck Human Error Reduction
Human Performance and Safety Activities
Human Performance and Safety
Safety Management System (SMS) Executive Council/FAA Safety Collaboration Team (SCT)/Safety Data Analysis Team (SDAT)
Integrated System Safety Assessment (ISSA)
Hazard Enterprise Architecture Tool (HEAT) Safety Data
Human Factors SMS Support for Acquisition Programs
NextGen Far-Term ATC Human Error Condition Identification and Mitigation
988
FAA System Safety Guidance: Development of Feasible Human Error Assessment Method Alternatives
1131

## Slide 95: Safety Roadmap: Assumptions
Identifier | Description
SAFE-01 | ASIAS is part of the FAA Mission Support EA. It is depicted on the Safety Infrastructure Roadmap for coordination purposes since: It will require NAS data. It will provide safety data and tools for the NAS
SAFE-02 | SMS Implementations for other LOBs are part of the FAA Mission Support EA. These activities are depicted on the Safety Infrastructure Roadmap for coordination purposes.
Notes: 95

## Slide 96: Safety Roadmap: Decision Points (1 of 1)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 97: Surveillance
Objective: The Surveillance roadmap depicts the sustainment of legacy surveillance systems and the evolution towards the NextGen environment.
For more information, please contact James Baird (james.baird@faa.gov).

## Slide 98: Surveillance Roadmap (1 of 4)
Cooperative Surveillance - Broadcast Services
ADS-B In Applications
ADS-B Services & Baselines
Advanced Surveillance Enhanced Procedural Separation
Includes Space-Based ADS-B
IARD
1323
ADS-B In Appl - Interval Management Planning
ADS-B
ADS-R
ADS-B Advanced Interval Management
(A-IM)
ADS-B Baseline Services Future Segments
ADS-B Enhancement
FIS-B
TIS-B
ADS-C
Advanced Surveillance Enhanced Procedural Separation (ASEPS)
SBS Monitor
ADS-B Out
Avionics
ADS-B In
Avionics
1213
1213
IARD
1233
FID
1234
ADS-B Baseline Services Future Segments Phase 2
FID
1240
FID
1232
FID
1327
1329
IARD
1348
FID
1349

## Slide 99: Surveillance Roadmap (2 of 4)
Cooperative Surveillance – Multilateration Systems
Cooperative Surveillance – Beacon Systems
Co-located Mode S and ATBCI-6 systems replaced by SENSR; all others replaced by MSBRS
ASR-11 MSSR function replaced by MSBRS; PSR function replaced by ANSR
Select Mode-S systems replaced by WAM
FID 1321
Interfaces
SENSR
Terminal and En Route Surveillance Technical Refresh Portfolio
ATCBI-6
ASR-11
MODE S
Mode S Beacon Replacement System Phase 1A
ATCBI-5
WAM
SENSR
FID 1103
MSBRS
Mode 3/A/C
Transponder
Mode S
Transponder
TCAS
ACAS X
ACAS-X
IARD
1239
ATCBI-6 Sustainment
ASR-11 Sustainment 4
ACAS-X Segment 2
ATCBI-5 Sustainment 2
1165
Mode S Beacon Replacement System Phase 1B
ATCBI-5 Sustainment 1
ASR-11 Sustainment 3
FID 806
MODE S Sustainment 4
CD-2
Mode S Beacon Replacement System Phase 2
FID 1103
FID 1343
FID 1103
FID
1327

## Slide 100: Surveillance Roadmap (3 of 4)
DoD/DHS funded/FAA maintained
DoD/DHS funded/FAA maintained
X
Non-Cooperative Surveillance
Interfaces
ASR-11 MSSR function replaced by MSBRS; PSR function replaced by ANSR
ASR-9 Sustainment 4
SENSR
ASR-11
ASR-11 Sustainment 3
FID 806
ASR-9
ASR-9 Sustainment 3
CV-4400
TDX-2000
CTD
ASR-8
ARSR-4
Common ARSR
ASR-8 Sustainment 1
SENSR
FID 1103
Terminal and En Route Surveillance Technical Refresh Portfolio
IARD
1239
Airspace Non-Cooperative Surveillance Radar (ANSR)
ANSR
IARD
1236
IID
1237
FID
1238
ASR-11 Sustainment 4

## Slide 101: Surveillance Roadmap (4 of 4)
SFO Only
Support
Activities
Surface and Approach
Evaluate Impact of Wind Turbine
Interference on Radar Systems
Airport Surface Detection Equipment (ASDE) Sustainment
PRM E-SCAN
ASDE-X
ASDE-3
ASSC
RWSL
Runway Status Lights (RWSL) Sustainment
Surface Surveillance Portfolio Sustainment
FID 1103
FID 1319
FID 1319
Surveillance Portfolio Analysis
IARD
1236
IARD
1323
FID 1321
IARD
1236
FID 1343

## Slide 102: Surveillance Roadmap: Assumptions
Identifier | Description
SURV-01 | Backup to mitigate loss of on-board GPS positioning source for ADS-B is required: a) Retain all en route beacons (~150 monopulse systems) b) Retain limited set of terminal beacons (or WAM) based on need (Core 30 airports for resiliency, other airports based on economic analysis and ADS-B equipage rates) c) All terminal non-cooperative surveillance coverage areas are retained for safety purposes d) Selected terminal surveillance systems that will no longer be required will be divested starting in CY2020
SURV-02 | a) The Spectrum Efficient National Surveillance Radar (SENSR) will replace the following legacy surveillance systems: 1) ARSR-4 and CARSR non-cooperative surveillance systems 2) En route ATCBI-6 and Mode S cooperative surveillance systems b) SENSR will NOT replace any other surveillance system c) SENSR will NOT impact the provision of any ADS-B related service (ADS-B, ADS-R, TIS-B, FIS-B) d) The scope of the SENSR program may change, at which point the roadmaps will be updated accordingly
SURV-03 | The Mode-S Beacon Replacement System (MSBRS) will replace all remaining beacon systems (including the MSSR portion of ASR-11) that are not replaced by SENSR or WAM
SURV-04 | The ASR Replacement system will replace all remaining ASR-8, ASR-9, and ASR-11 (PSR portion) systems

## Slide 103: Surveillance Roadmap: Decision Points (1 of 2)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 104: Surveillance Roadmap: Decision Points (1 of 2)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 105: Weather
Objective: The Weather Roadmap presents an Executive View (EV) of weather-related acquisition activities and the changes to these activities that exist within the Weather enterprise architecture (EA) domain (projects and programs) of the Federal Aviation Administration (FAA). The Weather Roadmap provides the evolution of the weather architecture via AMS milestones and related activities (e.g., aviation weather research, demonstrations, and other agency activities) necessary to achieve the performance objectives and capabilities to support NextGen. As a perspective of the changes in the NAS operational environment, the Weather Roadmap reflects major Weather interdependencies to support (or be supported by) other domains in the NAS enterprise architecture as depicted in NAS Roadmaps.
For more information, please contact Patrice Kone (patrice.kone@faa.gov).

## Slide 106: Weather Roadmap (1 of 4)
WSDS Sustainment 2
Airspace Non-Cooperative Surveillance Radar (ANSR)
ASWON Sustainment 2
WSDS
Non-FAA Sensors
Surface Weather Observing Service
ASWON Portfolio
WHDE
Radars
NEXRAD
LLWAS
PIREPS
Lightning Data
ACFT Wx
Sensors
LIDAR
JAWS
Non-Fed AWOS
ASR-9 WSP
TDWR
JAWS Sustainment
Weather
Camera (Sys Ops)
NEXRAD Sustainment 2
ASOS
AWOS-C
DASI
SAWS
SWS
FID
1015
Wind Shear Service
Weather Channel
ASR-8
ASR-9
ASR-11
X
FID
1109
WSDS Sustainment 2
TDWR Sustainment 3
LIDAR Sustainment
FID
1107
IARD
1106
IARD
648
FID
650
Weather Camera Enhancement 1
IARD
1241
TDWR Sustainment 2
NEXRAD Sustainment 3
ANSR
FID
1238
Weather Camera Program Hawaii
FID
814
NEXRAD Sustainment 1
IARD
812
FID
1243

## Slide 107: Weather Roadmap (2 of 4)
NOAA Satellite
Data Services
NOAA/NWS
Wx Services
Dissemination
Processing
Non-FAA Services
WARP RAMP
CIWS Prototype
X
X
X
NWP
NextGen Weather Processor (NWP)
NWP Sustainment 1
BCD
1333
WARP WINS & FBWTG
Common Support Services Wx
CSS-Wx
IARD
448
X
X
X
BCD
1331
X
X
X
ALDARS
WMSCR
ADAS/RASP
CIWS CDDS
CREWS
CSS-Wx Sustainment 1
FID 1247
IARD 1245
IID 1246
Non
FAA
ITWS VOLPE
ITWS NFU
WIFS
OPC Prototype
Vendor Wx Data Services
ITWS
Weather Enhancement 1
NWP Enhancement 2
Vendor Wx Data to WARP
Vendor Wx Data to Flight Services
Vendor Wx Data to TFMS (FMDS)
Vendor Wx Data to FIS-B
Observations & Forecast products from CWSUs, Aviation Wx Center, NG ITWS, NWS WFOs, NCEP
Vendor Satellite Imagery (Visual and IR) & products
IARD
1344
Terminal Precipitation on the Glass (TPoG)
FID
1346
IARD
452
IID
453
FID
143
FID
341
IID
1345

## Slide 108: Weather Roadmap (3 of 4)
Translation
Convection
Improved Icing
Establish New Verification Methods
Enhanced Ceiling and Visibility Translation
Port Translation S/W into NWP
IFI Translation Demo
Wind
IARD
448
FID
1109
Offshore Precipitation Capability
Wx Obs Improvement (WOI) Winter Wx Precipitation
Turbulence
CONUS GTG NowCast (GTG-N)
IARD
448
FID
143
FID
143
FID
341
FID
341
Terminal Precipitation on the Glass Detailed Concept Assessment
Winter Weather Translation

## Slide 109: Weather Roadmap (4 of 4)
Validate Wx Performance Rqm’ts for TBFM/IMRO – Bravo Seg.
NWS
Wx Modeling & Simulation
Ceiling & Visibility (C&V)
IARD
448
Validate Wx Performance Rqm’ts for TBFM, CATMT, IMRO, SM, PBN WP5 - Charlie Segment
IARD
448
Visibility Estimates from Weather Cams
Wx Standards
FID
1243
IARD
448
FID
143
FID
341
Definition of Weather Standards for UAS Flight
Draft Amendments to ICAO Annex 3
Weather Transition (Wx Trans)

## Slide 110: Weather Roadmap: Assumptions (1 of 3)
Identifier | Description
WX-01 | Ongoing NextGen Weather functional & performance requirements validation may result in new/emerging requirements in NextGen Weather Architecture.
WX-02 | FAA Terminal Weather Sensor 'Sustainment' divides into four functional divisions: A) weather radar, B) Wind Shear Detection Systems (WSDS), C) Aviation Surface Weather Observing Systems (ASWON), and D) other. A) includes TDWR with Sustainment 2 extended to 2024; a Sustainment 3 and future Sustainments needed. B) WSDS Sustainment 2 addresses LLWAS and WSP obsolescence issues to allow sustainment beyond 2030. C) Includes the ASWON Portfolio which has been standardized into ASOS / AWOS-C / SWS. Decommissioned are all legacy AWOS (FAA upgraded them to AWOS-C), AWSS, WEF, and C&G DASI systems via the ASWON Sustainment Program. During ASWON Sustainment 2 all SAWs will be replaced with SWS as well as address future obsolescence of the ASWON portfolio systems to allow sustainment beyond 2030. D) Includes both JAWS (turbulence detection) and LIDAR (dry microburst detection) systems that exist as unique systems at single airports. LIDAR is O&M funded.
WX-03 | 1) ADAS-Rehost serves as consolidating access point for Weather observations by NWP/CSS-Wx Enhancements 2) WMSCR communications functionality and ADAS RASP, including ALDARS functionality to be subsumed by NWP/CSS-Wx Enhancements.
WX-05 | The NAS Weather Infrastructure Portfolio incorporates R&D Research to Ops (RTO) with new weather products/information with increased forecast accuracy/frequency to NAS Users with minimal architectural/infrastructure change. Moreover, RTO Support Activities will further augment support to NAS operational decision-making by including weather “translation” as well as “uncertainty” capabilities.

## Slide 111: Weather Roadmap: Assumptions (2 of 3)
Identifier | Description
WX-06 | Weather processing functions converge into NextGen Weather Processor (NWP) that will be implemented in several phases. Initial NWP implementation (formerly called NWP WP1) provides NWP-Central services replacing prototype CIWS functions including 0-2 hour weather capability and 2-8 hour convective forecast (CoSPA) capability. The Weather and Radar Processor (WARP) Radar Acquisition and Mosaic Processor (RAMP) function is subsumed in initial NWP implementation. NWP/CSS-Wx Enhancements hosts Wx R&D algorithms matured since initial implementation baseline freeze including improved Convective and Translation algorithms. NWP Enhancement 2 will implement NextGen weather Far-term capabilities. ITWS (including ITWS VOLPE and ITWS NFU) will continue providing terminal weather information for pacing airports.
WX-08 | NAS Infrastructure Portfolio will supply weather information at user-specified resolution, both spatially and temporally. NWP will host the first NextGen mid-term "weather translation" product, e.g., Weather Avoidance Fields (WAF) to TFM of convective weather constraints to aircraft movement in NAS airspace (delivered by CSS-Wx). WAFs may be machine-translated into NAS operational impacts by User DSTs. NWP Enhancement 1 and Enhancement 2 will add additional weather translation products e.g. Turbulence, Wind, Ceiling, Visibility, and Precipitation.
WX-09 | Products developed from requirements allocated to NWS, will likely be delivered to FAA via NWS’ NextGen IT Web Services (NGITWS). These products will be accessible via CSS-Wx initial implementation, or via CSS-Wx Enhancements.
WX-10 | To address emerging anti-icing regulations and to mitigate automated surface observing shortfalls at Level A/B airports, FAA will continue to evaluate R&D opportunities in sensor and algorithm development to improve precipitation discrimination (freezing/frozen/liquid including ice pellets and drizzle). Once mature and tested to meet all FAA automated sensor requirements, in conjunction with NWS this capability will be integrated into ASOS/AWOS-C to support aircraft and airport ground anti/de-icing operations.
WX-11 | Weather observation/forecast R&D will continue to be periodically evaluated for maturity to determine whether new/improved functionality should be implemented.

## Slide 112: Weather Roadmap: Assumptions (3 of 3)
Identifier | Description
WX-12 | FAA will transmit validated Weather Forecast Performance Requirements to NWS after having successfully completed associated supporting activity and validation in Wx Modeling & Simulation. When FAA requirements are finalized and allocated to NWS, if NWS doesn't have the current capability to meet the requirement for weather forecasts (e.g., icing, convection, or C&V), FAA R&D funding will be provided to develop algorithms to fulfill those requirements for subsequent implementation by NWS.
WX-13 | The SENSR Executive Steering Group down-scoped the SENSR Program by removing all FAA Short-Range ATC Weather, FAA Terminal Weather, and NOAA / NWS Long-Range Weather requirements prior to IID (Surveillance Roadmap DP 1102). SENSR will NOT replace NEXRAD, TDWR, ASRs, or WSP (a WSDS provider).
WX-14 | New imagery channels, sounding data, and lightning data from Satellite Data Services will be baselined between 2017 Q3 and 2022 Q4. Requirements need to be identified and research conducted on integrating new weather satellite sensor data into FAA systems
WX-15 | ADS-B Weather (ADS-Wx) data (becoming available in 2022) is a component of ADS-B v3 data stream provided by the SBS network, will be distributed by CSS-WX Enhancements along with data from other weather sources in providing comprehensive weather information to its NAS Users.

## Slide 113: Weather Roadmap: Decision Points (1 of 2)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 114: Weather Roadmap: Decision Points (2 of 2)
DP # | Target Date CY | High Priority | Primary Domain | Type | Name

## Slide 115: Appendix A Acronym List

## Slide 116: Appendix A, Acronym List (1 of 6)
 | Acronym |  | Definition |  | Acronym |  | Definition
 | 4D |  | Four dimensional (x, y, z, t) |  | ANICS |  | Alaska NAS Interfacility Communication System
 | AC |  | Advisory Circular |  | ANSP |  | Air Navigation Service Provider
 | ACARS |  | Addressing, Communicating, and Reporting System |  | AOC |  | Airline Operations Center
 | ACAS |  | Airborne Collision Avoidance System |  | APNT |  | Alternative Positioning, Navigation, and Timing
 | ACE-IDS |  | ASOS Controller Equipment-Information Display System |  | APWS |  | AeroNav Products Workflow System
 | ACI |  | Aircraft Cybersecurity Initiative |  | ARMT |  | Airport Resource Management Tool
 | ACL |  | Airport Cable Loop |  | ARSR |  | Air Route Surveillance Radar
 | ACS |  | Aeronautical Common Service |  | ARTCC |  | Air Route Traffic Control Center
 | ACFT |  | Aircraft |  | ARTS |  | Automated Radar Terminal System
 | ADAS |  | AWOS Data Acquisition System |  | ASAT |  | Airspace Simulation and Analysis for Terminal Procedures
 | ADF |  | Automatic Direction Finder |  | ASDE |  | Airport Surface Detection Equipment
 | ADS-B |  | Automatic Dependent Surveillance-Broadcast |  | ASEPS |  | Advanced Surveillance Enhanced Procedural Separation
 | ADS-C |  | Automatic Dependent Surveillance-Contract |  | ASOS |  | Automated Surface Observing System
 | ADS-R |  | Automatic Dependent Surveillance-Rebroadcast |  | ASR |  | Airport Surveillance Radar
 | AEFS |  | Advanced Electronic Flight Strips |  | ASSC |  | Airport Surface Surveillance Capability
 | AF |  | Airway Facility |  | ASTI |  | Alaska Satellite Telecommunications Infrastructure
 | AFSM |  | Alaska Flight Service Modernization |  | ASWON |  | Aviation Surface Weather Observation Network
 | AFSS |  | Automated Flight Service Station |  | ATC |  | Air Traffic Control
 | A/G |  | Air-to-Ground |  | ATCBI |  | Air Traffic Control Beacon Interrogator
 | AGIS |  | Airports Geographic Information System |  | ATCSCC |  | David J. Hurley Air Traffic Control System Command Center
 | AHA |  | Aircraft Hazard Area |  | ATCT |  | Airport Traffic Control Tower
 | AIM |  | Aeronautical Information Management |  | ATIS |  | Automated Terminal Information System
 | AirNav |  | Airport and Navigational Aids Database |  | ATM |  | Air Traffic Management
 | AISR |  | Aeronautical Information System Replacement |  | ATO |  | Air Traffic Organization (FAA)
 | ALDARS |  | Automated Lightning Detection and Reporting System |  | ATOP |  | Advanced Technologies and Oceanic Procedures
 | ALS |  | Approach Lighting System |  | AW |  | Airworthiness
 | ALSIP |  | Approach Lighting System Improvement Program |  | AWCS |  | Airport Wireless Communications Systems
 | AMASS |  | Airport Movement Area Safety System |  | AWOS |  | Automated Weather Observing System
 | AMMS |  | Automated Maintenance Management System |  | BCD |  | Baseline Change Decision
 | AMS |  | Acquisition Management System |  | BUEC |  | Backup Emergency Communications

## Slide 117: Appendix A, Acronym List (2 of 6)
 | Acronym |  | Definition |  | Acronym |  | Definition
 | BVLOS |  | Beyond Visual Line of Sight |  | DC |  | Data Communications or DataComm
 | BWM |  | Bandwidth Manager |  | DCNS |  | Data Communication Network System
 | C2 |  | Command and Control |  | DHS |  | Department of Homeland Security
 | C&V |  | Ceiling & Visibility |  | DME |  | Distance Measuring Equipment
 | CAEG |  | Computer-Aided Engineering Graphics |  | DMN |  | Data Multiplexing Network
 | CARF |  | Central Altitude Reservation Function |  | DoD |  | Department of Defense
 | CAT |  | Category |  | DOTS+ |  | Dynamic Ocean Track System Plus
 | CATMT |  | Collaborative Air Traffic Management Technologies |  | DP |  | Decision Point
 | CCF |  | Combined Control Facility |  | DSP |  | Departure Spacing Program
 | CCS |  | Conference Control System |  | DUATS |  | Direct User Access Terminal Service
 | CD |  | Common Digitizer |  | DVARS |  | Data, Visualization, Analysis, and Reporting System
 | CDM NET |  | Collaborative Decision-Making Network |  | EA |  | Enterprise Architecture
 | CDTI |  | Cockpit Display of Traffic Information |  | ECG |  | En Route Communications Gateway
 | CFE |  | Communication Facilities Enhancement |  | EDDS |  | ERAM Data Distribution System
 | CIP |  | Capital Investment Plan |  | EDMS |  | Electronic Document Management System
 | CIWS |  | Corridor Integrated Weather System |  | EFB |  | Electronic Flight Bag
 | CONOPS |  | Concept of Operations |  | EFSTS |  | Electronic Flight Strip Transfer System
 | CONUS |  | Conterminous United States |  | EFVS |  | Enhanced Flight Vision System
 | CRDR |  | Concepts and Requirements Definition Readiness |  | E-IDS |  | Enterprise Information Display System
 | CS |  | Commercial Space |  | ELT |  | Emergency Locator Transmitter
 | CSPR |  | Closely Spaced Parallel Runways |  | ELVO |  | Enhanced Low Visibility Operations
 | CSS-Wx |  | Common Support Services-Weather |  | ERAM |  | En Route Automation Modernization
 | CTD |  | Common Terminal Digitizer |  | ERIDS |  | En Route Information Display System
 | CTS |  | Coded Time Source |  | ETR |  | Emergency Transceiver
 | CY |  | Calendar Year |  | ETVS |  | Enhanced Terminal Voice Switch
 | DAA |  | Detect and Avoid |  | EWD |  | Enhanced WINS Dissemination
 | DADS |  | Digital Aeronautics Database System |  | FAA |  | Federal Aviation Administration
 | DALR |  | Digital Audio Legal Recorder |  | FANS |  | Future Air Navigation System
 | DASI |  | Digital Altimeter Setting Indicator |  | FBWTG |  | FAA Bulk Weather Telecommunications Gateway
 | DBRITE |  | Digital Bright Radar Indicator Tower Equipment |  | FCS |  | FAA Cloud Service

## Slide 118: Appendix A, Acronym List (3 of 6)
 | Acronym |  | Definition |  | Acronym |  | Definition
 | FDIO |  | Flight Data Input/Output |  | IDS |  | Information Display System
 | FDPS |  | Flight Data Processing System |  | IESP |  | Integrated Enterprise Services Platform
 | FFS |  | Future Flight Services |  | IFIA |  | International Flight Inspection Aircraft
 | FID |  | Final Investment Decision |  | IFPA |  | Instrument Flight Procedure Automation
 | FIM |  | Flight Interval Management |  | IFR |  | Instrument Flight Rules
 | FIP |  | Forecast Icing Product |  | IID |  | Initial Investment Decision
 | FIS-B |  | Flight Information Service-Broadcast |  | ILS |  | Instrument Landing System
 | FMS |  | Flight Management System |  | INM |  | Integrated Noise Model
 | FNS |  | Federal NOTAM System |  | IOC |  | Initial Operating Capability
 | FOC |  | Full Operational Capability |  | IP |  | Internet Protocol
 | FOMS |  | Flight Operations Management System |  | IPDS |  | Instrument Procedure Development System
 | FPPS |  | Facility Power Panel Schedule |  | IRU |  | Inertial Reference Unit
 | FSRM |  | Facility Security Risk Management |  | ISAM |  | Integrated Safety Assessment Model
 | FSS |  | Flight Service Station |  | ISD |  | In-Service Decision
 | FTI |  | FAA Telecommunications Infrastructure |  | ISS |  | Information Systems Security
 | FY |  | Fiscal Year |  | ITWS |  | Integrated Terminal Weather System
 | GA |  | General Aviation |  | IVSR |  | Interim Voice Switch Replacement
 | GBAS |  | Ground-Based Augmentation System |  | JAWS |  | Juneau Airport Wind System
 | GNSS |  | Global Navigation Satellite System |  | JRC |  | Joint Resources Council
 | GPS |  | Global Positioning System |  | L5 |  | A third civil signal on Navstar GPS (1176.45 MHz)
 | HFDL |  | High Frequency Data Link |  | LAANC |  | Low Altitude Authorization and Notification Capability
 | HSI |  | Human/Systems Integration |  | LDIN |  | Lead In Light System
 | HUD |  | Head-Up Display |  | LDRCL |  | Low-Density Radio Communications Link
 | H/W |  | Hardware |  | LED |  | Light-Emitting Diode
 | IAM |  | Identity Access Management |  | LIDAR |  | Laser Identification Detection and Ranging
 | IARD |  | Investment Analysis Readiness Decision |  | LLWAS |  | Low-Level Windshear Alert System
 | ICAO |  | International Civil Aviation Organization |  | LOC |  | Localizer
 | ICMS |  | Integrated Control and Monitoring System |  | LOS |  | Line of Sight
 | ICSS |  | Integrated Communications Switching System |  | LP/HP |  | Low Power/High Power

## Slide 119: Appendix A, Acronym List (4 of 6)
 | Acronym |  | Definition |  | Acronym |  | Definition
 | LRR |  | Long Range Radar |  | NGSS |  | Next Generation Satellite System
 | LVO |  | Launch Vehicle Operations |  | NIDS |  | NAS Information Display System
 | MAMP |  | Mobile Asset Management Program |  | NIEC |  | NextGen Integration and Evaluation Capability
 | MASPS |  | Minimum Aviation System Performance Standards (RTCA) |  | NME |  | NAVAIDs Monitoring Equipment
 | MASR |  | Mobile Airport Surveillance Radar |  | NMR |  | NADIN MSN Rehost
 | MB |  | Marker Beacon |  | NNCC |  | National Network Control Center
 | MDCRS |  | Meteorological Data Collection and Reporting System |  | NOAA |  | National Oceanic and Atmospheric Administration
 | MDR |  | Multi-Mode Digital Radios |  | NOCC |  | National Operations Control Center
 | MEARTS |  | Microprocessor En Route Automated Radar Tracking System |  | NOP |  | National Offload Program
 | MMAC |  | Mike Monroney Aeronautical Center |  | NOTAM |  | Notice to Airmen
 | MODE S |  | Mode Select |  | NSWRC |  | NextGen Surveillance and Weather Capability
 | MOPS |  | Minimum Operational Performance Standards (RTCA) |  | NVR |  | NAS Voice Recorder
 | MPAR |  | Multi-Function Phased-Array Radar |  | NVS |  | National Airspace System Voice Switch
 | NACGS |  | National Aeronautical Charting Group System |  | NWP |  | NextGen Weather Processor
 | NADIN MSN |  | National Airspace Data Interchange Network Message Switched Network |  | NWS |  | National Weather Service
 | NADIN PSN |  | National Airspace Data Interchange Network Packet Switched Network |  | OARS |  | Operational Analysis and Reporting System
 | NAIMES |  | NAS Aeronautical Information Management Enterprise Systems |  | OASIS |  | Operational and Supportability Implementation System
 | NAS |  | National Airspace System |  | Obs |  | Observation
 | NASA |  | National Aeronautics and Space Administration |  | OCC |  | Operations Control Center
 | NASE |  | NAS Adaptation Services Environment |  | ODALS |  | Omnidirectional Approach Lighting System
 | NASR |  | National Airspace System Resource |  | OEAAA |  | Obstruction Evaluation/Airport Airspace Analysis
 | NAVAID |  | Navigational Aid |  | OFDPS |  | Offshore Flight Data Processing System
 | NBSC |  | NextGen Backup Surveillance Capability |  | Ol |  | Operational Improvement
 | NCR |  | NAS Common Reference |  | OPC |  | Offshore Precipitation Capability
 | NDB |  | Non-Directional Beacon |  | Ops |  | Operations
 | NEMC |  | Network Enterprise Management Center |  | OPSNET |  | Operations Network
 | NEMS |  | NAS Enterprise Messaging Service |  | ORS |  | Obstacle Repository System
 | NEXCOM |  | Next-Generation VHF A/G Communication System |  | PAPI |  | Precision Approach Path Indicator
 | NEXRAD |  | Next Generation Weather Radar |  | PBN |  | Performance-Based Navigation
 | NextGen |  | Next Generation Air Transportation System |  | PDARS |  | Performance Data Analysis and Reporting System

## Slide 120: Appendix A, Acronym List (5 of 6)
 | Acronym |  | Definition |  | Acronym |  | Definition
 | Ph. |  | Phase |  | SDI |  | Space Data Integrator
 | PIREPS |  | Pilot Reports |  | SE |  | System Engineering
 | PRM |  | Precision Runway Monitor |  | Segmt. |  | Segment
 | PS3 |  | Power Systems Sustained Support |  | SENSR |  | Spectrum Efficient National Surveillance Radar
 | Qn |  | Calendar Quarter n (n = 1-4) |  | SFDPS |  | SWIM Flight Data Publication Service
 | R&D |  | Research & Development |  | SLEP |  | Service Life Extension Program
 | RCE |  | Radio Control Equipment |  | SMA |  | Surface Movement Advisor
 | RCF |  | Radio Communication Facility |  | SMGCS |  | Surface Movement Guidance and Control System
 | RCL |  | Radio Communications Link |  | SOA |  | Service Oriented Architecture
 | RCOM |  | NAS Recovery Communications |  | SOCC |  | Security Operations Control Center
 | RDVS |  | Rapid Deployment Voice Switch |  | SSMT |  | System Safety Management Transformation
 | REIL |  | Runway End Identifier Lights |  | STARS |  | Standard Terminal Automation Replacement System
 | RMLS |  | Remote Maintenance and Logging System |  | STDDS |  | SWIM Terminal Data Distribution System
 | Rn |  | Release n (n = 1, 2,…N) |  | STVS |  | Small Tower Voice Switch
 | RNAV |  | Area Navigation |  | Svc. |  | Service
 | RNP |  | Required Navigation Performance |  | SVGS |  | Synthetic Vision Guidance System
 | RSA |  | Runway Safety Area |  | SVO |  | Space Vehicle Operations
 | RTCA |  | Radio Technical Committee for Aeronautics |  | SVS |  | Synthetic Vision System
 | RV |  | Re-entry Vehicle |  | S/W |  | Software
 | RVR |  | Runway Visual Range |  | SWIM |  | System-Wide Information Management
 | RVSM |  | Reduced Vertical Separation Minima |  | SWS |  | Surface Weather System
 | RWSL |  | Runway Status Lights |  | TACAN |  | Tactical Air Navigation
 | SAA |  | Special Activity Airspace |  | TAMR |  | Terminal Automation Modernization and Replacement
 | SAMS |  | Special Use Airspace Management System |  | TARGETS |  | Terminal Area Route Generation Evaluation and Traffic Simulation
 | SATCOM |  | Satellite Communication Network |  | TAWS |  | Terrain Awareness and Warning System
 | SAWS |  | Stand-Alone Weather Sensor |  | TBFM |  | Time-Based Flow Management
 | SBAS |  | Satellite-Based Augmentation System |  | TBO |  | Trajectory-Based Operations
 | SBS |  | Surveillance and Broadcast Services |  | TCAS |  | Traffic Alert and Collision Avoidance System
 | SCT |  | Safety Collaboration Team |  | TCF |  | Terminal Convective Forecast
 | SDAT |  | Sector Design and Analysis Tool |  | TDLS |  | Tower Data Link Services

## Slide 121: Appendix A, Acronym List (6 of 6)
 | Acronym |  | Definition |  | Acronym |  | Definition
 | TDM |  | Time-Division Multiplexing |  | VoIP |  | Voice Over Internet Protocol
 | TDWR |  | Terminal Doppler Weather Radar |  | VOR |  | VHF Omnidirectional Range
 | TFDM |  | Terminal Flight Data Manager |  | VOR MON |  | VOR Minimum Operating Network
 | TFM |  | Traffic Flow Management |  | VORTAC |  | VOR with TACAN
 | TFM-I |  | Traffic Flow Management - Infrastructure |  | VOT |  | VHF Omnidirectional Range Test
 | TFMS |  | Traffic Flow Management System |  | VSBP |  | Voice Switch Bypass
 | TFR Bldr |  | Temporary Flight Restriction Builder |  | VSCS |  | Voice Switching and Control System
 | TIS-B |  | Traffic Information Service-Broadcast |  | VTABS |  | VSCS Training and Backup System
 | TR |  | Technology Refresh |  | WAAS |  | Wide-Area Augmentation System
 | TRACON |  | Terminal Radar Approach Control |  | WAM |  | Wide Area Multilateration
 | TSO |  | Technical Standard Orders |  | WARP |  | Weather and Radar Processor
 | TVSR |  | Terminal Voice Switch Replacement |  | WEF |  | Wind Equipment Series F
 | TWIP |  | Terminal Weather Information for Pilots |  | WINS |  | Weather Information Network Server
 | UAS |  | Unmanned Aircraft System |  | WJHTC |  | William J. Hughes Technical Center (FAA)
 | UIC |  | Universal Interlock Controller |  | WME |  | Wind Measuring Equipment
 | UIS |  | Unstaffed Infrastructure Sustainment |  | WMS |  | WAAS Master Station
 | URET |  | User Request Evaluation Tool |  | WMSCR |  | Weather Message Switching Center Replacement
 | USNS |  | United States NOTAM Service |  | WPn |  | Work Package n (n = 1, 2, …N)
 | UTM |  | Unmanned Traffic Management |  | WSDS |  | Wind Shear Detection Services
 | VASI |  | Visual Approach Slope Indicator |  | WSP |  | Weather System Processor
 | VHF/UHF/HF |  | Very High Frequency/Ultra High Frequency/High Frequency |  | WT |  | Wake Turbulence
 | VLOS |  | Visual Line of Sight |  | WTMA |  | Wake Turbulence Mitigation for Arrivals
 | VNAV |  | Vertical Navigation |  | Wx |  | Weather

## Slide 122: Appendix B Change History

## Slide 123: Aircraft
Synchronized elements with other Roadmaps
Updated Support Activities based on RTCA milestones and schedules

## Slide 124: Airport
Synchronized elements with other Roadmaps
Updated to reflect the most recent CIP

## Slide 125: Airspace & Procedures
Added “Reductions in Minimum Radar Separations (MRS)” Support Activity from PLA Mapping and removed completed Support Activities
Aligned secondary elements to primary roadmaps

## Slide 126: Automation
TFMS Sustainment 3 will continue, but Flow Management Data and Services (FMDS) initiated to replace TFMS. TFMS E5 is cancelled
STARS SP1, a Tech Refresh Portfolio, reverted to regular STARS Sustainment 4 project
AIMM inserted FNS Sustainment prior to AIMM E1
Offshore Automation Strategic Decision 2021Q1 adjusted acquisition strategy

## Slide 127: Communications
DataComm Enhanced Services:
  DP 1126 (FID) - DataComm Seg1Ph2 shifted two years out
Remote Telecommunications Infrastructure Replacement (RTIR):
  New addition to the Roadmap. RTIR was started in 2020 and will continue through 2025
Small Tower Voice Switch – Technology Refresh(STVS-TR):
  Added STVS Technology Refresh (STVS-TR). This will extend the planned end date for the system from 2026 to 2035
TDM-to-IP:
  Extended program end date to 2030

## Slide 128: Enterprise Services
Added Operational Readiness Value Stream (to better reflect moving towards service-based architecture)
The secondary decision point for SWIM Segment 2C & 3 was updated
The Enterprise Services Roadmap synchronized elements from the Automation, Communications and Weather Roadmaps
The Enterprise Services roadmap has no primary DPs

## Slide 129: Facilities
  Updated DP #1092 (N90 Sustainment)
  Updated DP #1224 (ATCT/TRACON Replacement Portfolio)
  Updated DP#1307 (Flight Program Fleet Modernization FID 2)
  Moved Mobile Asset Sustainment to page 1
  Synchronized elements from Automation & Surveillance Roadmaps

## Slide 130: Human Systems Integration
  Human Factors Integration: Consolidated ATC/Tech Ops and flight deck portions of the roadmap to provide an integrated view of human factors research functions and investments.
  Technology Labels: Added labels to each HSI Roadmap diagram to group similar air/ground human factors information by technology topics.
  Added 8 new Support Activities:
  Controller/Pilot Readiness Research:
    Flight Deck Task Management Issues and Mitigations Baseline – Next Generation Aircraft Systems, Equipment, and Operations
    ATC Evaluation Criteria for Cognitive Workload and Operational Acceptability of Trajectory Option Sets (TOS) in En Route and Terminal
    Regional Integration of Time-Based Management Operations and Strategies – Traffic Manager Information Needs Analysis
    Criteria to Evaluate the Effectiveness of Training Recommendations for Use of ATC Systems that Enable TBO
  Human Factors Acquisition Evaluation Support Research:
    Human Readiness Levels (HRL) – Initial Adaptation of Design Evaluation Criteria to Support NAS System Development and Acquisitions
  Human-Machine Interface and Interaction Research:
    Combined Vision Systems – Initial Human Factors Evaluation During Low Visibility Operations
    Monocular vs. Binocular Head-Worn Displays – Initial Human Factors Evaluation During Low Visibility Operations
    Anticipated Human Factors Issues with Connected Flight Deck Technologies – Information Source Differentiation

## Slide 131: Navigation
At the end of CY27, the DME and VORTAC CIP will no longer be managed in the Landing and Lighting Portfolio and will be transitioned into the DVT Sustainment Program Phase 2.
Added WAAS milestones related to H-ARAIM implementation

## Slide 132: New Entrants – Commercial Space
  Added Support Activity “Space Integration Capabilities Space-Operator Generated Hazard Volumes Concept Demonstration/Prototyping”
  Updated SDI P2 to NSIC E1

## Slide 133: New Entrants – UAS
Extended dates for Support Activities:
  Identify and Standardize Unique UAS Airworthiness (AW) : BVLOS, Focus Area 3
  Identify and Standardize Unique UAS Airworthiness (AW) : VLOS Urban Ops, Focus Area 1
Added New Support Activities
  AAM BNM Project Kickoff and Use Case Development
  ETM Engineering Planning and Analysis
  Unmanned Navigation Capabilities Assessment
  UPP Phase 2 Systems Engineering

## Slide 134: Safety
Updated OARS to better reflect funding profile and depiction as a System
Updated depiction of systems being subsumed into the updated Phase of OARS

## Slide 135: Surveillance
Cooperative Surveillance – Broadcast Services:
  Added decision points for ADS-B Baseline Services Future Segments Phase 2
Cooperative Surveillance – Beacon Systems:
  Adjusted programs and decisions within the Terminal and En Route Sustainment Portfolio to ensure system coverage until deployment of the MSBRS
Surface and Approach Systems:
  Added decisions for Extended Surface Surveillance and the ASDE-3 Surface Movement Radar Replacement

## Slide 136: Weather
  Approval of CSS-Wx and NWP Baseline Change Decisions (BCDs)
  Removal NEXRAD Sustainment II IARD and FID
  Addition of Terminal Precipitation on the Glass (TPoG) SD, IARD, and FID)*
  * Pending 10/26 coordination meeting with Rob Hunt on TPoG implementation strategy.

## Slide 137: Appendix C Diagram Updates