Thirteenth Meeting of the Cross Polar Trans East Air Traffic Management Providers’ Work Group (CPWG/13)

(Reykjavik, Iceland, 19-22, 2012)

Agenda Item 4:	Provide Status on CPWG/12 Actions

- EXPANSION OF THE OCEAN21 (OC21) AUTOMATION PLATFORM TO

- ANCHORAGE CENTER’S ARCTIC FLIGHT INFORMATION REGION (FIR)

- (Action Item CP06-02)

(Presented by the Federal Aviation Administration)

SUMMARY This paper presents information on the plan to expand the use of the Ocean21 Oceanic Automation System within Anchorage Center’s Airspace.

- Introduction

1.1	This is an update on the expansion of the Ocean21 (OC21) automation platform at Anchorage Air Route Traffic Control Center (ARTCC).

2.	Adaptation

  - Seventy five percent of the required adaptation work is completed.

3.	Hardware Upgrades

3.1	Hardware updates to the External Communications Server Simulator were completed in March 2012. Anchorage ARTCC can now utilize 16 radar feeds for either simulated testing or can use live radar for targets of opportunity testing. Previously they were limited to five radar feeds.

3.2	Expansion of the Dynamic Simulator (DYSIM) needed for additional controller training was completed in May of 2012.

4.	Software Testing

4.1	Anchorage ARTCC is currently testing early versions of Build T20 software.

4.2	The North American Interface Control Document (NAM ICD) testing for the automated coordination of aircraft with Vancouver Area Control Center (ACC) took place in May 2012 utilizing NavCanada’s off-line test system in Ottawa and the FAA’S test system at the William J. Hughes Technical Center in Atlantic City, NJ.

5.	Schedule

5.1	Phase One of this plan will transition Anchorage ARTCC Sectors 63, 68 and 69 to the OC21 automation platform creating a seamless OC21 to OC21 boundary between Anchorage and Oakland ARTCCs. The Phase One transition date is now scheduled for May 2013. Phase Two, the Arctic region, is scheduled for the Fall of 2013.

6.	Program Funding

6.1	A February 2011 Federal Aviation Administration (FAA) budget review resulted in the Facilities and Equipment (F&E) program ending in fiscal year (FY) 2015, and a reduction of $24 million dollars of the remaining $37.9 million planned from FY2012 to FY2015.

6.2	In August 2011 a decision was made to re-allocate $1.2 million from the Advanced Technologies & Oceanic Procedures (ATOP) program to support the En Route Automation Modernization (ERAM) ICAO Flight Plan 2012 development.

6.3	In November 2011 the ATOP budget was further reduced from $8 million to $4 million for FY2012.  In January 2012, a decision was made to defer the $4 million cut mentioned above from FY2012 to FY2014 and FY2015.

6.5	What do the F & E budget impacts mean to the program?

6.5.1	A number of National Change Proposals (NCPs) that have already been prioritized will not be implemented.  Future NCPs will be limited to $1 million dollars (approximately 2000 to 2500 software lines of code).  The ability to support new initiatives cannot be supported by the remaining ATOP F&E baseline.

6.5.2	New sources of funding from other FAA program budgets will be needed after 2015 to continue Ocean21 functional enhancements.

7.	Recommendation

- The Meeting is invited to note the information provided.