Thirteenth Meeting of the Cross Polar Trans East Air Traffic Management Providers’ Work Group (CPWG/13)

(Reykjavik, Iceland - 19-22 June 2012)

Agenda Item 6:	Communications, Navigation, Surveillance (CNS) and Air Traffic Management (ATM) issues

- STATUS OF FAA IMPLEMENTATION OF AMENDMENT 1 TO PROCEDURES FOR AIR NAVIGATION SERVICES/AIR TRAFFIC MANAGEMENT (PANS/ATM)

(Presented by the Federal Aviation Administration)

SUMMARY This paper provides an update and status of United States (U.S.) implementation of Amendment 1 to the PANS/ATM.

- Introduction

  - This paper provides an update and status of United States (U.S.) implementation of Amendment 1 to the PANS/ATM.  Attachment 1 provides the details of the systems impacted, expected schedule, and approaches to testing and training.

- System Development and Testing

  - All affected systems have been identified and all system changes are underway or complete.

  - Internal (system testing and FAA to FAA interface testing) is underway for most systems; all system testing is expected to be complete by June 2012 with the exception of the OASIS system used for Flight Services in Alaska, which is expected to complete in July.

  - Automated international interface and flight plan filer interface testing has begun on a limited basis.  Testing is proceeding with systems that are complete and in some cases with systems that are partially complete but in a “known state” that is useful to support testing.  Contacts have been set up with the relevant States (see Attachment for the list of automated interfaces) and planning is underway.  The majority of international interface testing is expected to take place in July and August of 2012.

  - Flight plan filer testing will be done at the FAA Technical Center in New Jersey, using a capability to connect a testbed with an updated system to the Aeronautical Fixed Telecommunications Network (AFTN).  This testing should commence in April or May 2012.  As systems are deployed to operational facilities, flight plan filer testing with some facilities will be conducted prior to entering transition mode.

- Training

  - Training development has begun and is scheduled to complete in time to start training personnel in June 2012.

  - Training will have both general and system-specific and position-specific aspects.  The training for air traffic controllers will be task oriented, focusing on the data that they will need to use or modify.

- Procedures and Documentation

  - Air Traffic Control Procedures (FAA Order 7110.65), Flight Services Procedures (FAA Order 7110.10), the Aeronautical Information Publication (AIP), the Aeronautical Information Manual (AIM), ICAO Flight Plan filing instructions, and other documents were evaluated for impacts.  Document Change Proposals are in process for required changes.

  - The Attachment describes specific changes that were made.

- Deployment and Transition

  - Systems containing the updated software will be deployed as they are ready and will be spread out over several months.  All sites are expected to have upgraded software by September 2012.

  - As systems are deployed, each facility will conduct interface testing with relevant adjacent States and with flight plan filers.

  - The FAA will declare readiness for transition mode - when filers can shift all operations to NEW format if desired - when all sites are ready, expected in mid-September 2012.

- Transition to NEW

  - Assuming operations in transition mode are successful, and filers are filing NEW format flight plans, the FAA will switch to NEW mode and start rejecting PRESENT flight plans on 15 November 2012.

  - The FAA proposes that users begin filing NEW flight plans only on 12 November, to ensure only NEW format flight plans are present on 15 November, and to allow proper evaluation that everyone has successfully transitioned to operations using NEW flight plans.

- Action by the Meeting

  - The meeting is invited to note the information provided.