## Slide 1
Edmonton Area Control Centre presentation to the CROSS POLAR WORKING GROUP “Edmonton ACC Airspace Amalgamation”
Reykjavik, Lýðveldið Ísland June 19-22, 2012
Presented by:
Bryon Carlson
Edmonton ACC North High & Shield Supervisor
Notes: <number>
<number>
<number>
Also Present at CPWG –
Robert Fiege, Manager Area Control Centre Operations, Edmonton

## Slide 2: Background
NAV CANADA has always desired airspace efficiency improvements.
In Summer, 2010, Edmonton ACC was tasked with re-analyzing it’s air space.
Various options were examined, including the transfer of some Edmonton airspace to YUL &/or YWG.

## Slide 3: Background
Internal Edmonton proposal was put forward in September, 2011 to amalgamate “North High” and “Shield” specialties.
Plan was approved in January, 2012.
Cross-training began in February, 2012.
42 Controllers & 9 Supervisors in amalgamated specialty.
All 9 Supervisors fully cross-trained as of May, 2012.
7 Controllers fully cross-trained & 6 Controllers partially cross-trained as of Summer 2012.
~1200 “person-days” of cross-training through to completion of the project in 2014.

## Slide 4: How to make this work??
Comprehensive, individual cross-training plans were created, reflecting individual experience levels.
Some low level (below FL290) airspace was delegated to “North Low” specialty as of May 31, 2012. This follows the theory of “putting like with like” – low level and high level standards are very different.
High traffic density airspace in the Calgary-Edmonton-Ft. McMurray corridor to be delegated elsewhere within Edmonton ACC. This will separate “arrival/departure” control, on a small radar scale, from pure “enroute” control, on a large scale.

## Slide 5: Background
~ 2.5 million miles2 of airspace in amalgamated specialty.
~ 1.4 million miles2 (~56%) is radar and/or ADS-B.
Flight count = 400+ flights/day.
Extremely large specialty in area, but with low traffic density.
45 VHF frequencies.
6 main radar & 8 ADS-B sources, combined with 10 radar sources fed from adjacent jurisdictions.
Coordination with 7 external units.

## Slide 6
14 internal sectors
With 30+ consolidation combinations, including a few commonly used:

## Slide 7
Original boundary between specialties
The outline of the amalgamated specialty on a “North American” scale…

## Slide 8
…and on a “Northern Hemisphere” scale…..

## Slide 9: Customer benefits
Staff availability & flexibility. Instead of staffing two separate specialties with inherent duplications, only one specialty will be staffed with no duplication.
Will allow human resources to be efficiently focused where needed.
Flights will be controlled on a large scale, with one ATC unit controlling a flight, vs. many ATC units being involved.
Using Polar flights as an example, Edmonton can control a flight for 30% of total air time, and Edmonton’s control actions can have a “down-line” effect for up to 50% of an individual flight’s air time.

## Slide 10
Examples of harmonized traffic planning and management:
NAT – harmonized planning and management
vs. fragmented planning and management
PAC & Polar: harmonized planning and management
vs. fragmented planning and management

## Slide 11
Amalgamated Northern airspace has numerous published airways and waypoints.

## Slide 12
Reducing the number of published airways and waypoints reduces training time and knowledge retention - with a definite customer service benefit!
Reference to separate CPWG/13 presentation: “NAV CANADA Northern Airspace Plan.”

## Slide 14: Questions/Discussion
??