# Thirteenth Meeting of the Cross Polar Trans East Air Traffic Management Providers’ Work Group (CPWG/13)

(Reykjavik, Iceland, 19-22 June 2012)

Agenda Item 4:	Provide Status on CPWG/12 Actions

NAT PERFORMANCE BASED COMMUNICATION AND SURVEILLANCE IMPLEMENTATION PLAN

(Action Item #CP11-01)

(Presented by the Federal Aviation Administration)

Summary

This paper provides information on the NAT Performance Based Communication and Surveillance Implementation Plan to implement required communication performance (RCP) and required surveillance performance (RSP) in the North Atlantic Region.

# Introduction

## Reductions in separations and other operational initiatives are predicated on communication, surveillance and navigation performance. With appropriate communication and surveillance performance, improved route conformance monitoring and intervention capability would reduce the effects of gross navigation errors (GNEs), large height deviations (LHDs), and speed deviations.

## Given the current ground system implementations, an air traffic control (ATC) facility can potentially misapply air traffic services to an operator or aircraft type. This is most likely occurring today where reduced separations are applied in other regions, because the qualification criteria for communication and surveillance are not formally applied. These Required Communication Performance (RCP) and surveillance criteria are not prescribed and there is no formal approval mechanism in place to ensure that the end-to-end system complies with the criteria.

## The 47th Meeting of the North Atlantic Systems Planning Group (NAT SPG/47) in June 2011 endorsed the following Conclusion:

NAT SPG Conclusion 47/5 –	Approval of the NAT RCP and ADS-C Surveillance Performance based operations implementation plan

That:

- the NAT RCP and ADS-C surveillance performance based operations implementation plan be endorsed;

- the NAT IMG

- include the management and execution of the NAT RCP and ADS-C surveillance performance based operations implementation plan on its work programme; and

- provide updates to the NAT SPG.

## Since NAT SPG/47, the 40th Meeting of the NAT Implementation Management Group (NAT IMG/40) in Paris, France, 7 to 10 May 2012, agreed on some amendments based on inputs from the NAT IMG sub-groups and took several decisions to support execution of the plan.  This paper provides information, which was taken from the Summary of Discussions (SOD) of the NAT IMG/40 Meeting, dated 12 May 2012.

## The NAT IMG was provided with a summary of the proposed amendments to the NAT RCP and ADS-C Surveillance Performance Based Operations Implementation Plan.  The meeting agreed with changing the title of the plan to the NAT Performance Based Communication and Surveillance Implementation Plan.

## The NAT IMG agreed with the proposed modifications, noted the status of the on-going activities, and decided the following:

NAT IMG Decision 40/15  –	Approval of the revised NAT Performance Based Communication and Surveillance Plan

That the ICAO Regional Director, Europe and North Atlantic, take appropriate measures for circulation of the revised NAT performance based communication and surveillance implementation plan as provided at [Attachment A].

## Further details on the structure of the NAT SPG and subgroups, as well as the FAA delegates, is shown at Attachment B.

## The NAT IMG was informed that the NAT Safety Analysis and Reduced Separation Implementation Group (NAT SARSIG) received a briefing in March 2012 concerning the purpose and application of the RCP concept, which had been helpful in increasing its understanding of RCP.  Therefore, the NAT IMG agreed that it would be beneficial if the NAT IMG and all of its contributory groups receive the same type of briefing, as appropriate to their work programmes and decided the following:

NAT IMG Decision 40/16 –	RCP Briefings

That the United States is invited to provide briefings from a Required Communication Performance (RCP) subject matter expert to the NAT IMG and its appropriate contributory bodies.

## The NAT IMG requested its Communication, Navigation and Surveillance Group (NAT CNSG) to provide a clear indication of whether current implementations in each NAT Oceanic Control Area were meeting RCP 240 and RSP 180 specifications, and if not, to identify what aspects of the system’s performance were not compliant with the requirements and what possible effect those shortcomings might have on the implementation of reduced separation minima.  The NAT IMG decided the following:

NAT IMG Decision 40/17 –	Assessment of compliance with RCP 240

That the NAT Communications, Navigation and Surveillance Group (NAT CNSG):

a)	provide a clear indication of whether or not Required Communications Performance (RCP) 240 is being met in each NAT Oceanic Control Area currently being assessed;

b)	identify, if RCP 240 is not being met, what aspects of the system’s performance are not compliant with the RCP 240 specification; and

c)	determine the potential effects of those shortcomings on the implementation of reduced separation minima.

## The NAT IMG also agreed that a Proposal for Amendment to the NAT Regional Supplementary Procedures (SUPPs) (Doc 7030) was needed to prescribe the performance specifications for communication and surveillance to support reduced lateral and longitudinal separation minima.

## The NAT Performance Based Communication and Surveillance Implementation Plan supports operational improvements where an acceptable level communication and surveillance performance is essential for safe and efficient air traffic operations.  The plan is targeting a “full” implementation date of February 2015, at which time RCP and Required Surveillance Performance (RSP) specifications will be prescribed in Regional SUPPs.

# DISCUSSION

- Although there are no global requirements at this time for RCP and RSP specifications to support reductions in lateral and longitudinal separation, some the ANSPs from Canada, Iceland, Norway and the United States control airspace in the NAT Region and will apply the procedures described in this paper.

- It is anticipated that global requirements for RCP and RSP will be put into place in the future.

- It would be appropriate for the CPWG to further study the NAT Performance Based Communication and Surveillance Implementation Plan and determine whether such a plan should be developed for the Arctic airspace.

# RECOMMENDATION

- The meeting is invited to:

  - note the information presented in this paper and Attachment A;

  - consider the need for a similar plan for the Arctic airspace; and

  - consider requesting the FAA to provide a subject matter expert (SME) briefing at CPWG/14.

Attachment A (Draft SOD for NAT IMG/40, Appendix M refers)

NAT Performance Based Communication and Surveillance Implementation Plan
(paragraph 6.31 refers)

Associated with the NAT data link services in support of RLongSM and RLatSM.

|  | TASKS | COMPLETE BY | STATUS | LEAD | Remarks |
| --- | --- | --- | --- | --- | --- |
|  | GENERAL PROJECT DEVELOPMENT & MANAGEMENT |  |  |  |  |
| 1 | Prepare a draft RCP and ADS-C Surveillance Performance-Based Operations Plan outlining the way forward for consideration by the NAT IMG | NAT IMG/38 and NAT SPG/47 | Approved by NAT SPG/47. | NAT CNSG |  |
| 2 | Identify Key Target Dates on implementing RCP and ADS-C surveillance performance framework and prescribing specifications to support RLongSM, and RLatSM. | NAT IMG/38 and NAT SPG/47 | Pending target dates for associated operations. | NAT IMG | NAT SPG Conclusion 44/11 targets 2015. Target dates for RCP/ADS-C performance specifications need to be in combination with the target dates for RLongSM and RLatSM operational implementation. |
| 3 | - Confirm applicable performance specifications that will be used for operational implementation of data link services in support of RLongSM. Detail and validate CRM assumptions against actual performance measurements in accordance with GOLD. - Confirm applicable performance specifications that will be used for operational implementation of data link services in support of RLatSM. Detail and validate CRM assumptions against actual performance measurements in accordance with GOLD. | NAT SPG/47 | Approved by NAT SPG/47 | NAT SARSIG | -During trials of RLongSM and RLatSM, specifications are not prescribed, but will provide guidelines against which the actual performance is measured. -RCP 240 and RSP/180 are the candidate’s specifications to be prescribed for RLatSM and RLongSM operations.(subject to validation during the trials and Doc 4444 amendments) . |
| 17 | Conduct workshops to raise awareness on RCP and surveillance performance. | 2012-2013 | Planned in 4Q2012 in conjunction with the PfA drafting task force and depending on the availability of the workshop material | ICAO/States |  |
| 4 | a)Update operational concepts for implementation of RLatSM, RLongSM supported by associated RCP and surveillance performance specifications. b)Develop operational concept (of use), including procedures, for data link services using CPDLC and ADS-C to reduce the number and exposure of operational errors and pilot deviations, regardless of whether or not reduced ADS-C based separations are applied. For example, concept of use should detail conformance monitoring, intervention and route re-clearances. c)Review and comment on material for incorporation in GOLD, NAT Doc 006 and Doc 007. | NAT IMG/42 and NAT SPG/49 | a)complete b) and c) Draft and review through end 2012. The 1st draft for the GOLD material prepared to be further reviewed at CNSG/7 | NAT ATMG in coordination with CNSG | . Review and propose text to be candidate for GOLD amendment. |
|  | DOCUMENTATION |  |  |  |  |
| 5 | Development of the GOLD material in support of reduced separations : -the provisions for data link service (AIC, guidance for AIPs, eligibility requirements etc) -performance specifications -initial qualifications for operations of operators, aircraft and ATC -post implementation monitoring | NAT SPG/46 | In progress | GOLD ad-hoc group | Amendments to GOLD are in work for tasks 3, 5, 6 and 7. Adoption planned at NAT SPG/49. |
| 6 | Develop flight crew and controller contingency procedures in the event of service outage, malfunction or failure that would cause performance to degrade below that required by specifications. Review and comment on material for incorporation in GOLD, NAT Doc 006 and Doc 007. | NAT IMG/42 and NAT SPG/49 | Draft and review through end 2012. Further review at ATMG/40 | NAT ATMG/ CNSG | Further review at ATMG/40. Doc006 will include ref to Chapters 4 and 5 of the GOLD |
| 7 | Develop the criteria for resuming data link service, RLatSM, or RLongSM operations after service communication and/or surveillance capabilities are restored to acceptable level of performance. Review and comment on material for incorporation in GOLD, NAT Doc 006 and Doc 007. | NAT IMG/42 and NAT SPG/49 | Draft and review through end 2012 . | NAT ATMG/ CNSG | Included in NAT Doc 006. Amendments needed to ensure that long duration outages/degradations are also considered. Similar provisions should be included in the GOLD and NAT Doc 007. |
| 8 | Draft guidance material for the flight plan to define the descriptors for performance specifications, as appropriate, using the new format planned for 2012 implementation. Review and comment on material for incorporation in GOLD. | a) NAT IMG/40 and NAT SPG/48 (as part of the NAT SUPPs PfA) and GOLD b)12th Air Navigation Conference – amend Doc 4444 target date - NAT SPG/50 | await the OPLINKP initiated Doc 4444 amendment | NAT CNSG ICAO (Global) | Definition of P descriptors in Item 10a and expansion or redefinition of descriptors for ADS-C. |
| 9 | Draft or update PfA (or revise existing drafts) to the NAT Regional Supplementary Procedures (SUPPs) (Doc 7030) to prescribe the performance specifications for communication and surveillance to support RLatSM and RLongSM. PfA should include criteria for operator eligibility, aircraft equipage, requirements for flight planning, monitoring, alerting and reporting. | NAT IMG/42 and NAT SPG/49 | Draft and review through end 2012. Dependent on the trials and amendment to Doc 4444 | NAT CNSG NAT ATMG | Dependent on timeline for RLatSM and RLongSM trials and Doc 4444 amendment. |
| 10 | Amend AIPs and other State documents to support SUPPs amendment. | Consistent with Task 9 | Consistent with Task 9 | States | Consistent with Task 9 |
| 11 | Implement operational communications performance monitoring capability in ATC automation. | Before the start of operational trials of RLongSM or RLatSM. | Gander – completed Shanwick –completed Reykjavik –4Q/2011 Santa Maria – 2Q/2011 New York – Completed Bodo – TBD Shannon –1Q/2013 | NAT ANSPs | Should be in place prior to effective date of data link mandate and start of RLatSM or RLongSM trials. |
| 12 | Measure actual performance against specifications for feasibility, i.e., ACP, ACTP, PORT, ADS-C latency for operators and aircraft types | Prior to operational implementation | Ongoing | ANSPs/ DLMA/ CNSG/ SARSIG | Collect and analyze data in accordance with GOLD, Apx D. |
| 16 | Develop a guidance material to clarify the interpretation of RCP and surveillance specification in terms of compliance/non-compliance. | NAT SPG/49 NAT IMG/42 | In progress | CNSG |  |
|  | AIRWORTHINESS AND OPERATIONAL ELIGIBILITY |  |  |  |  |
| 13 | Provide guidance to State regulators related to aircraft equipage and operator eligibility requirements taking into account the GOLD and appropriate RCP and surveillance performance specifications. Review and amend GOLD, if required. | NAT IMG/42 and NAT SPG/49 | Draft and review through end 2012. | OPS/AIR | Refer to FAA AC 20-140A and AC 120-70B. Other State material may apply. |
| 14 | Develop or revise State guidance and/or regulations, as necessary. Establish State airworthiness requirements. Establish operational policy/procedures requirements for operational approval. Prepare State inspectors to perform tasks for operational approval. Develop plan to issue operational approval to national operators by [date], to extent possible. Train pilots and, if applicable, dispatchers on RCP and surveillance performance aspects of reduced separation. Develop and distribute operations manuals, pilot bulletins or other appropriate docs containing RCP and communication surveillance performance policy/procedures. | End of 2014 Prior to operational implementation of RLatSM or RLongSM | On-going Need status reports from States | SOG/ States/ ANSPs/ Users | Implementation tasks in this plan need to be completed by NAT SPG/49 (June 2013) to allow time for operational readiness to implement RCP/surveillance performance by 2015. |
|  | POST IMPLEMENTATION TASKS |  |  |  |  |
| 15 | Post-implementation monitoring, analysis and corrective action per GOLD, Apx D and any other necessary monitoring tasks. |  | On-going See related Task 11. | ANSP/sDLMA/ CNSG | When performance falls below specified levels, operational judgment may be a consideration in determining appropriate actions. |

Note: Tasks renumbering TBD post IMG approval