## All Actions (Open or Closed)
CPWG/6 Agenda Order | Capacity Enhancement Goal | Supporting Goal Initiatives | Action Number | Legacy Action Number | Information/Status | Responsible Organization | Action Pending | Target Date | Status (Open, Moved or Closed)
1 |  | Establish PACOTS track across NOPAC into RFE |  | 030601 CPx-xx | A. ZAN implementing permanent daily night time flex tracks from U.S. west coast to RTE entry fixes BESAT, OME (for ERNIK, VALDA and KUTAL) and FRENK. ZAN to update progress at CPWG/5. Oct 2007 daily flex tracks were published FRENK, KUTAL, VALDA, BESAT – constraints for only overnight departures – began use of UPRs from US west cost and YVR to RTE fixes – program continues – looking at removing other constraints and broadening program. | FAA - ZAN | Extend RFE flex track trial with Cathay Pacific to include FRENK. |  | Closed
1 |  | Establish PACOTS track across NOPAC into RFE |  | 030601 CPx-xx | B. State ATM in process of opening new entry points and will report at CPWG/5 on status and realignment of B932 to BAMOK. | State ATM | Extend RFE flex track trial with Cathay Pacific to include FRENK. |  | Moved to AI 030609
1 |  | Establish PACOTS track across NOPAC into RFE |  | 030601 CPx-xx | C. State ATM opened RUSOR and is working with ZAN to make it available in ZAN airspace – will be one more Polar fix between P2 and P3 in late 2008. Realignment of B932 could be completed by August 2008 | State ATM | Extend RFE flex track trial with Cathay Pacific to include FRENK. |  | Moved to AI 030609
2 | Reduce Separation Standards | RVSM in Arctic Ocean (Russian Oceanic FIRs) |  | 030602 CP1-02 | Russia advises that RVSM implementation over the Arctic was rejected by the Russian Ministry of Justice due to the lack of such separation standards in the national rules. Therefore it has been decided to pursue RVSM implementation in both domestic and oceanic airspace simultaneously. Possible target date in oceanic/domestic is late 2010 (not firm) - to be confirmed in late 2008. CPWG/6 Update: FANA contracted State Research Institute Air Navigation to perform simulation of RVSM. | State ATM | State ATM will provide update at next CPWG | CPWG/7 | Open
3 | Reduce Separation Standards | RVSM in Arctic Ocean (Russian Oceanic FIRs) |  | 090733 CP4-33 | Positions papers provided for TRASAS/2 and CPWG/5 regarding RVSM. Russia does not need the letter. | IATA | IATA provided FANA an official letter requesting prioritization over the Arctic Oceanic airspace. | CPWG5 or before | Closed
4 | Improve Efficiencies | RVSM transition over high seas |  | 040836 CP5-36 | To be incorporated into CPWG Work Plan CPWG/6 Update: Incorporated into Work Program. Presented in WP/2 | ANSPs | IATA requesting CPWG ANSPs develop RVSM transition procedures based on ATM requirements | CPWG/6 | Closed
5 | Improve Efficiencies | Westbound use of FL360 |  | 030603 CP1-03 | State ATM Corporation will consider IATA proposal and advise at the next CPWG CPWG/6 Update: FAA is to prepare airspace chart with agreed changes and complete the SMS-HIRA process. FAA to also revise ZAN-Magadan LOA to include PILUN | State ATM | IATA proposed to use FL360 WB and ban the use of 11,100m EB. | CPWG/7 January AIRAC cycle | Open
6 | Administration | ATFM collaboration between FAA/ATO, State ATM and NavCanada |  | 030608 CP1-08 | A. Bilateral agreements between US/Canada and US/Russia in development/negotiation. CPWG/6 Update: US/Canada have agreed to add polar route management to existing LOAs - completed. US/Russia agreement still open pending coordination and signing of new MOA - open | ATCSCC/NOC/ATM/FANA | Provide follow-up on bilateral. | CPWG/7 | Open
6 | Administration | ATFM collaboration between FAA/ATO, State ATM and NavCanada |  | 030608 CP1-08 | B. The LOA between State ATM Corp's Main ATM Center and NavCanada's NOC was signed in Oct. 2006. Both parties are now reviewing the possibilities for its practical implemtation. Polar route management procedures will be added to NOC agreement. | ATCSCC/NOC/ATM/FANA | Provide follow-up on LOA completion | CPWG/6 | Closed
6 | Administration | ATFM collaboration between FAA/ATO, State ATM and NavCanada |  | 030608 CP1-08 | C. The FAA's Command Center and State ATM Corp's Main ATM Center draft Agreement outlining areas of future cooperation including coordination and management of flow of air traffic between the U.S. and Russia will be an Annex to the MOU being coordinated between FAA and FANA. MOU and Annex are awaiting signatures. FAA/FANA to update at next CPWG. | ATCSCC/NOC/ATM/FANA | Provide follow-up on LOA completion | CPWG/7 | Open
6 | Administration | ATFM collaboration between FAA/ATO, State ATM and NavCanada |  | 030608 CP1-08 | D. ATCSCC and NOC have agreed to add Polar Route management to existing LOA CPWG/6 Update: Added polar route | ATCSCC/NOC/ATM/FANA | Provide follow-up on LOA completion | CPWG/6 | Closed
7 | Improve Efficiencies | Agreement to make B932 regular, permanent route with limited hours of operation, reduce longitudinal separation to 15 minutes, and permit bidirectional utilization |  | 030609 CP1-09 | A. Current MOU between Khaborovsk and Sapporo ACC expired fall 2007. Will become permanent route in LOA. CPWG/6 Update: Appendix to future Air Navigation Service agreement. Close old MOA and sign new MOA. Old agreement has not been closed out. Bilateral in July with JCAB. It was decided to realign effective 11/20, available 24 hours, bidirectional use, and with longitude separation of 15 minutes on same FL. LOA with JCAB updated. FAA to initiate SMS-HIRA process to ensure any issues are mitigated with changes to routes in ZAN airspace. It was agreed that outcome is applicable for all RTE routes, UPR available, current traffic flows continues, and safety maintained. | State ATM/JCAB | A. State ATM and JCAB to extend current MOU. FAA to provide status on SMS-HIRA Panel Process and completion of route B932. | CPWG/7 | Open
7 | Improve Efficiencies | Agreement to make B932 regular, permanent route with limited hours of operation, reduce longitudinal separation to 15 minutes, and permit bidirectional utilization |  | 030609 CP1-09 | B. Current MOU between Petropavlovsk-Kamchatsky ACC and ZAN expired fall 2007. Will become permanent route in LOA | State ATM/FAA (ZAN) | B. State ATM and ZAN to extend MOU | CPWG/7 | Open
7 | Improve Efficiencies | Agreement to make B932 regular, permanent route with limited hours of operation, reduce longitudinal separation to 15 minutes, and permit bidirectional utilization |  | 030609 CP1-09 | C. Revise MOUs to permit 15 minute separation. CPWG/6 Update: Agreed to in State ATM and JCAB bilateral (July). | State ATM/JCAB/ FAA (ZAN) | C. All parties agreeable to this change and will be incorporated concurrently with extending MOUs. JCAB to consider State ATM realignment proposal. | CPWG/6 | Closed
7 | Improve Efficiencies | Agreement to make B932 regular, permanent route with limited hours of operation, reduce longitudinal separation to 15 minutes, and permit bidirectional utilization (Cont.) |  | 030609 CP1-09 | D. Goal is to realign route so as to exit Russian Airspace at BAMOK instead of KOKES. FAA will concurrently pursue extending route across Anchorage FIR from BAMOK to CZF. JCAB requires TBE VOR to be operational for route usage. JCAB to begin work to expand TBE operational hours and will report progress at next CPWG. All parties will update at next CPWG. | State ATM/FAA (ZAN) | D. Realign route segments east of PEKUT | CPWG/6 | Open
7 | Improve Efficiencies | Agreement to make B932 regular, permanent route with limited hours of operation, reduce longitudinal separation requirement to 15 minutes, and permit bidirectional utilization |  | 030609 CP1-09 | E. This action tied to overall NOME-BESAT-NEONN reorganization CPWG/6 Update: Agreed to in State ATM and JCAB bilateral (July). | JCAB | E. Make B932 a permanent route (24 hours) | CPWG5 or before | Closed
7 | Improve Efficiencies | Agreement to make B932 regular, permanent route with limited hours of operation, reduce longitudinal separation to 15 minutes, and permit bidirectional utilization (Cont.) |  | 030609 CP1-09 | F. Consider bidirectional use. CPWG/6 Update: Agreed to in State ATM and JCAB bilateral (July). | FAA (ZAN) | F. Permit bidirectional traffic | CPWG/6 | Closed
7 | Improve Efficiencies | Agreement to make B932 regular, permanent route with limited hours of operation, reduce longitudinal separation to 15 minutes, and permit bidirectional utilization (Cont.) |  | 030609 CP1-09 | G. Report on status of new entry points and realignment of BAMOK. State ATM opened RUSOR and is working with ZAN to make it available in ZAN airspace. There will be one more Polar fix between P2 and P3 in late 2008. Realignment of B932 could be completed by August 2008. Will provide status at next CPWG. CPWG/6 Update: State ATM reported difficulties with route proposal, oceanic ok but not continent, look forward to completing installation in next year and status at next meeting | State ATM Corporation | State ATM in process of opening new entry points and will report at CPWG/6 on status and realignment of B932 to BAMOK | CPWG/7 | Open
8 | Improve Efficiencies | Track load FRENK & VALDA as separate routes |  | 030613 CP1-13 | Trial was not conducted since Magadan advised they no longer required this restriction. | FAA (ZAN) State ATM | Conduct 30 day trial to asses operational impact | CPWG5 or before | Closed
9 | Improve Communications | HF Blackouts |  | 030614 CP1-14 | -Northern TDA will include HF actuals and forecasts. NOC will work with Iceland, FAA, Russia to include actual data north of 60N for entire region. -NavCanada to solicit data from other Polar HF providers and formulate into database. Results to be provided at next CPWG. -NavCanada to coordinate with FAA (ARINC), Iceland, Russia, and Bill Murtagh to include information on new website. CPWG/6 Updates: NavCanada reported no blackouts in past 3 years. Consider action closed until next solar cycle (2011). | NavCanada/ State ATM/ Iceland | Sharing of blackout data and development of procedures | CPWG/6 | Closed
10 | Improve Communications | Automated Flight Data exchange between facilities |  | 030615 CP1-15 | A. | Isavia | A. Iceland will provide State ATM copies of North Atlantic and European Interface Control Documents. | CPWG5 or before | Closed
10 | Improve Communications | Automated Flight Data exchange between facilities |  | 030615 CP1-15 | B. CPWG/6 Update: Magadan will be ready to support AIDC once upgraded; no modifications will be necessary if FAA system is the same as OLDI. State ATM will provide a technical lead point of contact for Alpha3 & Ocean21 testing with ZAN. | State ATM | B. State ATM to review ICDs and investigate options for possible implementation. | CPWG/7 | Open
10 | Improve Communications | 0 |  | 030615 CP1-15 | C. NavCanada advises Edmonton probably will not be ready until 1st quarter 2009. Both FAA and NavCanada will update if available at next CPWG. CPWG/6 Update: NAMICD will be implemented post CATS (Spring 2009). | NavCanada/ FAA | C. Implement AIDC between Edmonton ACC and Anchorage ARTCC | CPWG/7 | Open
11 | Administration | ATS & benefits statement |  | 030617 CP1-17 | IATA advised that prioritization of ATS efforts should be: 1. Implementation of RVSM, 2. Improve Air Traffic Flow Management, 3. Implement of new routes, and associated entry points, across Russian airspace. | IATA | Revise and update at next CPWG | CPWG5 or before | Closed
12 | Improve Efficiencies | Manage GRL compliance |  | 030618 CP1-18 | A. | All | A. Monitor GRL Compliance. | CPWG5 or before | Closed
12 | Improve Efficiencies | Manage GRL compliance |  | 030618 CP1-18 | B. Nav Canada will monitor operator use of FL380 in the GRL | NavCanada | B. Monitor use of FL380. | CPWG5 or before | Closed
12 | Improve Efficiencies | Manage GRL compliance |  | 030618 CP1-18 | C. Conduct trial of RTA | FAA NavCanada | C. Nav Canada to prepare and coordinate RTA trial proposal. FAA to coordinate same through ATCSCC/ZAN. Operators to participate as required. Report of actual trial or, if not completed, report of progress towards trial to be reported at next CPWG. | CPWG5 or before | Closed Moved to AI 090734
12 | Improve Efficiencies | Manage GRL compliance |  | 030618 CP1-18 | D. Provide updates GRLS automatical via AFTN. | FAA | D. This capability is now incorporated in DOTs+ software | CPWG5 or before | Closed
10 | Improve Communications | Automated Flight Data exchange between facilities | CP | CP6-1 | E. FAA requested agreement on adding AIDC ICD to Work Program | FAA | It is the intent from ICAO to develop global standard and the FAA is requesting that the group work together ensure common standard between providers in polar region. There is an AIDC Task Force looking at a global standard through the North Atlantic Special Planning Group. NavCanada will provide status. | CPWG7 | Open
12 | Improve Efficiencies | Manage GRL compliance |  | 030618 CP1-18 | E. Testing is still underway. No date for implementation available CPWG/6 Update: FAA briefed that testing is underway and expected to be completed by end of 2008. Ops demonstrations planned to occur by last quarter of 2009. Comments to be submitted to Timothy.McHale@faa.gov | FAA | E. DOTS+ Online web-based Track Advisory program Update | CPWG/7 | Open
13 | Reduce Separation Standards | Mach Number Technique |  | 030619 CP1-19 | A. MNT to be incorporated into Anchorage/Murmansk LOA OCT. 2007 | FAA State ATM | A. Incorporate MACH number technique (MNT) into the Anchorage ARTCC/Murmansk ACC LOA | CPWG5 or before | Closed
13 | Reduce Separation Standards | Mach Number Technique |  | 030619 CP1-19 | B. Reverse MNT to be incorporated into Anchorage/Murmansk and Anchorage/Magadan LOAs effective Oct. ’07. | FAA State ATM | B. Implement “Rule of 11” and “Reverse MNT” in Anchorage ARTCC / Magadan ACC LOAs. | CPWG5 or before | Closed
14 | Administration | Performance Metrics |  | 090625 CP2-25 | This item to remain open as place holder for issue. ATS providers and Operators to update as/when required. State ATM believes this item should be closed at next meeting unless new information is forthcoming. | All | Performance Metrics Carry over item from IOAC | CPWG5 or before | Closed
15 | Improve Efficiencies | Ocean 21/Arctic FIR |  | 090626 CP6-2 | FAA to make determination on extent of Ocean21 implementation by end of ’07. FAA will update at next CPWG. CPWG/6 Update: IP/4 FAA waiting for signoff and then will need to fit the changes into the overall Ocean21 schedule. | FAA | FAA exploring implementation options for the Anchorage Arctic FIR. | CPWG/7 | Open
16 | Develop Contingency Plan | Contingency Response |  | 090627 CP2-27 | A. FAA (ZAN) presented an initial listing to the group for review in WP06. Requesting ANSPs to complete and return matrix to Mark McClure, ZAN. Update at next meeting. CPWG/6 Update: FAA recently received response from NavCanada covering the whole NAT and is requesting updates from other ANSPs | FAA, State ATM Corporation, NavCanada, Isavia | A. Develop listing of possible generic contingencies. Listing should consider both airborne and pre-departure aircraft status. | CPWG/7 | Open
16 | Develop Contingency Plan | Contingency Response |  | 090627 CP2-27 | B. Awaiting completion of step A. | All | B. Develop Contingency response for each listing. | Deferred | Open
16 | Develop Contingency Plan | Contingency Response |  | 090627 CP2-27 | C. Tabletop exercise rescheduled for next meeting pending feedback on contingency matrix. CPWG/6 Update: State ATM requested the group conduct a table top exercise to evaluate reroute scenarios due to volcanic ash. Exercise to be conducted before CPWG/7. Operators are invited to participate. State ATM should keep Gail Ferguson informed. | State ATM | C. Conduct tabletop exercise(s) as able. | CPWG/7 | Open
16 | Develop Contingency Plan | Contingency Response |  | 090627 CP2-27 | FAA to make determination on extent of Ocean21 implementation by end of ’07. FAA will update at next CPWG. CPWG/6 Update: IP/4 FAA waiting for signoff and then will need to fit the changes into the overall Ocean21 schedule. | NavCanada | D. Send previous tabletop documents. | CPWG/7 | Open
17 | Improve Communications | HF air-ground Data Link |  | 040729 CP3-29 | FAA will contact Operators (Continental, Northwest) to design and conduct test. FAA/ZAN to provide update and results at CPWG/6 CPWG/6 Update: No status at this time. FAA presented IP that provided intermediate report on HFDL trial that was held in Pacific. | FAA and Operators | Continued exploration of HFDL as possible solution for Polar Operations. | CPWG/7 | Open
| Improve Communications | HF air-ground Data Link |  | CP6-3 | State ATM to confirm if Magadan system currently accepts FANS messages HFDL. FAA to follow up with ARINC on services provided to Russia. | FAA |  | CPWG/7 | Open
18 | Reduce Separation Standards | Standardize Polar Region Separation Standards |  | 040730 CP3-30 | A. CPWG/6 Update: FAA proposed reopening and to remain as a standard open document updated at each CPWG. Bodo FIR has been added. NavCanada reported table updates of CPDLC 2009 and AIDC 2009. The group agreed and FAA will update and provide status at next meeting. | FAA | A. Complete inventory of current ATS/CNS adequacies | CPWG/7 | Open
18 | Reduce Separation Standards | Standardize Polar Region Separation Standards |  | 040730 CP3-30 | B. IATA developed and presented paper and position from airlines on RNP that was presented at March 18-19, 2008 TRASAS/2 Meeting. Presented WP at CPWG/5 for group to begin working toward and ask that this be included as part of the CPWG Work Program to look and identify separation standards. | IATA | B. Determine which separation standards), when/if standardized would be most beneficial to Cross Polar traffic flows. | CPWG5 or before | Closed
19 | Improve Efficiencies | Implement use of Radar procedures between Magadan ACC and Anchorage ARTCC |  | 090731 CP4-31 | FAA and FANA to provide status at next meeting. CPWG/6 Update: State ATM update included installation of SSR radar with tentative date of 2011. Experimenting with ADSB and testing in progress, no decision made about ADSB in Russia. | FAA and FANA | TBD | CPWG/7 | Open
20 | Improve Efficiencies | Conduct Trial of Northern Canada to RTE Entry Points Flex Track |  | 090732 CP4-32 | A. No participation by customers – moving on. | Canadian NOC | A. Construct and coordinate paper trial procedures. | CPWG5 or before | Closed
20 | Improve Efficiencies | Conduct Trial of Northern Canada to RTE Entry Points Flex Track |  | 090732 CP4-32 | B. ZAN will continue generating tracks and would like feedback from airlines – will send out the tracks as test messages CPWG/6 Update: Presented IP/2 All agreed that FAA should not pursue expanding operational plane for DOTS+ | Anchorage ARTCC TMU | B. Provide DOTS+ generated tracks from 100W to RAMEL and ORVIT | CPWG/6 | Closed
20 | Improve Efficiencies | Conduct Trial of Northern Canada to RTE Entry Points Flex Track |  | 090732 CP4-32 | C. Table the proposal until Russia can support CPWG/6 Update: FAA provided status on efforts to generate tracks from KORD and KJFK and how it compared to the actual filed routings. | Anchorage ARTCC | C. Create a Cross Polar Organized Flex Track System – Set development and implementation timeline goals. | CPWG/7TBD | Open
21 | Improve Efficiencies | Cross Polar Trial |  | 090734 CP4-34 | Cross Polar Trial was successfully concluded and new procedures for DEVID, RAMEL, NIKIN and ORVIT were agreed. CPWG/6 Update: Presented WP/9 CP trial was successful and new procedures for LISKI are permanment. | ATCSCC NOC Anchorage ARTCC Edmonton ACC | FAA to report on outcome of LISKI trial | CPWG/6 | Closed
22 | Improve Efficiencies | Shorten and simplify Form “R” and filing process. |  | 090735 CP4-35 | Collected airline input – will review and report to the next meeting. CPWG/6 Update: State ATM presented IP/12 on changes made to simplify R form. AIP was amended to reflect change as well. IATA requested email or secure internet access (similar to NavCanada or Command Center). State ATM and IATA will discuss solution and provide update at next meeting. | FANA/State ATM Corp. IATA |  | CPWG/7 | Open
23 | Improve Efficiencies | China has approved the use of multiple entry points on routes but not all airlines are aware of this. FANA asked IATA to provide info to airlines. |  | 040837 CP5-37 | CPWG/6 Update: Information has been posted on www.aischina.com | IATA |  | ASAP | Closed
24 | Reduce Separation Standards | Mixed environment, capabilities & benefits to be gained. Partial mix of fleet. Need to identify obstacles to increase capacity, assess & identify obstacles & how to mitigate them. | CP6 | 040838 CP5-38 | CPWG/6 Update: IATA compiling world wide fleet census; action is to remain open and updated at next meeting. | IATA | IATA to provide position on mixed fleet benefits and capabilities | CPWG/7 | Open
24 | Reduce Separation Standards | Discussions on longitudinal separation, altitude changes |  | 040838 CP5-38 | CPWG/6 Update: Incorporated into Work Program. Presented in WP/2 | CPWG – make this action part of the work program | Part of CPWG Work Plan | CPWG/6 | Closed
25 | Administration | NavCanada addressed their monthly statistic report that they provide |  | 040839 CP5-39 | CPWG/6 Update: Monthly NavCanada statistics are posted on the CPWG website. | ALL | Asking ANSPs and Operators to review & see if there is any additional information to add to the report. Comments to be submitted to Dave Rome | ASAP | Closed
26 | Improve Efficiencies | Establishing new Routes |  | 040840 CP5-40 | CPWG/6 Update: Will be an offline with FAA (Bob) and Emirates. | FAA | Emirates Airlines asked FAA to provide information on any restrictions using "Q" routes and "HAR" waypoints along the west coast? | ASAP | Closed
27 | Reduce Separation Standards | Standardize Polar Region Separation Standards |  | 040841 CP5-41 | The group will develop a CPWG work program that will be discussed at the next meeting CPWG/6 Update: Incorporated into Work Program. Presented in WP/2 | ALL | B. Work to include Mach Number Technique in appropriate regional supplementary procedures (Doc 7030) | CPWG/6 | Closed
27 | Reduce Separation Standards | Standardize Polar Region Separation Standards |  | 040841 CP5-41 | The group will develop a CPWG work program that will be discussed at the next meeting CPWG/6 Update: Incorporated into Work Program. Presented in WP/2 | ALL | C. Work to include RNP-4 in Cross Polar Work Program. | CPWG/6 | Closed
27 | Reduce Separation Standards | Standardize Polar Region Separation Standards |  | 040841 CP5-41 | The group will develop a CPWG work program that will be discussed at the next meeting. CPWG/6 Update: Incorporated into Work Program. Presented WP/2 | ALL | A. Work to include RNP-10 in cross-polar and trans-east FIR's | CPWG/6 | Closed
28 | Improve Efficiencies | Airline Route Proposals |  | 040842 CP5-42 | Provide status on efforts CPWG/6 Update: Presentation at last CPWG and at RDGE meeting in Paris Two of the proposals will be implemented in the middle of next year. FAA requested that FANA/State ATM provide notification on route proposals, especially if routes extend beyond Russia FIR. FAA would like to be involved in development process and requests more advance notification. Agreed to have 2-AIRAC cycle notification. | IATA will act as a focal point for Airline Route proposals, prioritize them, and present to the States | To submit consolidated, prioritized Airline proposals to ANSPs for discussions and consideration. | CPWG/7 | Open
30 | Administration | Development of Work Plan |  | 040843 CP5-43 | CPWG/6 Update. Provided via email on October 08, 2008. | NavCanada | A. NavCanada to provide FAA with copy of ATMG Roadmap | ASAP | Closed
30 | Administration | Development of Work Plan |  | 040843 CP5-43 | CPWG/6 Update: Incorporated into Work Program. Presented in WP/2 | FAA | B. FAA to draft Initial work program for ANSPs and customers review | CPWG/6 | Closed
31 | Improve Efficiencies | Route Development and Coordination with China |  | 040844 CP5-44 | CPWG/6 Update: Agreed to bilateral before end of year. | IATA China | A. IATA to work with China in the development of new entry points | CPWG/7 | Open
31 | Improve Efficiencies | Route Development and Coordination with China |  | 040844 CP5-44 | CPWG/6 Update: Invitation extended on xxx xx, 2008. | FAA | B. FAA to officially invite China in the Development of new entry points | CPWG/6 | Closed
| Reduce Separation Standards | Mach Number Technique |  |  | B. Reverse MNT to be incorporated into Anchorage/Murmansk and Anchorage/Magadan LOAs effective Oct 2007 | B. State ATM/FAA | B. Implement "Rule of 11" and "Reverse MNT" in Anchorage ARTCC/ Magaden ACC LOAs | CPWG5 or before | Closed
| Develop Contingency Plan | Contingency Response |  | CP6-4 | D. Tabletop exercise regarding volcanic ash. CPWG/6 Update: State ATM requested the group conduct a table top exercise for volcanic ash either later this year or early next year. Look at reroute scenarios (ZAN, Nav, JCAB, and other parties). d the need for volcanic ash exercise since they expect volcanic activity in near future. Operators are invited to participate State ATM will take the lead on coordinating this activity. Conduct a tabletop exercise on volcanic ash before CPWG/7. Also, keep Gail Ferguson current. NavCanada will send the document from a previous table top exercise. | State ATM | D. Conduct tabletop exercise(s) regarding volcanic ash | CPWG/7 | Open
| Improve Efficiencies | Manage GRL compliance |  | CP6-5 | F. Testing is still underway and expected to be completed by end of 2008. The operations demonstration is expected to be completed by forth quarter 2009. | E. FAA | F. Provide update on testing and demo plans. | CPWG/7 | Open
| Improve Communications | HF air-ground Data Link |  | CP6-6 | FAA will provide update and results on HAL trial at CPWG/7 | FAA | Continued exploration of HFDL as possible solution for Polar Operations. | CPWG/7 | Open
|  | Performance Metrics |  | 090625 CPx-xx | This item to remain open as place holder for issue. ATS providers and Operators to update as/when required. State ATM believes this item should be closed at next meeting unless new information is forthcoming. | All | Performance Metrics – Carry over item from IOAC. What metrics would benefit Polar Routes Working Group |  | Closed
|  |  |  | CP6 |  | UAL
| Administration | Development of Work Program |  | CP6-9 |  | FAA | Revise the work program (CPWG/6 WP/2) to include only high-level strategic objectives. | Before CPWG/7 | Open
| Administration | Action Items |  | CP6-10 |  | FAA | Distribute updated Action List in new format (CPWG/6 WP/3) | 1 week after CPWG/6 | Open
| Administration | Statistics |  | CP6-11 | Where possible, track statistics on time/fuel savings for new and or improved routes | ALL |  | CPWG/7 | Open
| Improve Efficiencies | Tactical Reroutes |  | CP6-12 | Based on discussions on WP/7, it was agreed that State ATM would provide several options on tactical rereoutes for airlines to review at next meeting. | State ATM | State ATM to provide tactical reroute options at next meeting. | CPWG/7 | Open
| Improve Communications | Loss Communication & Procedures |  | CP6-13 | Based on discussions on WP/8 & IP/11, State ATM provided clarification on procedures and will update ICAO Doc. 7030. The FAA will address amending ICAO document 7030 to reflect agreement on loss of comm procedure. | State ATM and FAA | State ATM will forward AIC regarding procedures effective during January 15, 2009 AIRAC cycle. FAA will amend ICAO Doc 7030 to reflect agreement on loss of comm procedures | CPWG/7 | Open
| Improve Efficiencies | Routings to/from B970 |  | CP6-14 | IATA agreed to review and establish preference of LISKI overfly TATUM instead of VOLOB. | IATA |  | CPWG/7 | Open
| Improve Efficiencies | PILUN route |  | CP6-15 | IATA would like for ZAN to consider deleting the route restriction of crossing 140W, and instead focus on the 150W lat/long points to greatly improve the chances of getting efficiencies to PILUN. It is understood that flights may have to descend to lower flight levels, but feel it would be a worthwhile trade-off. | FAA | FAA to report back on deleting route restrictions of crossing 140W. | CPWG/7 | Open
Note on J1: tkarakis: To be used for filtering only the open items. Once filtered, the report can be printed with open items. Also, can filter on other columns such as Target Date of CPWG/6