Seventh Meeting of the Cross Polar Trans East Air Traffic Management Providers’ Work Group (CPWG/7)

(European and North Atlantic (EUR/NAT) Office of ICAO, Paris, France, 3-5 June 2009)

Agenda Item 4:  Provide Status on CPWG/6 Actions

FORMATION OF THE ARCTIC RNP 10 PROJECT

(Action Item 040730, CP3-30)

(Presented by Federal Aviation Administration and NAV CANADA)

SUMMARY The purpose of this paper is to inform the CPWG of a project being established to implement 50 NM lateral separation between operators/aircraft that are authorized required navigation performance (RNP) 10 or RNP 4 in the Canadian Minimum Navigation Performance Specifications (CMNPS) and Anchorage (ZAN) Arctic airspace. A primary objective of the project is to harmonize the lateral separation standards applied across the Polar Region. The project is planned to be progressed under the auspices of the Trans-Regional Airspace and Supporting ATM Systems Steering Group (TRASAS).

- Introduction

  - During the second Trans-Regional Airspace and Supporting Air Traffic Management (ATM) Systems Steering Group (TRASAS/2) meeting in March 2008, the participants agreed to several initiatives and conclusions that would be distributed to the appropriate working groups for implementation.  TRASAS Conclusion 2/2 was on RNP for Cross-Polar and Trans-East operations.

- Specifically, that all PIRGs concerned be invited to consider actions that will harmonise the application of separation standards and a means to achieve:

a)  Implementation of the RNP 10 provisions in the airspaces covering the Cross-Polar and Trans-East routes/operations as a short-term/medium-term action;

b) Implementation of the RNP 4 provisions in the same airspaces as described above, as a medium-term/long-term improvement; and

c)  Amend, as appropriate, the provisions of Regional Supplementary Procedures and the Regional Air Navigation Plans.

  - As part of the discussions and updates from the TRASAS/2 meeting, the CPWG members agreed to include the TRASAS Conclusion 2/2 as part of its new CPWG Work Program. The CPWG identified a need to harmonize separation standards and improve efficiencies across the polar region. It was agreed that the appropriate Air Navigation Service Providers (ANSP) would establish a work group to assess the feasibility of introducing 50NM lateral separation in all of the Flight Information Region (FIRs) in the Arctic Region and identify the tasks required for implementation.

- Discussion

  - The Federal Aviation Administration (FAA) Air Traffic Oceanic and Offshore Operations (AJE-32) office and Flight Standards Performance Based Flight Systems Branch, NAV CANADA and ISAVIA have formed a team to explore implementing 50 NM lateral separation between operators/aircraft authorized RNP 10 or RNP 4 in Anchorage (ZAN) Arctic FIR and Canadian Minimum Navigation Performance Specifications (CMNPS) airspace.  ISAVIA has participated and will continue to be part of discussions, but, at this time, will not implement a 50 NM lateral separation standard for the single polar track crossing their airspace. The Russian State ATM Corporation (State ATM) has agreed to consider adding additional boundary fixes on their boundary with Anchorage Center.  At this point, the State ATM is not participating in discussions because this would not be a reduction in separation for them.

  - The project will be progressed under the auspices of the TRASAS.  The ICAO European and North Atlantic Office is coordinating with the ICAO North American, Central American and Caribbean (NACC) Office to establish the lead ICAO office for the project.

  - The Arctic RNP 10 Work Group has held a number of teleconferences to date. Within the first several teleconferences during February and March, the group began discussions on the development of a draft Concept of Operations (CONOPS) and a project Task List.  The current draft CONOPS, a draft Summary Task List and a first draft North American (NAM) amendment to the Regional Supplementary Procedures (SUPPS) are posted in the appendices to this paper.  The Summary Task List contains a proposed target implementation date of 18 November 2010.

  - The draft task list is derived from that used to schedule and track required tasks for implementation of the West Atlantic Route System (WATRS) Plus project in June 2008.  The WATRS Plus project implemented 50 NM lateral separation in WATRS airspace and in the Miami Oceanic and San Juan Control Areas.  The task list contains the following major areas of work:

- General Project Development and Management

- International coordination:  ICAO Groups and Documents

- Airspace and Route Structure Review

- Safety Analysis and Monitoring

- Air Traffic Control Tasks – General

- Operations, Airworthiness and RNP Authorization

- State Responsibilities For RNP Authorization

- Operator Responsibilities and Tasks

- Final Implementation Decision and Notification

- Post-implementation Tasks

  - At the 26 February meeting, a concern was raised on the effect that the “RNP 10 time limit” could have on the polar aircraft fleet’s capability to meet RNP 10 for the duration of flights in Arctic FIR’s where 50 NM lateral separation is proposed to be applied.  (Standard and extended “RNP 10 time limits” are addressed in the ICAO Performance Based Navigation Manual (Doc 9613), Volume II, Part B, paragraphs 1.3.4.2.2 and 1.3.4.2.3 and in FAA order 8400.12A (RNP 10 Operational Approval)).   The task list discussed in paragraph 2.5 contains tasks to assess aircraft fleet capability and coordinate with the operator community to establish the feasibility of the operator/aircraft fleet meeting RNP 10 requirements.  FAA Flight Standards specialists have started work on this task and though the work has not yet been completed, they do not anticipate that the “RNP 10 time limit” will be an obstacle to progressing the project.  The Arctic RNP 10 Group will be informed as the work progresses.

- Actions

  - The meeting is invited to discuss the information provided in this paper and endorse the continued progression of the Arctic RNP 10 Project through appropriate ICAO Offices, States and forums.

ARCTIC RNP 10 CONCEPT OF OPERATIONS

1.	Vertical and horizontal boundaries of airspace

a.	Horizontal Boundary.  50 NM lateral separation is planned to be applied between aircraft authorized RNP 10 or RNP 4 operating on oceanic routes or areas within the Anchorage Arctic FIR and the airspace of the Edmonton FIR currently designated as CMNPS airspace.

The Anchorage Arctic FIR is that airspace bounded by:  90N 141W, 72N 141W, 72N 158W, 68N 168 58 23W, 90N 168 58 23W.

The Edmonton FIR, RNP 10 CTA is that airspace bounded by:  90N 141W, 70N 141W, 70N 130W, 67N 88W, 65 30N 60W, 65N 60W, 65N 57 45W, 76N 76W, 78N 75W, 82N 60W, 90N 141W.

b.	Vertical Boundary.  50 NM lateral separation is planned to be applied between aircraft authorized RNP 10 or RNP 4 operating FL280 to FL600 inclusive within the CTAs listed above.

2.	Lateral separation standard(s) to be applied

a.	50 NM Lateral Separation.

(1)  Anchorage Arctic FIR and Edmonton FIR, RNP 10 CTAs.  50 NM lateral separation will be applied between aircraft authorized RNP 10 or RNP 4 operating at any altitude within the Anchorage Arctic FIR and Edmonton FIR, RNP 10 CTAs FL280 to FL600 inclusive.

b.	Lateral Separation For Aircraft Not Authorized RNP 10 or RNP 4.

(1)  Within the Anchorage Arctic CTAs, the lateral separation standard applicable to Non-RNP 10 aircraft will be 90 NM.

(2)  Within the Edmonton FIR, RNP 10 CTAs, the lateral separation standard applicable to Non-RNP 10 aircraft will be 60 NM for CMNPS equipped flights and 90 NM for all other flights.

3.	Concept for transfer of control to FIRs adjoining ARCTIC FIRs

a.	Transfer of Control to Adjacent CTAs.  Aircraft transiting Anchorage Arctic FIR and Edmonton FIR, RNP 10 CTAs to other FIRs will be transferred as per regional documentation with the appropriate separation standard applied.

4.	Transition airspace

a.	Transition airspace is airspace in the Anchorage Arctic FIR regions adjoining the Anchorage Continental FIR (Anchorage Domestic).  Coordination is necessary to establish policies related to transfer of control and the separation to be applied.

b.	Transition airspace is airspace in the Edmonton FIR, RNP 10 shall be applied as per ATSAMM346.2 and 346.3 for flights transiting the RNPC line, within the Edmonton FIR, whereby the transition occurs over 50 NM.

c.	The airspace outside the _________ CTAs within the control area(s) of the _____ FIR(s) is considered transition airspace.

5.	Concept for use of fixed or flex routes.  At this time there will be no fixed or flex routes.  The airlines file user preferred routes.

6.	Flight Plan Equipment Suffix Requirements

a.	ICAO Flight Plans.  To inform ATC and to key ATC automation that they have

RNP 10 or RNP 4 authorization and are eligible for 50 NM lateral separation, operators must annotate:

- *Item 10 (Equipment) of the ICAO Flight Plan with the letter “R” (RNP type certification) and “Z” (Other equipment carried).

- *Item 18 (Other Information) with, as appropriate, “NAV/RNP10”, “NAV/RNP4”.

*Note 1:  the Item 18 entry “STS/NONRNP10” is used in WATRS Plus operations to indicate

Non-RNP 10 status.  The Arctic RNP 10 group will determine if this entry is necessary for Arctic application.

*Note 2:  ICAO is planning to publish revised ICAO Doc 4444, Appendix 2 policy for ICAO Flight Plan Item 18 entries to show aircraft Comm, Nav and Surveillance capabilities.   The planned effective date is 15 November 2012. Inquiries have been made as to current planned effective date for that material.

7.	Concept for use of ATC automation in Arctic Airspace - TBD

8.	DRAFT Provisions for accommodating aircraft not meeting RNP 10 or RNP 4

a.	For the project to be fully successful, operators flying on oceanic routes or areas in the Anchorage Arctic and Edmonton FIR, RNP 10 CTAs between FL 290-410 (inclusive) should obtain RNP 10 or RNP 4 authority (to the maximum extent possible).  For initial project implementation, however, the airspace of the Anchorage Arctic and Edmonton FIR,

RNP 10 CTAs will not be “exclusionary”.  Aircraft not authorized RNP 10 will be allowed to fly on oceanic routes or areas within Anchorage Arctic and Edmonton FIR, RNP 10 CTAs, however, 50 NM lateral separation will not be applied to them.  They will be cleared on their preferred routes and altitudes as traffic permits. Aircraft that are authorized RNP 10 or RNP 4 will have a better opportunity of obtaining their preferred route and altitude because the 50 NM lateral separation standard will be applied to those aircraft.

b.	The following DRAFT basic accommodation policies will apply:

(1)  Non-RNP 10 operators/aircraft will be able to file any route at any altitude in the Anchorage Arctic and Edmonton FIR, RNP 10 CTAs.  They will be cleared to operate on their preferred routes and altitudes as traffic permits.

(2)  Non-RNP 10 aircraft will retain the option of climbing to operate at altitudes above those where traffic is most dense (i.e., at/above FL 410).  To minimize the chance of conflict with aircraft on adjacent routes, Non-RNP 10 aircraft should plan on completing their climb to or descent from higher FL’s within radar coverage.

(3)  All aircraft can enhance their opportunity to be cleared on their preferred route and altitude if they operate at non-peak hours, approximately 0500 (?) to 1700 UTC.

9.	Operator/Aircraft requirements for operation on routes on the periphery of the Anchorage Arctic and Edmonton FIR, RNP 10 CTAs.  Operation on certain routes that fall within the boundaries of Anchorage Arctic and Edmonton FIR, RNP 10 CTAs will not be affected by the introduction of RNP 10/50 NM lateral separation, scheduled for TBD.  Operation on the following routes will not be affected:  NCA tracks and laterals, Northern OTS during the validity period and UPRs when not restricted by NOTAM.

10.	Aircraft Population RNP 10 Authorization Objective

a.	Implementation Objective:  Percentage of Flights Authorized RNP 10 or RNP 4.  The Arctic Task Force will progress its work with the objective of having at least 85% of flights operating in Arctic airspace authorized for RNP 10 or RNP 4 by TBD (i.e., one month prior to the TBD planned project implementation date).

b.	RNP 10 or RNP 4 Compliance to the Maximum Extent Possible.  The Arctic RNP 10 Task Force will advocate that all operators/aircraft that fly in the Anchorage Arctic and Edmonton FIR, RNP 10 CTAs obtain RNP 10 or RNP 4 authorization as soon as possible.

11.	Aircraft/operator authorization requirements (equipage, RNP 10 authorization documents)

a.	For 50 NM lateral separation to be applied, operators will be required to obtain RNP 10 or RNP 4 authorization from the appropriate State authority.

b.	Guidance to Be Used.  The FAA will use FAA Order 8400.12 (as amended) or, if applicable, FAA Order 8400.33 (as amended).   It is recommended that other States use either the FAA orders or the ICAO Performance Based Navigation (PBN) Manual (ICAO Document 9613).

12.	Target Dates:

a.	Implementation Decision Date:  August 18, 2010 (3 months prior to target implementation date).

b.	Operator/aircraft RNP 10 or RNP 4 Authorization Date:  October18, 2010 (calendar date, 1 month prior to target implementation date).

c.	Target Implementation Date: November 18, 2010 (AIRAC date, effective date for application of 50 NM lateral separation and re-designed route structure).

SUMMARY OF ARCTIC RNP 10 IMPLEMENTATION TASKS – DRAFT 13 May 2009

Introduction.  Proposed target implementation date for 50 NM lateral separation is 18 Nov 2010.  The following is a summary of major implementation tasks.

|  | SUBJECT | TARGET DATE | Arctic RNP 10: SUMMARY OF GENERALLY APPLICABLE IMPLEMENTATION TASKS |
| --- | --- | --- | --- |
| 1 | ICAO SARPS and Guidance | Complete | Review related ICAO SARPS and guidance documents: ICAO Doc 4444; Annexes 2, 6, 11. Note: 50-lat criteria is only published in Doc 7030 (NAT, PAC). ICAO planning to publish in 4444. |
| 2 | RNP 10 and RNP 4 authorization criteria | Complete | Review ICAO Performance Based Navigation (PBN) Manual (ICAO Doc 9613) for current criteria for RNP 10 and RNP 4 authorization. (Third Edition – 2008 is current) |
| 3 | ICAO Regional Supplementary Procedures | In progress | Confirm that amendment is required for North American (NAM) Regional Supplementary Procedures (Doc 7030) and begin coordination with ICAO Paris and Mexico City Offices. |
| 4 | Concept of Operations | In progress | Develop and coordinate Concept of Operations and incorporate into appropriate operational policy and procedures documents (e.g., FAA Notice, State AIP Supplements). |
| 5 | Operator/aircraft fleet readiness projection | In progress | Project operator/aircraft fleet can be authorized RNP 10 or RNP 4 by the implementation date. (Goal: approximately 85 % of flights conducted by RNP 10 or RNP 4 authorized aircraft). |
| 6 | ATC system modification |  | Establish system and time requirements to modify ATS provider ATC systems. |
| 7 | Task List and Schedule | In progress | Develop Task List and schedule for completion of individual tasks. |
| 8 | Regional Supplementary Procedures amendment | Nov 18, 2009 | Submit draft to ICAO Paris Office for distribution to States and industry for comment. Target date for ICAO publication: _____. |
| 9 | Safety Assessment | Nov 18, 2009 | Complete Safety Assessment/Collision Risk Modeling to be available at time of Doc 7030 submission. |
| 10 | Safety Risk Management Document | May 18, 2010 | Requirement for FAA participants: complete and submit SRMD (Safety Risk Management Document) for approval. |

| 11 | Route structure redesign |  | If applicable, complete route structure redesign, including validation of routes and fix coordinates; coordination with ATS providers with adjoining airspace; and possible impact on related SIDs/STARs and airport operations. |
| --- | --- | --- | --- |
| 12 | Plan and schedule for aeronautical chart data publication, if required |  | If applicable, develop plan and schedule for publication of aeronautical chart data. Consider whether or not it is necessary to publish “transition” waypoints on AIRAC date 56 days in advance of implementation date. |
| 13 | Information Dissemination Program | Oct 18, 2009 | Establish Webpage. Develop distribution list for State and industry organizations and key individuals. Distribute ICAO State letters, as necessary. |
| 14 | RNP 10 or RNP 4 Authorization Job Aids | Oct 18, 2009 | Post on Webpage. Ensure current PBN Manual references incorporated. Have ICAO State letter advocate use of Job Aids. |
| 15 | Advance notice | July 18, 2009 | Provide advance notice to States and operators of intent to implement (key dates, basic plan and operating policy, etc.). |
| 16 | ICAO State Letter | Nov 18, 2009 | ICAO Regional Office distribute ICAO State letter to: outline project and advocate use of RNP 10 and RNP 4 Job Aids and other guidance posted on the Webpage). |
| 17 | Coordination with Regional ICAO Working Groups | Start 5 June 2009 | Submit Working Papers and Information papers to appropriate ICAO Working Groups in the region: e.g., CPWG, NAT/SPG? |
| 18 | State regulator preparation | Nov 18, 2009 | States prepare responsible offices for RNP 10 or RNP 4 authorization tasks. |
| 19 | State regulations and guidance | Nov 18, 2009 | States revise or develop regulations and guidance for RNP 10 or RNP 4 authorization, as necessary. |
| 20 | Operational Policy & Procedures documents | Mar 18, 2010 | Distribute documents (e.g., State AIC’s, FAA Notice) containing applicable operational policy and procedures. |
| 21 | State ATS policy documents |  | States revise or develop Air Traffic Services policy documents, as necessary. |

| 22 | Transition Plan | Mar 18, 2010 | Determine if a transition plan is required. |
| --- | --- | --- | --- |
| 22a | Publish Transition Plan (if required) | Aug 18, 2010 | If required, publish coordinated plan and schedule to transition to new separation standard. |
| 23 | Pre-implementation Safety Assessment & Implementation Decision | Aug 20, 2010 | Update and complete final Safety Assessment and Readiness Review. |
| 24 | Notice of decision to implement | Sep 4, 2010 | Provide notification to States and operators of decision to implement. |
| 25 | State controller training |  | States train controllers. |
| 26 | Aeronautical chart and navigation databases |  | If applicable, publish and distribute revised aeronautical chart and navigation database information for redesigned route structure. |
| 27 | State ATC automation systems |  | Modify ATC automation systems and programs, as necessary. (Edmonton only) |
| 28 | Operator RNP 10 or RNP 4 authorization | Oct 18, 2010 | Operators of RNP 10 or RNP 4 capable aircraft should have obtained RNP 10 or RNP 4 authorization by one month in advance of implementation. |
| 29 | Target Implementation Date | Nov 18, 2010 | Implement 50 NM lateral separation and, if applicable, redesigned route structure. |
| 30 | Post implementation monitoring |  | Conduct post-implementation monitoring and convene specialists as necessary for monitoring. |

Major Sections Generally Contained in Implementation Task Lists:

| I. General Project Development & Management | VI. Operations, Airworthiness & RNP Authorization |
| --- | --- |
| II. International Coordination: ICAO Groups & Documents | VII. State Responsibilities For RNP Authorization |
| III. Route Structure Redesign & Publication | VIII. Operator Responsibilities & Tasks |
| IV. Safety Analysis & Monitoring | IX. Final Implementation Decision & Notification |
| V. Air Traffic Control Tasks – General | X. Post-Implementation Tasks |

FIRST DRAFT – MAY 13, 2009

PROPOSAL FOR AMENDMENT TO THE

REGIONAL SUPPLEMENTARY PROCEDURES – DOC. 7030/__

NORTH AMERICAN (NAM) REGION

(Serial No. ______ – ______)

a)	Regional Supplementary Procedures:

NAM

b)	Proposed by:

United States in coordination with Canada and with the support of the Trans-Regional Airspace and Supporting ATM Systems Steering (TRASAS) group

c)	Proposed amendment:

Editorial Note: Amendments are arranged to show deleted text using strikeout (text to be deleted), and added text with grey shading (text to be inserted).

1.  Amend the SUPPS applicable in the NAM Region as shown below.

On page NAM 2-1:

CHAPTER 2.   FLIGHT PLANS

2.1.2   Area navigation (RNAV) specifications

2.1.2.1	The letter R shall be inserted in Item 10 (Equipment) of the flight plan to indicate the aircraft meets the RNAV specification prescribed, has been appropriately approved and can comply with all conditions of that approval.  Additionally, the letter Z shall be inserted in Item 10 and NAV/RNP10 or NAV/RNP4, as appropriate, inserted in Item 18.

2.1.3   Required navigation performance (RNP) specifications

2.1.3.1	The letter R shall be inserted in Item 10 (Equipment) of the flight plan to indicate the aircraft meets the RNP specification prescribed, has been appropriately approved and can comply with all conditions of that approval. Additionally, the letter Z shall be inserted in Item 10 and NAV/RNP10 or NAV/RNP4, as appropriate, inserted in Item 18.

On page NAM 4-1:

CHAPTER 4.   NAVIGATION

4.1   PERFORMANCE-BASED NAVIGATION (PBN)

4.1.1   Area navigation (RNAV) specifications

4.1.1.1	RNAV 10 (RNP 10)

Note. – RNAV 10 retains the RNP 10 designation, as specified in the Performance-Based Navigation (PBN) Manual (Doc 9613), Volume I, 1.2.5.5.

Area of Applicability

4.1.1.1.1	A lateral separation minimum of 93 km (50 NM) may be applied between flights operating on oceanic routes or areas within the control area(s) of the Anchorage Arctic FIR and Edmonton FIR/CTA.

Note. – The NAT MNPS are set forth in NAT SUPPS, 4.1.1.5. NAT MNPS airspace is identified in NAT SUPPS, 4.1.1.5.1.

Means of Compliance

4.1.1.1.2	For application of 4.1.1.1.1, operators and civil aviation authorities must follow the provisions listed below.

4.1.1.1.3	The aircraft and operator must be approved RNP 10 or RNP 4 by the State of the Operator or the State of Registry, as appropriate. RNP 10 is the minimum navigation specification for the application of 93 km (50 NM) lateral separation.

- 4.1.1.1.4	States shall ensure, when granting approval for RNP 10 or RNP 4, that operators establish programmes to mitigate the occurrence of large lateral track errors due to equipment malfunction or operational error.

Note. – The PBN Manual (Doc 9613) provides guidance on aircraft, operations and maintenance programmes for the initial achievement and continued compliance with the authorized navigation specification.

On page NAM 6-1:

CHAPTER 6.   AIR TRAFFIC SERVICES

6.2   SEPARATION

6.2.1   Lateral

(P-ATM – Chapters 5 and 15)

EXISTING WORDING TO BE DELETED?:

6.2.1.1		Minimum lateral separation in the Anchorage Arctic CTA shall be 167 km (90 NM) except the lower minima in 5.4.1.2 of the PANS-ATM may be applied, or further reduced in accordance with 5.11 of the PANS-ATM, when the conditions specified in the relevant PANS-ATM  provisions are met.

END EXISTING WORDING TO BE DELETED?

NEW 6.2.1.1??  On oceanic routes or areas within the control area(s) of the Anchorage Arctic FIR and Edmonton FIR/CTA, minimum lateral separation shall be:

a)	93 km (50 NM) between aircraft meeting the provisions in 4.1.1.1 except, minimum lateral separation between aircraft transitioning from MNPS airspace in the Edmonton FIR/CTA to other MNPS airspace shall be 110 km (60 NM);

b)  ???  In the Edmonton FIR/CTA, 110 km (60 NM) between aircraft which meet the minimum navigation performance specifications (MNPS);

c)	??? 167 km (90 NM) between aircraft not approved RNP 10 or RNP 4 or meeting MNPS.

except that lower minima as detailed in 5.4.1.2 of the PANS-ATM may be applied, or further reduced in accordance with 5.11, where the conditions specified in the relevant PANS-ATM provisions are met (see 5.4).

On page NAM 7-1:

CHAPTER 7.   SAFETY MONITORING

7.2   AIRSPACE MONITORING

7.2.2   RNAV

7.2.2.1	RNAV 10 (RNP 10)

7.2.2.1.1	A target level of safety (TLS) of 5 x 10–9 fatal accidents per flight hour per dimension shall be established for route systems operating a 93 km (50 NM) lateral separation minimum. The safety level of such airspace shall be determined by an appropriate safety assessment.

Note. – Detailed guidance material on conducting safety assessments is contained in the Manual on Airspace Planning Methodology for the Determination of Separation Minima (Doc 9689) and the Safety Management Manual (Doc 9859).

7.2.2.1.2	Adequate monitoring of flight operations shall be conducted to provide data to assist in the assessment of the achieved lateral navigation performance of the aircraft population in relation to the lateral separation minimum. A safety assessment shall be carried out periodically, based on the data collected, to confirm that the safety level continues to be met. Data shall include operational errors due to all causes.

Note. – Monitoring will be conducted in accordance with the appropriate guidance material issued by ICAO. Detailed guidance is contained in the Manual on Airspace Planning Methodology for the Determination of Separation Minima (Doc 9689) and the Safety Management Manual (Doc 9859).

d)	Date when proposal received:

e)	Proposer’s reason for amendment:

1.	On day/month/year, the United States and Canada in coordination with the Trans-Regional Airspace and Supporting ATM Systems Steering Group (TRASAS) are planning to implement a reduction of lateral separation within the control area(s) of Anchorage Arctic FIR and Edmonton FIR/CTA.

2.	93 km (50 NM) lateral separation is planned to be applied between aircraft authorized Required Navigation Performance 10 (RNP 10) or RNP 4 by the State of Registry or State of Operator, as appropriate, operating on oceanic routes or areas.

Note. – Guidance and direction for RNP authorization is provided in ICAO Annex 6, Parts I and II, paragraph 7.2 (Navigation equipment). Criteria for the application of 93 km (50 NM) lateral separation between aircraft authorized RNP 10 or RNP 4 is currently published in Regional Supplementary Procedures for various regions including the CAR, NAT and PAC.

3.	Implementation of 93 km (50 NM) lateral separation in the Anchorage Arctic FIR and the Edmonton FIR/CTA will harmonize the application of 93 km (50 NM) lateral separation across the Pacific CTA/FIRs, the Anchorage Arctic FIR and Edmonton FIR/CTA.

4.	Reduction of lateral separation from 167 km (90 NM) to 93 km (50 NM) in the Anchorage Arctic FIR will increase the availability of routes and flight levels in the Anchorage Arctic FIR and enable more aircraft to operate on time and fuel efficient routes and flight levels.  This, in turn, will reduce fuel burn and engine emissions. In addition, en route capacity and air traffic management (ATM) flexibility will be enhanced.

5.	Analysis of aircraft types operating in the oceanic areas affected by this initiative indicates that almost all of the flights conducted in the airspace are now flown by aircraft meeting

RNP 10 or RNP 4 standards without modification.

6.	Aircraft that are not authorized RNP 10 or RNP 4 (non-RNP 10 aircraft) will be allowed to continue to file any route at any flight level in areas listed above. They will be cleared to operate on their preferred routes and flight level as traffic permits, however, 93 km (50 NM) lateral separation will not be applied to them.

7.	93 km (50 NM) lateral separation has been applied between operators/aircraft authorized RNP 10 or RNP 4 since 1998 in Pacific oceanic areas. It is also currently applied in the West Atlantic Route System (WATRS), in the European-South American Corridor; on routes between Santiago, Chile and Lima, Peru; on routes connecting Australia, Asia, the Middle East and Europe south of the Himalayas and trans-Africa routes. Project planners will currently apply the experience gained in these other areas to implementation planning for the Arctic FIRs and in the WATRS operational plans development.

f)	Proposed implementation date of the amendment: Day/Month/Year

g)	Proposal circulated to the following States and international organizations:

h)	Secretariat comments:

1.	The United States and Canada, working under the auspices of the Trans-Regional Airspace and Supporting ATM Systems Steering (TRASAS) group, have undertaken the task of implementing RNAV 10 (denoted as Required Navigation Performance 10 (RNP 10)) specifications for use of 50 NM lateral separation.

2.	Implementation of RNAV 10 (RNP 10) in the Arctic FIR’s controlled by the United States and Canada will allow 50 NM lateral separation to be applied. This is a pre-requisite for the redesign of _______ and will allow operators to receive benefits from ______a 40% increase in the number of routes as well as more direct route trajectories.

3.	??Monitoring arrangements for pre and post RNP 10 implementation have been established through the North American Approvals Registry and Monitoring Organization (NAARMO).??

— END —