Eighth Meeting of the Cross Polar Trans East Air Traffic Management Providers’ Work Group (CPWG/8)

(Atlanta, USA, 2-4 December 2009)

Agenda Item 4:	Provide Status on CPWG/7 Actions

- Anchorage Air Route Traffic Control Center (ZAN) Future Arctic Ocean21 Sector

- (Action Item # CP06-02)

(Presented by the Federal Aviation Administration)

SUMMARY This paper presents information on Anchorage Air Route Traffic Control Center (ZAN)’s plan to transition control of its Arctic Flight Information Region (FIR) from the FDP2000/MEARTS automation platform to the Ocean21 automation platform. The Arctic FIR transition is scheduled as the second phase of a larger effort to transition several ZAN sectors to the Ocean21 system.

- Introduction

- ZAN redesigned its airspace, changing from two specialties (East and West) to three specialties (North, South, and High) in May 2003.  The High Specialty was created specifically to utilize the Ocean21 (OC21) automation system developed by the FAA Advanced Technologies and Oceanic Procedures (ATOP) program.  Initial Operating Capability (IOC) for Ocean21 was achieved on 1 March 2007.  However, only two of the five High Specialty sectors transitioned from the Flight Data Processing (FDP) 2000/ Microprocessor En Route Automated Radar Tracking System (MEARTS) system to OC21.  High Specialty Sectors 10 and 11 (surface to FL600) were primarily oceanic and thus posed low risk to transition.  However, all or part of Sectors 63, 68, and 69 was stratified (FL290 to FL600) to avoid airport traffic, which OC21 does not handle well.  When software problems were encountered with the automated transfer of aircraft between OC21 and FDP2000/MEARTS in the stratified airspace, the transition of those remaining three “Sixties Sectors” to OC21 was indefinitely postponed.

- The OC21 system remains under-utilized at ZAN (only 1-2 sector positions staffed in an area with equipment capacity for nine positions).  Current High Specialty staffing on two automation platforms - OC21 and FDP2000/MEARTS - lengthens required training time and creates unnecessary overtime costs.  Transitioning the remaining Sixties Sectors will eliminate this situation, as well as benefit the airlines by increasing routing efficiencies and enabling reduced flight times, thereby reducing fuel costs.  In addition, ZAN’s Arctic FIR is the FAA’s last oceanic airspace without OC21 automation; therefore, its transition has become an FAA priority to achieve further cost benefits.  ZAN proposed creation of a new OC21 sector - Sector 64 – from current Sector 4 for this purpose.  The Sixties Sectors now collectively implies current Sectors 63, 68, 69 and the proposed new Sector 64.

- Discussion

- ZAN finalized a plan in December 2008 to transition Sectors 63, 68, 69 to OC21 in May 2009 (Phase 1) and implement new Sector 64 (Phase 2) at the end of September 2009, with a major tech refresh of OC21 hardware scheduled in-between.  Software fixes to the automation problems with transfers in stratified airspace was not available; however, ZAN had achieved sufficient system stability and operational experience with OC21 and it was expected that the Sixties Sectors could be transitioned using interim workaround procedures until the software was delivered.  ZAN tested the workaround procedures using the Dynamic Simulator in February 2009.  When the procedures did not work, the transition had to be delayed.

- Three software National Change Proposals (NCP) are currently required to resolve the automation problems with transfers in stratified airspace.  The MEARTS En Route Next Leg Processing NCP should be delivered in May-June 2010.  The Preferred Arrival Route Processing NCP is scheduled for implementation in September 2010.  The North American Interface Control Document (NAM ICD) NCP can be implemented in February 2011.  If the NCPs are delivered as scheduled, Phase 1 (63, 68, 69 transition) would be implemented in April 2011 and Phase 2 (Sector 64) would be implemented in May 2011.

- ZAN is considering the option of establishing an offshore OC21 Sector 64 as a step that could be taken in the meantime.  Although easier to implement from an automation standpoint (no stratification), a “sector swap” would be necessary to avoid staffing shortages in the High Specialty.  A second option includes a stratified shelf that captures traffic transiting the north coastline and the Brooks Range en route to PILUN/LISKI.  The stratification issues that apply to Sectors 63, 68 and 69, would also apply to the Sector 64 shelf.  Sector 64 with the shelf option will require the installation of Remote Communications Air/Ground (RCAG) and Backup Emergency Communications (BUEC) communications equipment on the North Slope to support High Specialty communication with cross-polar traffic there.  The ATOP Program Office has already provided funding to conduct the required engineering studies.  Radio equipment will be installed at Cape Lisburne, Barrow, and Barter Island; and back up radios will be sited at Point Lay and Deadhorse.  Construction is scheduled for summer 2010.

- Recommendation

- The Meeting is invited to note the information provided in this paper.

Proposed Sector 4 and 64 Reconfiguration