Coordination
Draft

FANS 1/A over
Iridium (FOI)
Project Plan

9 September 2008

Prepared by:

Performance Based Operations
Aviation Rulemaking Committee

Communications Working Group
(PARC CWG)

Foreword

The Performance-Based Operations Aviation Rulemaking Committee (PARC) is an FAA-sponsored activity that operates according to the Administrator’s authority under 49 USC 106(p)(5).  The PARC comprises members from the FAA and the aviation community at large, provides recommendations to FAA’s Senior Management for action and implementation.  The PARC has been effective over the last decade in implementing RNAV/RNP.  In 2005, the PARC established the Communications Working Group (CWG) to address a number of issues related to the implementation of aeronautical communication systems.  These systems included, among others, the future air navigation system (FANS) 1/A, the aeronautical telecommunication network (ATN), and satellite voice communications.

The PARC CWG is committed to applying the performance-based concept, which aims to leverage existing capability and maximize benefits by:

- Enabling cost-effective alternatives, using different technologies and existing capabilities, that meet business needs in a more timely manner;

- Providing performance-based criteria to demonstrate aircraft equipment and capability without technological or implementation-specific constraints; and

- Enabling different levels of service in common airspace to a fleet of aircraft with varying capability and performance.

The PARC CWG develops recommendations that directly support matters that relate to the FAA’s regulatory criteria and guidance material for implementation of voice and data communications within the U.S. National Airspace System (NAS).  However, the PARC CWG recognizes that global harmonization is crucial to the success of any State or regional implementation initiative.  As such, the PARC CWG prepares Coordination Drafts for broad review and solicits input on such matters of interest to the aviation community.  If you would like more information on PARC CWG activities or would like to comment on this Coordination Draft, please contact either Arnold Oldach (aoldach@rockwellcollins.com) or Tom Kraft (tom.kraft@faa.gov).

Table of contents

Contents		Page

Background	3

Goal of this project plan	3

Prerequisites	3

Project Administration	3

Stakeholders	3

Success criteria	3

Description of project	3

Operations	3

Aircraft equipage	3

End-to-end Iridium satellite system overview	3

Qualification means	3

Qualification Phase Definitions	3

Deliverables	3

End-to-end bench tests	3

Initial in-service operational trial	3

Project schedule	3

Attachments

Attachment A – Criteria for FANS 1/A over Iridium Project

Attachment B – FANS 1/A Over Iridium End-to-End Configurations

Attachment C – Iridium Satellite Network Pre-FOI Performance Reporting

Revision History

| Date | Description of changes |  |
| --- | --- | --- |
| 14-Jun-08 | incorporates changes and agreements at PARC CWG 15 includes placeholders for open action items and other updates |  |
| 25-Jun-08 | Includes configurations for Continental Micronesia and Cargolux fleets in Appendix B. |  |
| 31-Aug-08 | Updated following PARC CWG 16 meeting, includes data collection, analysis and reporting methods, Cargolux details, schedule updates, and other editorial cleanup. |  |
| 6-Sep-08 | Reformatted, added Foreword, editorial cleanup, incorporated data collection for restoration notifications, added prerequisite for aircraft equipment to comply with RTCA DO-262A, Iridium Satellite Normative Appendix. |  |

# Background

Over the last three years use of the Iridium satellite voice and data communications service to support the aviation community has grown dramatically.  Initial installations were geared more toward the business aviation market.  As new avionics were developed more than 10 commercial operators have installed Iridium systems for voice and data Aeronautical Operational Control (AOC) communications.  However, International Civil Aviation Organization (ICAO) has since approved Annex material to enable the use of Iridium for provision of air traffic services.  Also, both ARINC and SITA, the two main data link service providers, are providing ACARS over Iridium (AOI) as a new sub-network service, which has generated a lot of interest from commercial operators to pursue safety service certification.

Toward the end of last year some preliminary FANS 1/A over Iridium (FOI) scoping tests were run to assess the feasibility of using Iridium as an ACARS sub-network to support FANS 1/A ATC data link applications, specifically controller-pilot data link communications (CPDLC) and automatic dependent surveillance – contract (ADS C).  After several successful live end-to-end FOI informal tests, it is time to move forward toward more formal validation of Iridium as a viable sub-network supporting FANS 1/A data link applications.

It is envisioned that operators will benefit from the use of the Iridium satellite network for FANS 1/A applications by enabling fuel savings by offering more opportunities to apply reduced separations between approved aircraft pairs, more timely optimum route clearances, more efficient routes, and reduced weight from Iridium equipage as compared to Inmarsat.

# Goal of this project plan

This document defines the process that will be used to evaluate the Iridium sub-network with a goal of achieving approval as a viable sub-network for aeronautical safety services.

- The near term objective is to use Iridium as a viable sub-network for FANS 1/A applications supporting RCP 240 operations in different oceanic separation standards.  Some examples of the different separation standards where FANS 1/A provides an acceptable data link capability for RCP 240 operations are; reduced separation to 50nmi longitudinal in RNP 10 airspace, 30nmi lateral / 30nmi longitudinal.  Examples of different separation standards where FANS 1/A provides an acceptable data link capability for RCP 400 operations are; reduced separations to 50nmi lateral and existing time-based longitudinal separations.

- The mid term objective is to obtain operational approval of Iridium voice communications and data communications as a long range communication system equivalent to today’s HF radios enabling MEL relief to dispatch the aircraft with one HF radio inoperative.

- The longer term objective, given Iridium proves viable, is to evaluate architectures that use dissimilar sub-networks, e.g., VHF, Iridium, Inmarsat, HFDL, to meet performance criteria required to support longer term oceanic/remote operations and regressed HF voice operations.

# Prerequisites

In accordance with established PARC CWG procedures, participants must agree to provide information and data necessary to substantiate the goals of the project

Operators participating in this project must be eligible for FANS 1/A operations per Advisory Circular (AC) 120-70A, Operational Authorization Process for use of Data Link Communication System.

The data link capability for participating aircraft must be certified in accordance with AC 20-140, Guidelines for Design Approval of Aircraft Data Communications Systems, or equivalent.  The design approval must include:

- The FANS 1/A data link (CPDLC and ADS-C) installation has been shown to meet RTCA DO-258/EUROCAE ED-100 (transport and above), or later revision;

- The Iridium satellite data unit (SDU) installation has been shown to meet ARINC 741; and

- The SDU interface with the FANS 1/A applications has satisfactorily completed the airframe manufacturers Aircraft Equipment Interoperability Testing (AEIT)

# Project Administration

This project will be administered by the Performance-based Operations Aviation Rulemaking Committee’s (PARC) Communications Working Group (CWG).  For further information on becoming an eligible participant in the project, contact the PARC CWG chairmen, Tom Kraft (tom.kraft@faa.gov), Arnold Oldach (aoldach@rockwellcollins.com).

Brad Cornell (Bradley.d.cornell@boeing.com) will be the coordinator for this project plan, update it, as necessary, and distribute the updates to the participants and stakeholders of this project.

The data collected and results of any analyses will be provided to the PARC CWG.  The PARC CWG may rely on existing FANS Central Reporting Agency (CRA) for analysis, problem resolution, and improvement to support the project.  Regardless, the PARC CWG will ensure processes are in place to secure individual confidentiality of any data or analysis.

The PARC CWG will use the results from this project exclusively to substantiate the recommendations it formulates for the PARC to the FAA on the enabling criteria needed to approve the use of Iridium for ATS data communications.  Any other use that may come up during the course of this project will be negotiated by the parties involved prior to that use.

# Stakeholders

The participants in this trial are provided in Table 1.

Table 1 – FOI Project Participants

| Organization | Point of contact | email |
| --- | --- | --- |
| PARC CWG | Arnold Oldach Tom Kraft | aoldach@rockwellcollins.com tom.kraft@faa.gov |
| Aircraft Operators |  |  |
| Continental Airlines | Ron Renk (Primary) Janet Wiesner | ron.renk@coair.com Janet.Wiesner@coair.com |
| Continental Micronesia Airlines | Ralph Freeman (Primary) Dion Johnson | ralph.freeman@coair.com dion.johnson@coair.com |
| Cargolux | Bernard Korsec | Bernard.Korsec@cargolux.com |
| Qantas | Graham Rennie | grennie@qantas.com.au |
| Aircraft Manufacturers |  |  |
| Boeing | Brad Cornell | bradley.d.cornell@boeing.com |
| Avionics Suppliers |  |  |
| GE Aviation Systems | Jane Jurgensen | jane.jurgensen@ge.com |
| Avionica | Tony Rios | arios@avionica.com |
| ICG | Armin Jabs | AJabs@intcomgrp.com |
| Air Navigation Service Providers |  |  |
| UK NATS | Dave Lacey | david.lacey@nats.co.uk |
| NAV Canada | Kevin Stevens (primary) Norm Dimock | stevens@navcanada.ca dimockn@navcanada.ca |
| Isavia (Iceland) | Leifur Hákonarson | Leifur@isavia.is |
| Airways Corporation New Zealand | Paul Radford | Paul.Radford@airways.co.nz |
| FAA, Air Traffic Organization (ATO), Oceanic Operations | Karen Chiodini Dennis Addison (Oakland Center) Bob Hansen (Oakland Center) | Karen.l.chiodini@faa.gov dennis.addison@faa.gov bob.hansen@faa.gov |
| JCAB (Japan) | Yoshiyuki Mikuni | mikuni-y2bd@mlit.go.jp |
| Airservices (Australia) | Bob Peake (primary) Adam Watkin | Bob.Peake@AirservicesAustralia.com Adam.Watkin@AirservicesAustralia.com |
| Communication Service Providers |  |  |
| SITA | Eric Mehn | eric.mehn@sita.aero |
| ARINC | Tim Hinson | thinson@arinc.com |
| Iridium | Mike Meza | Mike.Meza@iridium.com |
| Operational Authorization and Aircraft Certification (FAA) |  |  |
| Federal Aviation Administration (FAA), Principal Ops Inspector (POI) for CMI | Gale Huey | gale.r.huey@faa.gov |
| FAA, Flight Standards, Flight Technologies and Procedures Division | Robert M Tegeder (Primary) Madison Walton David Maloy Tom Parmer | robert.m.tegeder@faa.gov madison.walton@faa.gov david.maloy@faa.gov Thomas.parmer@faa.gov |
| FAA, Flight Standards, Air Transportation Division | David Catey Robert M Davis (MEL Policy) | david.catey@faa.gov robert.m.davis@faa.gov |
| FAA, Aircraft Certification, Avionics Systems Branch | Dave Robinson (Primary) Matt Wade | matthew.wade@faa.gov david.w.robinson@faa.gov |

# Success criteria

The success criteria that will be used to evaluate the viability of FANS 1/A over Iridium can be found at Attachment A, which was based on:

- RTCA DO-306/EUROCAE ED-122, Safety and Performance Standard for Air Traffic Data Link Services in Oceanic and Remote Airspace, October 11, 2007; and

- Additional operational requirements as negotiated through various forums (e.g., NAT SPG (NAT FIG, RCP Task Force, ISPACG Data Link Working Group and FIT, IPACG FIT, etc).

# Description of project

## Operations

Continental Micronesia (CMI) is on schedule to outfit 9 Boeing 737-800 aircraft with an ARINC 741 compliant voice and data capable Iridium based SATCOM system. These aircraft will be equipped with a certified FANS 1/A package and Iridium SDUs. These aircraft are based in Guam and fly daily extended over water operations outside of VHF coverage (see Figure 1) in airspace currently supporting FANS services.  After obtaining operational authorization, these aircraft will fly using FANS 1/A ATC data link services via CPDLC and ADS-C. Five aircraft will be configured to use the SITA network and other four will be configured to use the ARINC network.

Figure 1 – CMI routes supporting FOI project

Cargolux (CLX) is on schedule to outfit 4 Boeing 747-400 aircraft with Iridium and the FANS 1/A package to support an operational trial to start in January 2009.  Each aircraft will be equipped in a different configuration to use different Avionica and ICG SDUs and different ARINC and SITA networks.  Cargolux operates in over 55 countries and services over 60 flight destinations (See Figure 2.)

Figure 2 – Cargolux routes supporting FOI project

## Aircraft equipage

The federated architecture typical for Airbus and Boeing aircraft equipment related to data link capability is shown in Figure 3.  The aircraft equipage must meet the prerequisites to participate in this project.  This project will evaluate the Avionica satLINK and ICG ICS-220A SDUs in various configurations which can be found at Attachment B.

Figure 3 – Typical federated aircraft architecture

## End-to-end Iridium satellite system overview

The end-to-end Iridium satellite system overview is shown in Figure 4.

Figure 4 – End-to-end Iridium satellite system overview

# Qualification means

A traditional phased testing plan used with other sub-network media will be used to qualify the Iridium sub-network.  Both ARINC and SITA offer ACARS over Iridium (AOI) service, which is a prerequisite to offering FOI.  End-to-end bench tests and monitored in-service tests defined in more detail below will ensure the Iridium based sub-network performs as intended to support ATS services.

## Qualification Phase Definitions

The qualification phases are:

- ARINC Avionics Qualification Program (AQP) and/or SITA Validation Assessment and Qualification (VAQ)

- End-to-end bench tests prior to operational trial

- In-service AOI (Pre-FOI) and FOI operational trials.

## Deliverables

The deliverables are:

- The ANSPs will provide statistically sufficient data sample of CPDLC transactions (only those requiring W/U response) and ADS-C position reports.

  - For each CPDLC data point, the data will include aircraft registration, time CPDLC uplink sent, time message assurance (MAS) received, time indicated in timestamp of downlink W/U response message, time response message received by the center’s system.

  - For each ADS-C data point, the data will include aircraft registration, time message sent by the aircraft and the time message received by the center.  (Undelivered messages need to be included in the data analysis).

- Prior to the start of the operational FOI trial, ARINC, SITA, and Iridium will provide data, analysis, and review to CWG in accordance with the criteria provided at Attachment C.

- The aircraft operators, controllers, communication service providers, or any participant should report any anomalies or potential problems using problem reporting procedures already in place for FANS 1/A data link operations, also submit the problem report to the PARC CWG.

## End-to-end bench tests

Prior to allowing any in-service operations, the Iridium sub-network must pass some structured formal bench testing. In addition to avionics test benches coordination will be required with appropriate ATC ground systems to enable end-to-end operational evaluations.  Boeing will install a representative Iridium based Satcom system into a 747 and 777 test bench at Boeing Field, Washington. This installation will have the ability to connect to either SITA’s or ARINC’s live ACARS network.  Boeing will coordinate with various Pacific and Atlantic oceanic ATC facilities and at a minimum with Oakland center (ZOA) to schedule formal live end-to-end evaluation tests.  In addition to single network tests several tests that require Iridium data link traffic to exercise the internetworking channel between the two DSPs will be executed.

Deliverables from end-to-end bench tests will be provided to the PARC CWG. The PARC CWG will coordinate with the established regional coordinating groups currently managing FANS services (i.e., IPACG, ISPACG, FIT-BoB, and NAT-FIG).

## Initial in-service operational trial

Once PARC CWG agrees successful ground tests have been completed, operational trials will commence.

# Project schedule

The FOI project schedule is shown in Figure 5.

Figure 5 – FOI project schedule

- – Criteria for FANS 1/A over Iridium Project

  - Extraction of DO-306/ED-122 performance requirements for RCP 240 and RCP 400

    - DO-306/ED-122 provides safety and performance requirements for data link services as follows:

- Data link services used in lieu of high frequency (HF) voice, greater than or equal to 50 NM lateral separation and existing time-based longitudinal separations, e.g., minimum navigation performance standard (MNPS);

- Data link services required for 30 NM lateral/30 NM longitudinal and 50 NM longitudinal separation standards; and

- Considering route conformance monitoring, separation assurance, reroutes, and weather deviations.

    - RTCA DO-306/EUROCAE ED-122 provides safety and performance requirements for communication and surveillance capabilities from an end-to-end perspective and allocates these requirements to all relevant components of the end-to-end system.  These components include the aircraft systems, flight crew procedures, communication service provider systems, and the procedures and systems at the oceanic air traffic control (ATC) centre (OAC).

    - DO-306/ED-122 provides a number of safety requirements.  These requirements were derived from an operational safety assessment that evaluated the effects of hazards on the intended operations.  The assessment contributed to the validation of the assumptions used to introduce the communications and controller intervention buffer (described in Appendix 5 of ICAO Doc 9689) to collision risk modeling for the separation standards.  The results of the assessment were also used to determine the availability, continuity, and integrity values for the required communication performance (RCP) types associated with the intervention capability and other requirements associated with the surveillance capability.  Showing compliance to these requirements is typically done as part of the initial approval processes for the different components of the system, e.g., type design approval, operational authorizations, and service provision.

    - The requirements provided by DO-306/ED-122 are consistent with ICAO provisions, including those for the separation standards provided in ICAO Doc 4444 for longitudinal distance-based separation minima.  The requirements associated with the controller intervention capability, such as with the controller-pilot data link communications (CPDLC) application, are grouped using the RCP 240 and RCP 400 labels.  The different RCP types are intended to apply to the different operating contexts as described in paragraph Attachment A.  Similarly, other requirements associated with the surveillance capability, such as with the automatic dependent surveillance – contract (ADS-C) application, are also grouped according to the different operating contexts.

    - Figure A- provides a time diagram that depicts a typical operational communication transaction for an intervention.  The RCP type applies to the complete transaction.  The various components, e.g., flight crew/human machine interface (HMI), aircraft system, etc., are shown and physical lines of demarcation have been identified to define the time allocations appropriate for any particular RCP type.  These allocations are used as a basis for component approval and operational monitoring.  The two significant allocations are the monitored operational performance, denoted by TRN, and the required communication technical performance, denoted by RCTP.

Figure A- – RCP allocations for intervention capability (DO-306/ED-122, Figure 5-3)

    - Table A- provides the time allocations for RCP 240 and RCP 400 when applied to a data communication transaction (denoted by /D).  The two RCP types are specified to support intervention capabilities for 50 NM longitudinal, 30 NM longitudinal, and 30 NM lateral separation minima.  Per ICAO Doc 4444, these separation minima require a normal means of communication and an alternative means of communication.

    - For RCP 240 and RCP 400, two sets of time values are provided.

- The first set of time values provided in the ET column is the allocation for the communication transaction time per ICAO Doc 9869.  The communication transaction time is the maximum time for the completion of the operational communication transaction after which the initiator should revert to an alternative procedure.  The frequency at which the maximum time can be exceeded is specified by the continuity requirement.

- The second set of time values provided in the 95% column is the allocation for normal operations or the time at which 95% of all attempted transactions have been successfully completed.

Note:	As the criteria for RCP 240 applies to the intervention capability in reduced separation environments, the end-to-end monitoring need only consider CPDLC transactions that are typical of an intervention capability, i.e., relatively simple clearances requiring a W/U response.

Table A- – 50 longitudinal and 30/30 - intervention (DO-306/ED-122, Table 5-6)

| RCP type | RCP 240/D |  | RCP 400/D |  |
| --- | --- | --- | --- | --- |
| Time Parameter | ET | 95% | ET | 95% |
| Time Value | 240 | 210 | 400 | 350 |
| RCP Time Allocations |  |  |  |  |
| Initiator | 30 | 30 | 30 | 30 |
| TRN | 210 | 180 | 370 | 320 |
| TRN Time Allocations |  |  |  |  |
| Responder | 60 | 60 | 60 | 60 |
| RCTP | 150 | 120 | 310 | 260 |
| RCTP Time Allocation |  |  |  |  |
| Aircraft | 15 | 10 | 15 | 10 |
| Communication service | 120 | 100 | 280 | 240 |
| ATS unit | 15 | 10 | 15 | 10 |
| Note 1: Values shown in seconds. Note 2: Expiration time (ET) is at the continuity requirement, which is 99.9%. |  |  |  |  |

    - Table A- provides the time allocations for position report delivery times when applied to a surveillance capability supported by data communications.  The delivery times are specified to support surveillance capabilities for 50 NM longitudinal, 30 NM longitudinal, and 30 NM lateral separation minima.  Per ICAO Doc 4444 and/or regional supplements, these separation minima collectively require position reports that are provided periodically, when the aircraft’s flight plan changes waypoint, and when the aircraft deviates laterally from its active flight plan by more than a specified distance, e.g., 5 NM.

- Normal surveillance – The position reporting (PR) service shall deliver a position report within 180 seconds at the continuity requirement and within 90 seconds at 95% probability for:

  - Periodic report, from the start of the periodic interval. The start of the periodic interval occurs when the periodic report is sent by the aircraft (see DO-306/ED-122, Figure 5-2); and

  - Waypoint change event report, from the actual time the aircraft crosses the waypoint.

- Normal surveillance – The information exchange and reporting (IER) service shall deliver the lateral deviation event report within 180 seconds at the continuity requirement and within 90 seconds at 95% probability from the time the aircraft system detects that the event has occurred.

- Non-normal surveillance – The IER service delivers a position report within 240 seconds at the continuity requirement and within 180 seconds at 95% probability for ADS-C demand report or CPDLC position report, from the time the ADS-C demand contract or CPDLC request was initiated by the ATS unit/controller.

Table A- – 50 longitudinal and 30/30 - surveillance (DO-306/ED-122, Table 5-7)

| Position report delivery times | Periodic, Waypoint, or Lateral Deviation Event |  |
| --- | --- | --- |
| Time Parameter | ET | 95% |
| Time Value | 180 | 90 |
| Time Allocation |  |  |
| Aircraft | 5 | 3 |
| Communication service | 170 | 84 |
| ATS unit | 5 | 3 |
| Note 1: Values shown in seconds. Note 2: Expiration time (ET) is at the continuity requirement, which is 99.9%. |  |  |

    - Table A- provides the time allocations for RCP 400 when applied to a data communication transaction (denoted by /D).  RCP 400 is specified for data communications used for intervention supporting lateral separations greater than or equal to 50 NM and existing time-based longitudinal separations, e.g., MNPS.  Per ICAO Doc 4444, these separation minima require only a normal means of communication, even though voice communication continues to be a requirement.

    - Table A- provides the time allocations for position report delivery times when applied to a surveillance capability supported by data communications.  The delivery times are specified to support surveillance capabilities for lateral separations greater than or equal to 50 NM and existing time-based longitudinal separation minima.  Per ICAO Doc 4444 and/or regional supplements, these separation minima only require position reports that are provided when the aircraft’s flight plan changes waypoint, although other types of position reports may be used.

Table A- – >50 lateral and time-based longitudinal - surveillance
(DO-306/ED-122, Table 5-8)

| Position report delivery times | Periodic, Waypoint, or Lateral Deviation Event |  |
| --- | --- | --- |
| Time Parameter | ET | 95% |
| Time Value | 400 | 300 |
| Time Allocation |  |  |
| Aircraft | 30 | 15 |
| Communication service | 340 | 270 |
| ATS unit | 30 | 15 |
| Note 1: Values shown in seconds. Note 2: Expiration time (ET) is at the continuity requirement, which is 99.9%. |  |  |

    - Table A- provides the values assigned to the availability, continuity, and integrity parameters applicable to operational transactions associated with the data link services used for intervention and position reporting.  These values are determined using DO-306/ED-122, Table 1-1 and the relevant safety objective(s) and qualitative probabilistic term(s) provided in DO-306/ED-122, Table 5-2.  The values for availability and continuity are defined as one minus the quantitative value assigned to the probabilistic term for the safety objectives associated with the parameter.

Table A- – Continuity, integrity, and availability (DO-306/ED-122, Table 5-9)

| Parameter | Value See Note 1 and Note 2. | Source information |  |  |
| --- | --- | --- | --- | --- |
|  |  | Safety Objectives per Table 5-2 | Hazard/ qualitative term per Table 5-2 | Quantitative value per Table 1-1 |
| Availability of service provision for all aircraft | 0.999 [1-10-3] | SO-1 | Loss of data link service (multiple aircraft, detected case) probable | 10-3 |
| Availability of an aircraft to use the service | 0.999 [1-10-3] | SO-2 | Loss of data link capability (single aircraft, detected case) probable | 10-3 |
| Continuity © | 0.999 [1-10-3] | SO-3 SO-4 SO-5 SO-6 | Unexpected interruption of the transaction (loss after initiation) probable | 10-3 |
| Integrity (I) | 10-5 | SO-7 SO-8 SO-9 SO-10 | Undetected corruption of the transaction remote | 10-5 |

    - Table A- provides the intended uses for RCP 240 and RCP 400

- RCP 240 is specified for the normal means of communication.

- RCP 400 is specified to support either an alternative (and independent) data communication means in reduced separation environments or as a normal data communication means when lateral separations are greater than or equal to 50 NM and existing time-based longitudinal separation, e.g., MNPS.

    - The above criteria are consistent with ICAO Doc 9869.

- Paragraph 3.2.6 indicates that RCP 240 would be used for controller intervention capability supporting separation assurance in a 30/30 separation environment.

- Paragraph 3.2.7 indicates that RCP 400 would be used for controller intervention capability supporting separation assurance in current environments where separations are greater than 30/30 and alternative technologies are planned for providing normal means of communication, e.g., Iridium voice or HF data link in lieu of HF voice.

    - It is noted that the scope of DO-306/ED-122 is for data communications.  Therefore, the allocations provided are suitable for data communication technologies.  The allocations for the data communications would not be applicable for voice communication technologies.  However, it is noted that the RCP types could be considered to establish a specification for alternative technologies (other than HF voice) for voice communications.

Table A- – Applicability of RCP types (DO-306/ED-122, Table 5-10)

| RCP type | Intended use | Transaction time (ET) (sec) | Continuity © (probability/ flight hour) | Availability (A) (probability/ flight hour) | Integrity (I) (acceptable rate/ flight hour) |
| --- | --- | --- | --- | --- | --- |
| RCP 240 | Normal means of communication for application of 30 NM lateral separation and reduced distance-based longitudinal separation minima | 240 See paragraph 5.2.3 | 0.999 See paragraph 5.2.5 | 0.999 See paragraph 5.2.5 | 10-5 See paragraph 5.2.5 |
| RCP 400 | Alternative means of communication for application of 30 NM lateral separation and reduced distance-based longitudinal separation minima | 400 See paragraph 5.2.3 | 0.999 See paragraph 5.2.5 | 0.999 See paragraph 5.2.5 | 10-5 See paragraph 5.2.5 |
| RCP 400 | Normal means of communication for application of lateral separation greater than or equal to 50 NM and time-based longitudinal separation | 400 See paragraph 5.2.4 | 0.999 See paragraph 5.2.5 | 0.999 See paragraph 5.2.5 | 10-5 See paragraph 5.2.5 |
| Note: The values for parameters of RCP types have been adjusted from those provided in ICAO Doc 9869 based on the results of the operational safety and performance assessments provided in section 5. |  |  |  |  |  |

  - Additional requirements to DO-306/ED-122 for RCP 240 and RCP 400

    - At the Special NAT SPG meeting, it was concluded that the RCP 240/D specification would include an additional service availability requirement for operational efficiency.  While DO-306/ED-122 specified a service availability requirement of 0.999 for safety, a service availability requirement of 0.9999 was needed for operational efficiency.  On a per Oceanic ATC Centre (OAC) basis, the 0.9999 service availability requirement would further translate into:

- No more than 4 outages (affecting a significant portion of aircraft) greater than 10 minutes for any 12 month period;

- Failures causing outages for multiple OACs are not counted more than once; and

- No more than 50 minutes of total downtime for any 12 month period.

    - At the NAT SPG Technical Task Force meeting, it was further concluded that the RCP 400/D specification would include additional clarification to the 0.999 service availability requirement as follows:

- No more than 24 outages (affecting a significant portion of aircraft) greater than 20 minutes for any 12 month period;

- Failures causing outages for multiple OACs are not counted more than once; and

- No more than 9 hours of total downtime for any 12 month period.

    - Furthermore, it was concluded that while DO-306/ED-122 included requirements for monitoring and alerting, additional requirements were needed on the time it would take to report an outage to the OAC.  This time is referred to in the North Atlantic Region as the indication delay.  After an outage begins, indication delay is the time before the communications service provides ATC automation with a positive indication that there is an outage.  The indication delay is 5 minutes for RCP 240 operations.  The indication delay is 10 minutes for RCP 400 operations.

Ed Note:  More work is needed on outage and restoration notifications.  During the last meeting, there was some discussion on Iridium service interruption announcements and warnings of future possible service degradation. The existing and necessary procedures may provide a starting point for developing guidance material related to outage and restoration notification to meet the “performance-based” criteria for RCP 240.  Note the criteria above is from when the outage begins to when the ANSP receives notification.  It is suggested also that if ANSPs are not notified of restoration, than that would seriously impact the overall yearly availability measurement against the 9 hour criteria for any 12-month period.

- – FANS 1/A Over Iridium End-to-End Configurations

  - Operational Trials

    - Continental Micronesia fleet planned for January 1, 2009 is shown in Table B-.

Table B- – CMI FOI Fleet Configuration

| A/C Registration | Iridium Satcom | ACARS | Service Provider |
| --- | --- | --- | --- |
| N25201 | Avionica satLINK | Collins CMU-900 | SITA |
| N13227 | Avionica satLINK | Collins CMU-900 | SITA |
| N14228 | Avionica satLINK | Collins CMU-900 | SITA |
| N26232 | Avionica satLINK | Collins CMU-900 | SITA |
| N14235 | Avionica satLINK | Collins CMU-900 | SITA |
| N35236 | Avionica satLINK | Collins CMU-900 | ARINC |
| N14240 | Avionica satLINK | Collins CMU-900 | ARINC |
| N27246 | Avionica satLINK | Collins CMU-900 | ARINC |
| N14249 | Avionica satLINK | Collins CMU-900 | ARINC |

    - Cargolux fleet planned for January 1, 2009 is shown in Table B-.

Table B- – Cargolux FOI Fleet Configuration

| A/C Registration | Iridium Satcom | ACARS | Service Provider |
| --- | --- | --- | --- |
| LX-FCV | ICG ICS-220A |  | ARINC |
| LX-GCV | ICG ICS-220A |  | SITA |
| LX-KCV | AVIONICA satLINK |  | ARINC |
| LX-LCV | AVIONICA satLINK |  | SITA |

- – Iridium Satellite Network Pre-FOI Performance Reporting

  - ACARS over Iridium (AOI) Data collection, analysis, and presentation

    - ICAO Annex 11 requires States to monitor data link performance to verify that data link services continue to meet an acceptable level of safety.  To facilitate in the decision to start in-service operational evaluation of FANS over Iridium it is essential to coordinate and establish a common methodology for the reporting of data link performance.  However, until there are participating aircraft exchanging FANS-1/A messages over Iridium, the performance of non-FANS-1/A ACARS over Iridium (AOI) message exchanges will be assessed via the two air-ground data link service providers, ARINC and SITA, Iridium, and the avionics vendors to establish a data link performance reporting plan.  Once participating aircraft start exchanging FANS-1/A messages with participating ANSPs, the ANSPs will then collect and monitor end-to-end performance data, and communication service providers will support data collection and analysis, on an as needed basis.

    - This portion of the overall FANS over Iridium project plan establishes the following for ACARS over Iridium:

- Values (data) to be collected

- Resolution of the data being collected

- Collection and reporting period

- Methodology for analyzing and presenting the data collected

- Methodology for treatment of performance data outliers, such as:

  - Drop outs

  - Erroneous values

  - Values (data) to be Collected

    - Figure C- describes the ANSP to aircraft uplink path.  Time stamp points are shown in the triangles points.  Note time stamp points 2a and 2b time logs are maintained by Iridium satellite and are provided to the respective data link service provider, ARINC or SITA.  ARINC and SITA will provide a one-time report which contain samples of the Iridium Satellite time logs but will not do so on an on-going reporting basis.

    - The time from ANSP to data link processor, between points 3 and 4, shall be set to 1 to 2 seconds, as provided by the FAA.

Figure C- – Message uplink timing points

    - The values to be collected, analyzed and reported on to be used to gauge the ability of the Iridium Satellite system to serve as a sub-network to the FANS network shall be:

- Uplink message time and the resulting message delivery acknowledgement time, where,

  - Message uplink times shall be recorded at the data link central processor (point 3).

  - Message delivery acknowledgement times shall be recorded at the data link central processor (point 3).

Note:  Message delivery acknowledgement  is the “positive technical acknowledgement” message specified in ARINC 618.

- Iridium satellite network service outage notification times.  The outage notification time is the time from when the outage begins to when the outage notification is provided to the ANSP/AOC.

- Iridium satellite network service outage duration time.  The duration time is the time from when the outage begins to when restoration notification is provided to the ANSP/AOC.

- Aircraft registration number and the associated data link service provider.

    - In addition to the on-going reporting of uplink message timing, based on measurement of when the uplink message was sent and when the message acknowledgement was received by the ARINC/SITA processors, the Iridium Satellite time stamps at 2a and 2b, will be provided “one time,” where,

- Message uplink times shall be recorded at the data link central processor (point 3), Iridium Satellite receipt of message (point 2b) and Iridium Satellite message delivery (point 2a).

- Message delivery acknowledgement times shall be recorded at the Iridium Satellite receipt of message (point 2a), Iridium Satellite message delivery (point 2b), and at the data link central processor (point 3)

    - Points 2 a and 2b are Iridium Satellite time stamps as defined below:

| To-Aircraft | 2a – Receive msg from CSP | 2b – Transmit msg to aircraft |
| --- | --- | --- |
| From-Aircraft (Message acknowledgement | 2a – Transmit msg to CSP | 2b – Receive msg from aircraft |

    - Results shall be in chart format and raw format (CSV, comma separated values).

  - Data Resolution

    - All times shall be provided in date, hours, minutes and seconds.  Tenths of seconds is not a requirement for reporting purposes.

  - Collecting and Reporting Period

    - It is recommended that data be collected and recorded daily, however the analysis and reporting period shall be 30 days

  - Methodology for analyzing and presenting the data collected

    - Message delivery timing shall be reported for each time point, but shall be charted based on the total duration of all messages that were uplinked (starting at point 3) to the time the message acknowledgement was (or was not) received at point 3 by the data link service processor during the reporting period.

    - The total duration shall be charted in a cumulative distribution function chart showing the 95% and 99.9% CDF thresholds.

    - What type of charts besides cumulative distribution function?  I propose we develop a chart that includes list of outages and service losses, outage duration, affected area, cause, and outage indication delays, etc.