THE TWENTY-THIRD MEETING OF THE

INFORMAL PACIFIC ATC COORDINATING GROUP

(IPACG/23)

(Tokyo, Japan, 12-15 July 2005)

Agenda Item 2: Air Traffic Management (ATM) Issues

Implementation of Reduced Vertical Separation Minimum (RVSM) of 1,000 ft

Between FL290 and FL410 Inclusive, in the Domestic Airspace of Japan,

in Conjunction with the RVSM Implementation in the Republic of Korea

(Presented by the Civil Aviation Bureau, Japan)

SUMMARY

Japan has been planning to implement RVSM in the domestic airspace of the Tokyo and Naha FIRs, in conjunction with the RVSM implementation in the Incheon FIR, the Republic of Korea (ROK), on 29 September 2005.  This IP provides the latest information regarding progress made at the 26th Meeting of the ICAO RVSM Implementation Task Force held in Tokyo, 4-8 July 2005.

1.	26th Meeting of the ICAO RVSM Implementation Task Force

1.1	Coordination has been conducted multilaterally through the ICAO RVSM Implementation Task Force, and the latest 26th meeting of the Task Force (RVSM/TF/26) was held in Tokyo from 4 to 8 July 2005.  This meeting was significant in making “Go/No-Go” decision, by reviewing the overall implementation process and ensuring that key activities were completed to facilitate the introduction of RVSM on 29 September 2005.  Three major areas which the RVSM/TF/26 reviewed and associated conclusions are summarized as below:

1.2	OPERATIONAL READINESS

1.2.1	Amendment to Japanese Civil Aeronautics Law

RVSM implementation in the Japanese domestic airspace required an amendment to the Japan Civil Aeronautics Law and associated regulations, to provide legislative foundations for JCAB to enforce various requirements for safety reasons.  The amendment to the Law passed the National Diet on 30 June 2005.

1.2.2	FLOS (Flight Level Orientation Scheme) in the domestic airspace within Tokyo and Naha FIRs

The single alternate FLOS will be used for domestic RVSM operations and non-standard levels will not be used.

1.2.3	ATC training

Japan and the ROK reported that simulations had been conducted to assess the impact of RVSM on the workload of controllers, and concluded that there would be no adverse impact on ATC.  JCAB will commence training for ATC, mainly at ACCs, in July and complete it by mid-September 2005.

1.2.4	ATC systems modifications

Flight Data Processing (FDP) and Radar Data Processing (RDP) systems require program modification to cater for ATC operational requirements.  Program changes are planned in mid-September and on the implementation date.

1.2.5	AIP

JCAB will amend the existing AIP relating to RVSM operations (ENR3.6 10-Implementation of RVSM in Tokyo FIR and Naha FIR) to cover the domestic RVSM operations.  The AIP Amendment will be published on 4 August 2005, to provide operators with 2 AIRAC cycles prior to the implementation on 29 September 2005.  This amendment will incorporate the Large Height Deviation (LHD) report procedures contained in the existing AIC (Nr. 007/05).  As a result, the AIC will be cancelled on 29 September 2005.

ROK published the AIP Supplement containing RVSM policy and procedures within the Incheon FIR on 1 July 2005.  Due to several items which require clarification, ROK agreed to review the contents and issue the AIP Amendment as soon as possible.

1.2.6	Wake turbulence and lateral offsets

Strategic lateral offset of 0, 1, 2 NM to the right will be applicable in the oceanic airspace, but not in the domestic airspace which is fully covered by radar.  In situations when pilots has to deviate from the center line of routes while under the radar control in order to mitigate wake turbulence, such deviations will be accommodated by ATC upon request as far as traffic permitted.

1.2.7	Non-compliant operations

All operators and aircraft planning to operate in the RVSM airspace must obtain RVSM approval.  Non-compliant aircraft will not be allowed to operate in RVSM airspace, except for special cases such as State aircraft, search and rescue, humanitarian, ferry flight and etc.  The policy relating to non-compliant operations will be promulgated in AIP.

1.2.8	Suspension of application of RVSM

Procedures for suspension of the use of the 1,000 ft vertical separation minimum will be in place for application by the respective ACCs.  RVSM/TF/26 noted that the term “Suspension of RVSM Operations” should not be used as the ICAO Manual on RVSM Doc 9574 (Paragraph 5.2.8 b) clearly stated that the appropriate ATC authority should consider temporarily suspending the use of 300m (1,000 ft) VSM in the affected area.  Therefore, the meeting reminded States to use the correct term to describe situations when the application of the 1,000 ft vertical separation minimum had to be temporarily suspended.

The meeting also noted that a requirement for procedures to suspend RVSM would be subject to the characteristic of the airspace and could vary from one region (or FIR or portion of airspace) to another region (or FIR or portion of airspace).  Therefore it was agreed that general procedures for suspension of RVSM operations should be reviewed at future meetings of RVSM/TF.

1.2.9	Large height deviation (LHD) reports

Japan and ROK will continue to collect LHD reports through existing systems and provide monthly reports to MAAR (Monitoring Agency for Asia Region), as part of safety oversight for the use of RVSM.

1.2.10	Switchover arrangements

Japan and the ROK agreed to switchover from CVSM to RVSM at 1900 UTC on 29 September 2005.　IATA and IFALPA confirmed that the agreed time was acceptable.

1.2.11	Flight planning

It is considered essential for operators (domestic and international) to have a thorough understanding of the procedures relating to RVSM operations in Naha, Tokyo and Incheon FIRs.  In particular, the flight planning requirements and arrangements for the switchover from CVSM to RVSM at 1900 UTC on 29 September 2005 should be highlighted.  In this regard, Japan and the ROK were requested to provide appropriate briefing to all operators who might operate in their airspaces.

1.2.12	Traffic management during the transition

Certain procedures (e.g. time and location of altitude changes, radio communication failure) should be agreed with adjacent ACCs for the switchover from CVSM to RVSM on 29 September 2005.  Particular attention should be given to the use of specific levels, i.e. FL310, FL350, FL390, since these levels would be used for east bound traffic in the RVSM environment but for west bound traffic in the CVSM environment.  Japan and the ROK will coordinate and implement appropriate procedures/program to manage traffic during the switchover from CVSM to RVSM on 29 September 2005.

1.2.13	Trigger NOTAM

Japan and the ROK will issue the Trigger NOTAM on 22 September 2005 in accordance with the ICAO procedure in AIS Manual (Doc 8126).  The text of the NOTAM would be as follows:

E)	TRIGGER NOTAM – PERM AIRAC AIP (AMDT/SUP reference number) EFFECTIVE 1900 UTC 29 SEP 2005 RVSM WILL BE IMPLEMENTED IN (FIR name(s)) FIR(s)

1.2.14	Letters of Agreement (LOA)

Amendments to LOAs between Incheon and Naha/Fukuoka/Tokyo ACCs will be finalized by the end of July 2005.  The ROK has no other LOAs to be amended.  Japan will finalize amendments to LOAs with other adjacent FIRs by mid-August 2005.

1.3	OPERATOR READINESS AND RVSM APPROVAL STATUS

1.3.1	RVSM/TF/26 reviewed the readiness of aircraft and operators for RVSM operations on domestic and international routes in Naha, Tokyo and Incheon FIRs.  Approximately 76.5% of aircraft being operated in the domestic airspace of Japan are RVSM-approved.  Japan expects this figure to exceed 90% in August 2005, as other operators are in the process of obtaining RVSM approval.  For Korean national carriers (i.e. Korean Air and Asiana Airlines), 100% has already obtained RVSM approval.  Hence, the target of 90% operator approval for the Japan and ROK RVSM implementation will be achieved.

1.3.2	It should be noted that most general aviation business jet that operated in Tokyo, Naha and Incheon FIRs are RVSM compliant.

1.4	SAFETY ASSESSMENT AND MONITORING

1.4.1	Review of LHD occurrences

RVSM/TF/26 reviewed the LHD occurrences in Japan and ROK airspace since July 2004 as shown the Table 1.

| Month-Year | No. of LHD Occurrences | LHD Duration (Min) | Cumulative No. of LHD Occurrences | Cumulative LHD Duration (Min) | Remarks |
| --- | --- | --- | --- | --- | --- |
| 2004 |  |  |  |  |  |
| Jul | - |  | 1 | 0.2 | 1 LHD occurrence in April 04 reported by ROK |
| Aug | 3 | 1.5 | 4 | 1.7 |  |
| Sep | 2 | 2.7 | 6 | 4.4 |  |
| Oct | - |  | 6 | 4.4 |  |
| Nov | 1 | 0.3 | 7 | 4.7 |  |
| Dec | - |  | 7 | 4.7 |  |
| 2005 |  |  |  |  |  |
| Jan | - |  | 7 | 4.7 |  |
| Feb | - |  | 7 | 4.7 |  |
| Mar | - |  | 7 | 4.7 |  |
| Apr | - |  | 7 | 4.7 |  |
| May | - |  | 7 | 4.7 |  |
| Jun | 1* | (40) | 7 | 4.7 |  |

Table 1: Summary of LHD Occurrences and Duration in Japan and ROK Airspace

There were seven LHD occurrences, accounted for the duration of 4.7 minutes up to May 2005.  Of these occurrences, one was associated with technical error, and incorporated to the technical risk estimation.  The rest of the occurrences were associated with operational errors, in which were subject to TCAS advisory, error in ATC-unit-to ATC-unit transferred/transition message, and other causes.  *Additionally, in June 2005, there was one LHD occurrence reported by Japan due to incorrect operation associated with the aircraft altimeter system and which accounted for approximately 40 minutes.  Such case would not happen in the RVSM environment since the aircraft must operated under the two independent altimetry systems with the difference being within 200 feet.

1.4.2	Review of the Risk Assessment

RVSM/TF/26 noted that risk calculation for the Japan and ROK RVSM implementation would exceed the agreed overall TLS.  This was due to the LHD that had occurred in Japan in June 2005.  The meeting also discussed the exact cause of the incident, and established that it was an isolated case of an operational error.  The meeting was advised by Japan that positive counter measures had been put in place to prevent the recurrence of such an incident.

In light of the preventive actions taken by Japan and the fact that it was an isolated case, the meeting agreed that this LHD occurrence could be excluded in the risk calculation.  As a result, both technical and total risks were as shown in Table 2.

| Source of Risk | Lower Bound Risk Estimation | TLS | Remarks |
| --- | --- | --- | --- |
| Technical Risk | 1.40 x 10-9 | 2.5 x 10-9 | Below Technical TLS |
| Operational Risk | 2.43 x 10-9 | - | - |
| Total Risk | 3.83 x 10-9 | 5.0 x 10-9 | Below Overall TLS |

Table 2: Risk Estimates for the RVSM Implementation in Japan/ROK Domestic Airspace

These estimates satisfied the agreed TLS value of no more than 2.5 x 10-9 and 5.0 x 10-9 fatal accidents per flight hour due to the loss of a correctly established vertical separation standard of 1,000 ft and to all causes, respectively.  In addition, trends of collision risk estimates for each month using the appropriate 12-month interval of LHD reports since April 2004 are provided in Figure 1.

Figure 1: Trends of Risk Estimates for the RVSM Implementation in

Japan/ROK Domestic Airspace

### 1.4.3	Pre-Implementation Safety Assessment for the Japanese Domestic Airspace

### 1.4.3.1	Preliminary Assessment and Route Modification

### Japan had completed pre-implementation safety assessment for the Japanese domestic airspace, based on traffic sample data (TSD) for a period between January 2003 and December 2003.  Since the preliminary assessment report in March 2004 showed that the passing frequencies of some segments of ATS route G581 exceeded the criteria of the Global System Performance Specification, JCAB modified the route structure of G581 on 17 February 2005. As a result, the passing frequency on G581 decreased to at least 40% compared with the figure before the route restructure.

### 1.4.3.2	Pre-Implementation Assessment and LHD

### A pre-implementation safety assessment was conducted, covering from 8 July 2004 to 30 June 2005, and assessed the technical risk and operational risk.  Table 3 presents the summary of the LHD reports received during the period.

| Month-Year | No. of LHD Occurrences | LHD Duration (Min) | Cumulative No. of LHD Occurrences | Cumulative LHD Duration (Min) |
| --- | --- | --- | --- | --- |
| 2004 |  |  |  |  |
| July | 0 | 0 | 0 | 0 |
| Aug | 3 (2 by TCAS/ 1 by TRF error) | 1.5 | 3 | 1.5 |
| Sep | 2 (1 by Technical error/ 1 by TRF error) | 2.7 | 5 | 4.2 |
| Oct | 0 | 0 | 5 | 4.2 |
| Nov | 1(overshoot) | 0.3 | 6 | 4.5 |
| Dec | 0 | 0 | 6 | 4.5 |
| 2005 |  |  |  |  |
| Jan | 0 | 0 | 6 | 4.5 |
| Feb | 0 | 0 | 6 | 4.5 |
| Mar | 0 | 0 | 6 | 4.5 |
| Apr | 0 | 0 | 6 | 4.5 |
| May | 0 | 0 | 6 | 4.5 |
| June | 1* | (40) | 7 | 4.5 |

Table 3: Summary of LHD reports received from 8 July 2004 to 30 June 2005

Table 4 provides estimates of technical risk, operational risk and overall risk, calculated for Japanese domestic airspace.

| Source of Risk | Lower Bound Risk Estimation [accidents / flight hour] | TLS [accidents / flight hour] | Remarks |
| --- | --- | --- | --- |
| Technical Risk | 1.5×10-9 | 2.5×10-9 | Below Technical TLS |
| Operational Risk | 2.6×10-9 | - | - |
| Overall Risk | 4.1×10-9 | 5.0×10-9 | Below Overall TLS |

Table 4: Risk Estimates for the RVSM Implementation in the Japan domestic airspace

The results of the safety assessment met the requirements, and JCAB concluded that RVSM in the Japan domestic airspace could be safely implemented on 29 September 2005.

1.4.4	Review of the Monitoring Requirements

MAAR presented information to update the meeting on the Asia RVSM Minimum Monitoring Requirements (MMR) which had been adopted by MAAR from 1 July 2005.  The MMR was identical to the one currently used by Pacific Approval Registry and Monitoring Organization (PARMO).

1.4.5	Future Directions

Japan informed the meeting that for RVSM implementation in the domestic airspace, JCAB had established the Airspace Safety Monitoring Unit in the ATC Division of JCAB (JASMU) in April 2004.  With support from the Electric Navigation Research Institute (ENRI), JASMU will have full capability to conduct the safety assessments and monitoring for RVSM operations in Japan domestic airspace within one year after the implementation.

MAAR informed the meeting of its future direction to continue to provide the safety monitoring services until the 90-day review of the Japan and ROK RVSM implementation.  To enable MAAR to complete this task, new TSD would have to be provided for the month of November 2005.  The data should be submitted to MAAR no later than 15 December 2005.  This would allow MAAR adequate time to conduct the safety assessment for the post RVSM implementation meeting tentatively scheduled in the first week of February 2006.

1.5.	GO/NO-GO DECISION

1.5.1	Based on the update provided by Japan and the ROK, as well as the safety assessments completed by MAAR, the meeting agreed to go ahead with the implementation of RVSM in the Incheon, Naha and Tokyo FIRs on 29 September 2005 (0400 local on 30 September 2005).

2.	Conclusion

2.1	Following the above decision made at RVSM/TF/26, JCAB will progress implementation process in coordination with the ROK and other authorities of adjacent FIRs, ICAO, aircraft operators, airspace users, in order to achieve the safe and smooth transition to RVSM from CVSM at 1900 UTC on 29 September 2005.  This harmonized implementation of RVSM in Tokyo, Naha and Incheon FIRs will provide more airspace capacity and seamless RVSM operations for international air traffic between North America and Japan/Korea/East Asia.

3.	Action by the meeting

3.1	The meeting is invited to note:

a)	ICAO RVSM/TF/26 agreed to go ahead with the implementation of RVSM in the domestic airspace of Tokyo and Naha FIRs and Incheon FIR;

b)	This implementation will take place at 1900 UTC on 29 September 2005 (0400 local on 30 September 2005).

---------------------------------------------