THE TWENTY-SECOND MEETING OF THE

INFORMAL PACIFIC ATC CO-ORDINATING GROUP

(IPACG/22)

(Los Angeles, USA, 25-28 January 2005)

Agenda Item 2:	Air Traffic Management (ATM) Issues

Progress of 30/30 NM Lateral/Longitudinal Separation in the Tasman Sea

(Presented by the Federal Aviation Administration)

SUMMARY

This paper provides an overview of the progress made by New Zealand, Australia, Fiji and others toward implementation of 30/30 NM lateral and longitudinal separation beginning in the Tasman Sea on 20 Jan 2005.

1.		Background

1.1	The South Pacific ATS providers from Australia, New Zealand and Fiji, along with pilots, navigators, regulators, air traffic controllers, airline representatives, the International Federal of Air Line Pilots Associations (IFALPA) and the International Air Transport Association (IATA) members are implementing 30 NM lateral and 30 NM longitudinal separation (30/30) on 20 January 2005.  They have worked hard toward this goal and have learned some lessons along the way that they are willing to share as other ATS providers plan to implement reduced separation minima throughout oceanic airspace safely and efficiently.

1.2	The following is a succinct summary of the experiences that the South Pacific ATS providers, airspace users and others had implementing 30/30 in the airspace across the Tasman Sea.

2.	Discussion

2.1	The Informal South Pacific ATS Coordination Group (ISPACG) established a 30/30 Work Group (30/30/WG) to manage this implementation.  The 30/30/WG felt that the overwhelming lesson to be learned from the implementation was that they underestimated the effort required to complete the task.  The initial meeting underrated the implications that flowed from the ICAO Doc 7030 and ICAO PANS/ATM Doc 4444 requirements.

2.2	One of the most important lessons was the understanding of what they needed to accomplish relative to the frequencies of observed or estimated separations between successive aircraft at the same level [Doc 7030, para 6.2.2.5, "The 4% rule"].  The assembling of the data and the calculation of the value should have been completed earlier.

2.3	The recalculation of the target level of safety was left until late in the project.  This should have been done earlier due to the level of effort required to assemble the data and obtain the mathematical resource to do the calculation.

2.4	One of the prime activities was the generation of the Hazard Register with its Hazard Log, mitigation activities, residual risk levels and safety requirements.  This activity was begun early enough and was the backbone for the safety assessment processes.  It provided a road map for mitigation activities, prioritization activities and project actions.  The Safety Management System (SMS) requirements were based upon the Australian SMS and the ICAO Doc 4444 SMS requirements.  The project effectively followed this process.  A prime tenet of the process was the effective provision of supporting evidence for every safety decision.  The view of the 30/30/WG was that the safety assessment must be able to stand alone as an extant document.  It should contain within itself all the evidence and arguments to support the safety outcomes for commissioning and for any future readers.

2.5	A vital strategy that was adopted was to include the regulatory agencies and airline representatives in all discussions and meetings.  This saved many weeks of e-mails, dialogues, phone calls and clarification meetings.  They were at all the meetings, heard all the debates, participated in the outcomes and gained assurance in the integrity of the process.

2.6	One important aspect of the project that they managed well was the continual provision of status reports to all stakeholders.  By providing this level of information they found they experienced less managerial interference and fewer "please explain" questions.  This enabled them to effectively focus on the tasks and reduced the level of "political" management.

2.7	They attempted to run their approvals processes in parallel instead of serial approvals so that they could concatenate the project timeline.  This procedure worked effectively but required effective coordination by the Project team leaders to ensure all stakeholders were receiving up-to-date and accurate project information.

2.8	The management of the operational commissioning procedure related to the aeronautical information publications (AIP) and the national ATC manuals was not as effective as it should have been.  The 30/30/WG misunderstood the automated nature of the commissioning NOTAM actions that flowed from the AIP Supplement, and as a consequence there was some confusion when the commissioning date was delayed.  The Project Chairman did not fully appreciate the process and this was a valuable lesson.  The WG should have understood all the operational procedures related to the commissioning.

2.9	One of the strengths of this project was the use of a dynamic task list that was developed by everyone involved.  All 30/30/WG team members continually had input to this task list and actively coordinated the activities, due dates and responsibilities.  The task list was always the first item on the 30/30/WG meeting agenda.

2.10	The project worked due to the diligence and professionalism of the small team of multi-skilled members.  The team was comprised of pilots, navigators, regulators, air traffic controllers, airline representatives, IFALPA and IATA members.  The broad base of this team ensured that risks were effectively identified and solutions to problems efficiently managed.

3.	Recommendation

3.1	The meeting is invited to note the information in this paper.