THE TWENTY-SECOND MEETING OF THE

INFORMAL PACIFIC ATC CO-ORDINATING GROUP

(IPACG/22)

(Los Angeles, USA, 25-28 January 2005)

Agenda Item 2:	Air Traffic Management (ATM) Issues

30NM Lateral/30NM Longitudinal Separation Throughout the Pacific

(Presented by the Federal Aviation Administration)

SUMMARY

This paper introduces a plan to promote 30 NM lateral/30 NM longitudinal separation (30/30) throughout Pacific oceanic airspace, using lessons learned from the Tasman Sea implementation as well as methods used in other oceanic separation reduction efforts.  It provides a task list for the meeting to review and discuss as a possible template for a task list to implement 30/30 throughout the Pacific.

1.		Background

1.1	Building on the achievement obtained by Airservices Australia, Airways New Zealand and Strategic Air Services Limited Fiji in their implementation of 30 NM lateral/30 NM longitudinal separation minima (30/30) in the Tasman Sea, it is important to begin planning to implement this separation minima throughout Pacific Oceanic airspace.  Provisions for this separation reduction have already been included in the Regional Supplementary Procedures for the Oakland, Anchorage and Tokyo flight information regions (FIRs).  While it is not expected that significant airspace capacity enhancements will exist in the more sparsely flown South Pacific, that airspace has proven fruitful for testing new technologies and initiatives.  Starting with implementation in Oakland FIR South Pacific airspace by the end of 2005, the FAA hopes to learn more about implementation using FAA oceanic automation, then expand 30/30 NM trials into the Central and North Pacific airspace—and possibly into the Arctic region.

1.2	North Atlantic ATS providers have presented a plan to implement 30/30 separation minima in North Atlantic airspace around 2013.  The International Air Transport Association (IATA) has expressed a desire to achieve benefits from separation reductions in Atlantic oceanic airspace prior to that, so they can take better advantage of their investments in future technologies and gain better airspace efficiency and capacity.  The FAA hopes to be able to assist neighboring Atlantic oceanic ATS providers in implementing reduced horizontal separation earlier so that airspace users can achieve earlier benefits and ATS providers can better take advantage of new automation systems, avionics, and supporting procedures.

2.	Discussion

2.1 	While it is important to implement reduced horizontal separation minima in a safe and timely manner, it is also important that neighboring FIRs are committed to a harmonized implementation of reduced separation minima.

  - As was learned during the implementation of reduced vertical separation minimum (RVSM), such an international implementation can be very complex, requiring specific national and international implementation steps.

2.3	For 30/30 implementation in the Tasman, the work group used a task list that was very similar to the attached task list, then adapted it for their implementation in the Tasman.  Every meeting of the Tasman 30/30 work group began with a review and update of their task list.

2.3	In order to begin planning for 30/30 implementation in the Central and North Pacific  areas, it may be valuable to begin now to develop a task list that will present potential considerations and steps to be evaluated.  A task list for consideration by the meeting is presented at Attachment 1.

3.	Recommendation

3.1  	The meeting is invited to

a.	discuss plans for implementation of 30/30 throughout the Pacific oceanic FIRs and propose milestones for incremental implementation as appropriate, and

b.	review the proposed task list and determine if it would be useful for the proliferation of 30/30 throughout Pacific oceanic airspace.

30/30 Implementation Working Group

Task List

| ID | Task | Responsible Office | Start Date | Finish Date | Completion Date | Reference Source |
| --- | --- | --- | --- | --- | --- | --- |
| 1.0 | Identify Operational Needs |  |  |  |  |  |
| 1.1 | Draft operational concept |  |  |  | 1993 | ISPACG Fiji 1993 |
| 1.2 | Examine the operational factors and workload associated with implementation |  |  |  |  |  |
| 1.3 | Co-ordinate and update operational concept |  |  |  |  |  |
| 1.4 | Define 30/30 airspace |  |  |  |  |  |
| 1.5 | Define horizontal and vertical limits |  |  |  |  |  |
| 1.6 | Define ADS-C certification and approval process |  |  |  |  |  |
| 2.0 | Conduct Cost Benefit Analysis |  |  |  |  |  |
| 2.1 | Determine need for CBA |  |  |  |  |  |
| 2.2 | Complete CBA |  |  |  |  |  |
| 3.0 | Safety Assessment |  |  |  |  |  |
| 3.1 | Define data collection plan |  |  |  |  |  |
| 3.2 | Complete plan to collect data necessary to establish safety case |  |  |  |  |  |
| 3.3 | Collect gross navigational error reports |  |  |  |  |  |
| 3.4 | Collect weather and turbulence data in Oceanic FIRs in preparation for analysis |  |  |  |  |  |
| 3.5 | Collect safety analysis data |  |  |  |  |  |
| 3.6 | Update 30/30 risk model assumptions/parameters |  |  |  |  |  |
| 3.7 | Analyze data to verify collision risk model and target level of safety |  |  |  |  |  |
| 3.8 | Confirm that automation ground systems meet safety objective |  |  |  |  |  |
| 3.9 | Complete safety analysis |  |  |  |  |  |
| 3.10 | Develop plan for long-term monitoring and Problem Reports |  |  |  |  |  |
| 4.0 | Determination of Requirements (Airborne & Ground Systems) |  |  |  |  |  |
| 4.1 | Monitor and advise datalink performance issues |  |  |  |  |  |
| 4.2 | Determine RNP4 equipage |  |  |  |  |  |
| 4.3 | Implement automation equipment at Oceanic ACCs |  |  |  |  |  |
| 4.4 | Ensure separation tools meet needs |  |  |  |  |  |
| 4.5 | Assess workload and procedures |  |  |  |  |  |