## Sheet1
COMPOSITE MATERIAL FIRE FIGHTING
(RPD 140)
PROJECTS: |  | WORK TO CONTINUE IN 2015
[7 empty] | 2 | 0 | 1 | 3 | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5
|  |  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  | 2013 | 2014 | 2015 | TOTAL
1. Identifying Effective Extinguishing Agents
| Development of a Live Fire Test Protocol |  | 100 | 100 |  | 200 | X | X | X | X | X | X | X | Ä
2. Identifying Effective Extinguishing Methods
| Determining the Required Forces to Penetrate the Aircraft Skin |  |  |  |  | 0 | Ä
| Development of a Computer Model for Future Composite Designs |  | 100 |  |  | 100 | X | X | X | X | Ä
| Required Forces for Forcible Entry into Composite Aircraft |  | 50 | 50 | 50 | 150 | X | X | X | X | Ä |  |  |  | X | Ä
| Evaluate Extinguishing Systems Designed for Composite Fires |  |  | 100 | 250 | 350 | X | X | X | X | X | X | X | X | X | X | X | X
3.Determine Quantities of Agent Required
| Live Fire Testing of Composite Materials |  | 150 | 150 | 250 | 550 | X | X | X | X | X | X | X | X | X | X | X | X
4.Identify Hazards Associated with Airborne Fibers
| Analyze air quality samples from forcible entry testing |  |  |  | 50 | 50 | [8 empty] | X | Ä
| Analyze air quality samples from live fire testing |  | 100 | 100 | 150 | 350 | X | X | X | X | X | X | Ä
| Total Contract Funds |  | 500 | 500 | 750 | 1750
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK