## Sheet1
Data Mining
(RPD 141)
PROJECTS:
[6 empty] | 2 | 0 | 1 | 3 | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5
|  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 2013 | 2014 | 2015 | TOTAL
Data Characterization |  |  |  | 250 |  | X | X | X | X | X | X | X | X | X | X | X | X
Database Maintenance |  |  |  | 100 |  | X | X | X | X | X | X | X | X | X | X | X | X
Perform Data Analysis |  |  |  | 100 |  |  | X | X |  |  | X | X |  |  | X | X
Mitigation Plan(s) for Top Risks |  |  |  | 50 |  |  |  | X |  |  |  | X |  |  |  | X
Total Contract Funds |  | 0 | 0 | 500 | 500
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK