## Sheet1
Problematic Geometry
(RPD 142)
PROJECTS:
[6 empty] | 2 | 0 | 1 | 3 | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5
|  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 2013 | 2014 | 2015 | TOTAL
Estimated Construction Unit Costs | [8 empty] | X | X | X
Conduct Inventory | [8 empty] | X | X | X
Prioritization |  |  |  | 500 | [6 empty] | X | X | X | X | X
Improvement Plan |  |  |  | 500 | [11 empty] | X | X
Total Contract Funds |  | 0 | 0 | 1000 | 1000
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK