## Sheet1
AIRCRAFT BRAKING FRICTION (RPD 147)
PROJECTS: |  | WORK TO CONTINUE IN 2016
[7 empty] | 2 | 0 | 1 | 3 | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5
|  |  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  | 2013 | 2014 | 2015 | TOTAL
1. Braking Research Aircraft Work
| Procure Storage Facility |  | 50 |  |  | 50 | X | X
| Aircraft Maintenance/Repair |  | 325 | 275 | 175 | 775 | X | X | X | Ä | X | X | X | Ä | X | X | X | Ä
| Nose Gear Brake Modifications |  | 25 |  |  | 25 | X | X | X | Ä
| Instrumentation of Nose Gear and Data Acquisition System |  | 75 |  |  | 75 | X | Ä
| Upgrades to Wheel Load Scales |  | 50 | 75 |  | 125 |  |  | X | X | X | Ä
| Installation of New Nose Gear Brakes |  | 25 |  |  | 25 |  |  | Ä
| Manufactured Snow for Testing |  | 50 |  |  | 50 | X | X | X | Ä | X | Ä
| Mu-Slip Testing with Nose Gear Brakes |  | 150 |  |  | 150 | X | X | X | Ä | X | Ä
| Analysis and Report on Nose Gear Testing |  | 125 |  |  | 125 |  |  |  |  | X | X
| Procurement/Installation of New Main Gear Brakes |  | 150 |  |  | 150 |  |  | X | Ä
| Instrumentation of Main Gear and Data Acquisition System |  | 250 |  |  | 250 | X | X | X | Ä | X | Ä
| Mu-Slip Testing with Main Gear Brakes, Phase 1 |  | 300 | 175 |  | 475 |  |  | X | X | X | Ä
| Analysis and Report on Phase 1 Main Gear Testing |  |  | 150 |  | 150 |  |  |  |  | X | X
| Mu-Slip Testing with Main Gear Brakes, Phase 2 |  |  | 175 | 75 | 250 |  |  |  |  | X | X | X | Ä | X | Ä
| Analysis and Report on Phase 2 Main Gear Testing |  |  | 150 | 50 | 200 | [6 empty] | X | X | X | X
| Aircraft Radio and Intercom System |  | 50 |  |  | 50 |  |  | X
2. Pavement Load Test Vehicle Braking Friction Testing
| Design for Incorporating Aircraft Brake into Single Wheel Module |  | 25 |  |  | 25 |  |  | X | X
| Procurement and Installation of Aircraft Brake System |  |  | 75 |  | 75 |  |  |  | X | X
| Instrumentation of Single Wheel Module |  |  | 50 |  | 50 |  |  |  | X | X
| Braking Friction Testing in NAPTF |  |  | 50 |  | 50 |  |  |  |  | X | X | X | Ä
3. Anti-Skid Brake System Simulation Lab
| Simulation Lab Design |  | 25 | 50 |  | 75 |  |  |  | X | X | X
| Simulation Lab Procurement/Assembly |  | 25 | 50 |  | 75 |  |  |  | X | X | X
| Simulation Lab Testing and Analysis |  | 200 | 150 |  | 350 | X | X | X | Ä | X | X | X | Ä
| Development of ASBS Controller |  | 150 | 150 | 50 | 350 | X | X | X | Ä | X | X | X | Ä | X | X | X | Ä
| Integrate ASBS Controller into Aircraft |  |  |  | 75 | 75 | [8 empty] | X | X | X | Ä
4. Flight Simulator Work
| Simulator Development |  | 150 | 125 |  | 275 |  |  | X | Ä | X | X | X | Ä
| Simulator Runs |  |  | 100 | 30 | 130 |  |  |  |  | X | X | X | Ä | X | X | X | Ä
| Simulator Run Analysis |  |  | 100 | 45 | 145 |  |  |  |  | X | X | X | Ä | X | X | X | Ä
| Total Contract Funds |  | 2200 | 1900 | 500 | 4600
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK