## Schedule
Visual Guidance - RPD 151
PROJECTS: | Funds ($k) |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015
| 2013 | 2014 | 2015 | TOTAL | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Lighting | 1800 | 1500 | 1900 | 5200
General Aviation |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X
New Technology |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X
Airfield Lighting Infrastructure |  |  |  |  | X | X | Ä | X
Standards for Internally Lighted Wind cone |  |  |  |  | X
Linear Light Sources |  |  |  |  | X | X | X | X | X | X | Ä | X
Crash-Test Performance of Frangible Connections |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | Ä
Signs | 200 | 300 | 0 | 500
Approach Hold/Runway Safety Area signs/markings |  |  |  |  | X | X | X | X | X | Ä | X
EMAS sign/lighting |  |  |  |  | X | Ä | X
Markings | 200 | 100 | 0 | 300
Structured Methylmethacrylate (MMA) Marking | [7 empty] | X | X | X | X | Ä
Vertical Flight | 500 | 500 | 500 | 1500
Heliport Flood Lighting |  |  |  |  | X | X | X
Heliport Light Canister and Installation Critera | [5 empty] | X | X | X | X | X | Ä
Heliport Touchdown Position Marking | [6 empty] | X | X | X | X | X | X
Total Contract Funds | 2700 | 2400 | 2400 | 7500
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK