## Sheet1
IMPROVED RESCUE & FIRE FIGHTING EQUIPMENT and AGENTS | [6 empty] | (RPD 152)
PROJECTS: |  | WORK TO CONTINUE IN 2015
[7 empty] | 2 | 0 | 1 | 3 | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5
|  |  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  | 2013 | 2014 | 2015 | TOTAL
1. Alternative Fire Fighting Agents
| Testing of new alternative agents |  | 50 | 50 | 50 | 150 | X | X | X | X | X | X | X | X | X | X | X | X
2. Maintenance & Upgrades of Test Facilities and Vehicles
| L1011 Test Bed |  |  | 50 |  | 50 |  |  |  |  | X | X | Ä
| Burn Pad Concrete Expansion |  |  |  |  | 0 | Ä
| 311A Conversion to an Interior Fire Test Chamber |  | 30 | 0 | 50 | 80 | X | X | X | X |  |  |  |  | X | X | Ä
| Retrofit of current dual nozzle HRET to single nozzle |  | 50 |  |  | 50 | Ä
3.Crash Simulation for Predicting Fuel Release
| Phase I - Modelling of Constellation Test |  |  |  |  | 0
| Phase II - Modelling of A380 |  |  |  |  | 0 | X
| Phase III - Modelling of Additional Aircraft |  | 100 |  |  | 100 | X | X | X | X | X | Ä
4.New Fire Fighting System Minimum Perf. Baseline
| Develop Test Protocol for Baselining Technologies |  | 50 |  |  | 50 | X
| Live Fire Validation of Test Protocol for Baselining Technologies |  | 150 | 150 | 150 | 450 | X | X | X | X | X | X | X | X | X | Ä
5.Cargo Aircraft Interior Fire Fighting
| Development of Project and Test Plans |  |  |  |  | 0
| Testing of Cargo Bay Lining Materials |  |  |  |  | 0 | X | X | X | Ä
| Full-Scale Live Fire Testing Of Cargo Aircraft |  | 100 | 100 | 100 | 300 | X | X | X | Ä | X | X | X | X | X | X | X | X
6. Bio-Fuel Fire Fighting Research
| Literature Review |  | 20 |  |  | 20 | X
| Small-Scale Fire Tests |  | 150 | 150 | 50 | 350 |  | X | X | X | X | X | X | X | X | X | X | X
| Full-Scale Fire Tests |  |  |  | 150 | 150 | [8 empty] | X | X | X | X
7. Full-Scale Fire Testing of New ARFF Technologies
| Full-Scale Fire Tests |  |  | 200 | 250 | 450 | [5 empty] | X | X | X | X | X | X | X
| Total Contract Funds |  | 700 | 700 | 800 | 2200
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK