## Sheet1
AIRPORT TECHNOLOGY RESEARCH TAXIWAY
(RPD 153)
PROJECTS: |  | WORK TO CONTINUE IN 2015
[7 empty] | 2 | 0 | 1 | 3 | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5
|  |  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | 1 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  | 2013 | 2014 | 2015 | TOTAL
2. Research Runway Construction
| Runway Construction - General Items |  | 400 | 1000 |  | 1400 |  |  | X | X | X | X | X
| Runway Construction - Electrical Items |  | 222 | 230 |  | 452 |  |  |  | X | X | X | X | X
| Runway Construction - Pavement Items |  |  | 300 |  | 300 |  |  |  |  | X | X | X | X
| Construction Package Completion |  |  |  |  | 0 | [5 empty] | X | X | X
2. LED Electrical Architecture Testing
| Circuit Installation and Optimization |  |  |  | 1000 | 1000 | [8 empty] | X | X | X | X
| Check out equipment and beta testing |  |  |  | 300 | 300 | [8 empty] | X | X | X | Ä
| Pavement Testing Items |  |  |  | 200 | 200 | [8 empty] | X | X | X | Ä
| Total Contract Funds |  | 622 | 1530 | 1500 | 3652
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK