## Sheet1
INNOVATIVE AIRPORT SENSOR TECHNOLOGIES
(RPD 154)
PROJECTS: |  | WORK TO CONTINUE IN 2015
[7 empty] | 2 | 0 | 1 | 3 | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5
|  |  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  | 2013 | 2014 | 2015 | TOTAL
1. Low Cost Surface Surveillance Framework
| Phase 1 Procurement/Deployment of Pilot System at Site #1 |  |  |  |  | 0
| Testing of Baseline System |  | 700 |  |  | 700 |  | X | X | X
| Analysis and Report on Phase 1 Testing |  | 300 |  |  | 300 |  |  | X | X
| Phase 2 Procurement/Deployment of Pilot System at Site #2 |  |  | 800 |  | 800 |  |  |  |  | X | X | X | X
| Testing of System at Site #2 |  |  | 540 |  | 540 | [5 empty] | X | X | X
| Analysis and Report on Phase 2 Testing |  |  | 140 | 250 | 390 | [6 empty] | X | X | X | X
| Phase 3 Procurement/Deployment of Pilot System at Site #3 |  |  |  | 800 | 800 | [8 empty] | X | X | X | X
| Testing of System at Site #3 |  |  |  | 140 | 140 | [9 empty] | X | X | Ä
| Analysis and Report on Phase 3 Testing |  |  |  |  | 0
| Conduct Cost Benefits Analysis |  |  |  |  | 0
| Deliver Technical Report |  |  |  |  | 0
2. Vehicle ADS-B Evaluation
| Procure UAT Vehicle Units |  |  |  |  | 0
| Phase 1 Demonstrate Initial Operational Capability |  |  |  |  | 0
| Phase 2 Demonstrate Certified UAT and AEROMACS Capability |  |  |  |  | 0
| Phase 3 Data Collection |  |  |  |  | 0
| Deliver Technical Report |  |  |  |  | 0
3. Sensor Performance Assessment Support (Ongoing)
| Literature Review (Cameras, Radars, Acoustic, RFID, Nano….) |  |  | 25 | 25 | 50 | [5 empty] | X | X | Ä | X | X | X | Ä
| Proof Of Concept Demonstration |  |  | 25 | 25 | 50 | [5 empty] | X | X | Ä | X | X | X | Ä
| Deliver White Paper |  |  | 10 | 10 | 20 | [8 empty] | X | X | X | Ä
| Deployment Support |  |  |  | 0 | 0 | [8 empty] | X | X | X | Ä
| Total Contract Funds |  | 1000 | 1540 | 1250 | 3790
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK