## Sheet1
Heated Pavements
(RPD 155)
PROJECTS:
[6 empty] | 2 | 0 | 1 | 3 | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5
|  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 2013 | 2014 | 2015 | TOTAL
1. Geothermal Demonstration Project (Binghamton Airport)
| Concrete Pavement with Hydronic Piping |  |  |  | 0 | Ä
| Geothermal Wells & Mechanical Equipment |  |  |  | 0 |  |  |  | X | Ä
| Data Collection and Analysis | [9 empty] | X | Ä
2. Heated Pavement Research
| Airport Heated Pavement Study | 400 | 400 | [5 empty] | X | X | X | X | X | X | Ä
| Advanced Materials Research | 300 | 300 |  | 600 |  |  |  | X | X | X | X | X | X | X | Ä
| Advanced Construction Techniques | 300 | 300 | [5 empty] | X | X | X | X | X | X | X | Ä
| Heated Pavement Test Sections |  |  | 500 | [11 empty] | X | X
| Total Contract Funds | 1000 | 1000 | 500
Ä REPRESENTS FY QUARTER FOR DELIVERABLE COMPLETION