## Sheet1
AIRPORT PLANNING
(RPD 132)
PROJECTS: |  | WORK TO CONTINUE IN 2015
[7 empty] | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  |  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  | 2014 | 2015 | 2016 | TOTAL
1. Airport & Airspace Simulation Model Enhancements |  |  | 10 | 10 | 10 | 30 | X | X | X | X | X | X | X | X | X | X | X | X
| Graphical Interface for Executing & Animation | [9 empty] | X | X | X | X | X | X | X | X
Building Airspace Routes with Network Interfaces (completed 2010)
| Manuals | [5 empty] | X | X | X | X | X | X | X | X | X | X | X | X
| Utility Programs | [5 empty] | X | X |  |  | X | X | X | X | X | X | X | X
2. Building Airport Database |  |  | 180 | 180 | 180 | 540 | X | X | X | X | X | X | X | X | X | X | X | X
| Completed 7 - "Core 30" airfileds (JFK, SFO, LAX, OAK, ORD, DFW, FLL) | [5 empty] | X | X | Ä
| Completed "Core 30" airfileds | [9 empty] | X | X | X | X | X | X | X | X
| Completed 2 - Non "Core 30" airfields (TEB, ANC) | [5 empty] | X | X | Ä
| Completed Non "Core 30" airfields | [9 empty] | X | X | X | X | X | X | X | X
3. Improve Digitization of Airports |  |  | 100 | 100 | 100 | 300 | X | X | X | X | X | X | X | X | X | X | X | X
| Received ASDE-X data for three airports | [5 empty] | X | X | X
| Received ADACEL data for two airports | [5 empty] | X | X
4. Develop Processes to Incorporate use of PDARS Data |  |  | 120 | 120 | 150 | 390 | X | X | X | X | X | X | X | X | X | X | X | X
5. Build Airport Latitude & Longitude |  |  | 90 | 90 | 110 | 290 | X | X | X | X | X | X | X | X | X | X | X | X
| Received ADACEL data for two airports | [5 empty] | X | X
| Total Contract Funds |  | 500 | 500 | 550 | 1550
X - REPRESENTS FY QUARTER FOR DELIVERABLE
X - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK