## Sheet1
IMPROVED PAVING MATERIALS
(RPD 136)
PROJECTS:
[6 empty] | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  | Funds | ($K) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 2014 | 2015 | 2016 | TOTAL
1. Materials Testing Lab
| Testing Support for Projects / Labor | 365 | 350 | 375 | 715 | X | X | X | X | X | X | X | X | X | X | X | X
| Equipment and supplies | 85 | 75 | 85 | 160 | X | X | X | X | X | X | X | X | X | X | X | X
| Equipment Maintenance & Calibration | 50 | 50 | 50 | 100 |  |  | X | X |  |  | X | X |  |  | X | X
| Lab Certifications | 25 | 30 | 30 | 55 | X | Ä | X | Ä | X | Ä | X | Ä | X | Ä | X | Ä
2.ASR Affected Concrete Slabs
| Application of De-icer and Monitoring | 5 | 5 |  | 10 | X | X | X | X | X | X | X | X
| Petrographic Analysis / Specialized Testing | 10 | 10 |  | 20 |  |  | X | Ä |  |  | X | Ä
| Reports/ Documentation | 5 | 5 |  | 10 |  |  |  | Ä |  |  |  | Ä
3. Ashaplt Mix Design for Gyratory Compactor
| Documentation/Reports | 25 | 25 |  | 50 |  |  | X | Ä | X | Ä
| Testing and Analysis |  | 50 | [6 empty] | X | Ä
4. Reflective Cracking Tests
| Remove/Replace Asphalt | 60 | 60 | 60 | 120 | X |  | Ä |  |  | X |  | Ä |  | X |  | Ä
5. Evaluate Alternative HMA Mixes
| Test Pavement Construction |  | 100 | 110 | 100 | [7 empty] | X | X | X | Ä
| Material Testing and Documentation |  | 40 | 40 | 40 | [7 empty] | X | X | Ä
6. Effects of Subbase Quality for Flexible Pavements
| Analysis of Post Traffic Investigation | 20 |  |  |  |  | X
| Draft Report Preparation | 10 |  |  |  |  | X | X | X
| Final Report | 10 | [5 empty] | X | Ä
7. Testing Supprt ERDC IA
| Mix Design For Gyratory Compactor | 125 |  |  |  | X | X | X | X |  |  |  |  | X | X | Ä | X
| Geosynthetics | 50 | 75 | 150 |  | X | X | X | Ä | X | X | X | Ä | X | X | X | Ä
9.Pavement Construction
| CC7 Construction | 600 |  |  |  | X | X | X | Ä | X | Ä
| CC6 Demolition | 150 |  |  |  | X | X | X | Ä
| CC8 Construction | 75 | 725 | 250 |  |  |  |  | X | X | X | Ä |  | X | Ä
| CC7 Demolition |  |  | 200 | [11 empty] | X | X
| CC8 Demolition |  |  | 300 | [12 empty] | X
10. "Green" Sustainable Pavement Technologies
| Literature Review | 50 | [6 empty] | X | X | Ä
| Testing of Sustainable Pavement Materials |  | 100 | 100 | [6 empty] | X | X | Ä | X | X | X
| Total Contract Funds | 1700 | 1700 | 1750
Ä | - REPRESENTS FY QUARTER FOR DELIVERABLE / COMPLETION