## Sheet2
ADVANCED AIRPORT PAVEMENT DESIGNS
(RPD 144)
PROJECTS:
[6 empty] | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 2014 | 2015 | 2016 | TOTAL
1. FAARFIELD Documentation and Support
| Software Maintenance and Support (continuing) | 75 | 75 | 25 | 175 | X | X | X | X | X | X | X | X | X | X | X | X
| Develop modifications to AC 150/5320-6E for FAARFIELD 1.4 | 50 |  |  |  | X | Ä
| Other software testing and documentation work | 0 | 50 | 0 | 50 | X | X | X | X | X | X | X | X | X | X | X | X
2.Workshops and Training
| Airport Pavement Workshops and Computer Laboratories | 0 | 25 | 25 | 50 | X | X | X | X | X | X | X | X | X | X | X | X
| Support for Technology Transfer Conference | 25 | 0 | 0 | 25 | X | X | Ä
3. FAARFIELD-Based PCN
| Implement PCN critical aircraft function in FAARFIELD | 50 | 50 | 50 | 150 | X | X | X | Ä
| Develop/test FAARFIELD PCN module |  |  | 200 | 200 |  |  |  |  | X | X | X | X | X | X | X | Ä
| Total Contract Funds | 200 | 200 | 300 | 700
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK