## Sheet2
PAVEMENT DESIGN AND EVALUATION METHODOLOGIES
(RPD 145)
PROJECTS:
[6 empty] | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 2014 | 2015 | 2016 | TOTAL
1. Doubling of Pavement Life to 40 Years
| Data Collection and Analysis at Medium/Large Hub Airports | 500 | 500 |  | 1000 | X | X | X | X | X | X | X | Ä
| Performance Model Development | 500 | 1500 | 1000 | 3000 | X | X | X | X | X | X | X | X | X | X | X | X
2.Overlay Design Procedure Development
| CC4 Analysis and Modeling (Penn State) | 150 |  |  | 150 | X | X | X | X | Ä
| Improve convergence of PCC-on-rigid overlay designs | 50 | 50 |  | 100 | X | X | X | X | X | Ä
| Develop Reflection Cracking Model | 50 | 200 | 500 | 750 |  |  | X | X | X | X | X | X | X | X | X | X
3. Slab Curling/Top-Down Cracking Failure Mode
| Field Data Analysis (continuing) | 50 | 50 | 50 | 150 | X | X | X | X | X | X | X | X | X | X | X | X
| FEAFAA Modifications to compute total slab stress | 100 |  |  | 100 | X | X | Ä
| Implement top-down proc. in FAARFIELD evaluation version | 200 |  |  | 200 | X | X | Ä
| CC8 Data Analysis |  | 200 | 200 | 400 |  |  |  |  | X | X | X | Ä
| Develop criteria for top-down stress in design |  | 100 | 250 | 350 |  |  | X | X | X | X | X | X | X | X | X | Ä
4. ACN/PCN Methodology
| Numerical simulation of CBR test for field collected materials | 250 | 125 |  | 375 | X | X | X | X | X | X | X | Ä
| Analysis of Case Studies |  | 125 | 250 | 375 |  |  |  |  | X | X | X | X | X | X | X | X
6. LCCA Integrated Design Procedure
| Develop framework for integration | 150 | 150 | 150 | 450 | X | X | X | X
| Modify HMA-on-flexible overlay design procedures for 40-yr life |  |  | 850 | 850 |  |  |  |  | X | X | X | X | X | X | X | X
| Total Contract Funds | 2000 | 3000 | 3250 | 8250
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK