## Sheet1
High Temperature Pavement Test Facility (HTPTF)
(RPD 135)
PROJECTS:
[6 empty] | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 2014 | 2015 | 2016 | TOTAL
1. Maintenance and Equipment |  | 100 | 50 | 100 |  | X | X | X | X | X | X | X | X | X | X | X | X
2. Set-up Database, Process and Analyze Data |  | 75 | 150 | 200 | 425 | X | X | X | X | X | X | X | X | X | X | X | X
3. Test Pavement Construction |  | 600 | 200 | 300 | 1100 | X | X | X | X | X | X | X | X | X | X | X | X
4. Data Acquisition System & Instrumentation |  | 150 | 50 | 200 | 400 | X | X | X | X | X | X | X | X | X | X | X | X
5. APTV Building |  |  |  |  | 0
| Building Construction | 175 | 0 | 0 | 175 | X | X | Ä
| APTV Testing | 0 | 0 | 0 |  | X | X | X | X | X | X | X | X | X | X | X | X
6. APTV Operation
| APTV Operation | 0 | 300 | 0 |  | X | X | X | X | X | X | X | X | X | X | X | X
| Total Contract Funds | 1100 | 750 | 800
Ä - REPRESENTS FY QUARTER FOR DELIVERABLE/COMPLETION