## Sheet1
AIRPORT DESIGN
(RPD 133)
PROJECTS: |  | Funds | ($k) |  |  | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  | 2014 | 2015 | 2016 | TOTAL | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1. Taxiway Deviation Studies
| DG3 Data Processing | 10 |  |  | 10 | X | X
| DG3 Analysis and Report of Data | 20 |  |  | 20 | X | X | Ä
| DG2 Test Plan Development | 20 |  |  | 20 | X
| DG2 System Installation | 100 |  |  | 100 | X | X
| DG2 System Maintenance | 75 | 40 |  | 115 | X | X | X | X | X | Ä
| DG2 Data Collection | 85 | 50 |  | 135 | X | X | X |  | X | X | Ä
| DG2 Data Processing | 50 | 50 |  | 100 | X | X | X | X | X | X | X | Ä
| DG2 Analysis and Report of Data | 20 | 30 | 10 | 60 | X | X | X | X | X | X | X | X | X | Ä
| DG1 Test Plan Development |  | 10 |  | 10 | [6 empty] | X | X
| DG1 System Installation |  | 95 | 95 | 190 | [6 empty] | X | X | X | Ä
| DG1 System Maintenance |  | 5 | 50 | 55 | [7 empty] | X | X | X | X | Ä
| DG1 Data Collection |  |  | 60 | 60 | [8 empty] | X | X | X | Ä
| DG1 Data Processing |  |  | 45 | 45 | [8 empty] | X | X | X | X
| DG1 Analysis and Report of Data |  |  | 20 | 20 | [10 empty] | X | X
2. Runway Width Study
| Runway Width Study - Proof of Concept | 100 |  |  | 100 |  | X | X | X
| Runway Width Study - Plan Development | 10 |  |  | 10 |  |  | X | X
| Runway Width Study - Installation at Test Site |  | 100 | 90 | 190 |  |  |  |  | X | X | X
| Runway Width Study - System Maintenance |  | 75 | 75 | 150 | [5 empty] | X | X | X | X | X
| Runway Width Study - Data Collection |  | 75 | 75 | 150 | [5 empty] | X | X | X | X | X
| Runway Width Study - Data Processing |  | 75 | 75 | 150 | [5 empty] | X | X | X | X | X | X | X
| Runway Width Study - Analysis and Report of Data |  |  | 10 | 0 | [11 empty] | X
3. FOD Detection
| FOD Database Construction | 25 | 25 | 25 | 75 | X | X | X | X | X | X | X | X | X | X | X | X
| FOD Database Maintenance | 10 | 10 | 10 | 30 | X | X | X | X | X | X | X | X | X | X | X | X
| FOD Characterization Study | 25 | 25 | 25 | 75 | X | X | X | X | X | X | X | X | X | X | X | X
| FOD Detection Technology Evaluation | 25 | 25 | 25 | 75 | X | X | X | X | X | X | X | X | X | X | X | X
4. Artificial Turf - Runway Safety Area
| Maintenance | 50 | 0 |  | 50
| Data Collection | 50 | 0 |  | 50 | X | X | X
| Analysis and Report of Data | 25 | 10 |  | 35 |  |  | X | X | Ä
| Other New Initiatives |  |  | 10 | 10 | [5 empty] | X | X | X | X | X | X | Ä
5. Surface Safety Initative Team
| Support BOS CARA Team | 0 | 0 |  | 0 |  | X | X | X | X
| Support DFW CARA Team | 0 | 0 |  | 0 |  | X | X | X | X
| Support (Airport TBD) |  | 0 |  | 0 |  |  |  |  | X | X | X | X
| Support (Airport TBD) |  | 0 |  | 0 |  |  |  |  | X | X | X | X
| Support (Airport TBD) |  |  | 75 | 75 | [7 empty] | X | X | X | X | X
| Support (Airport TBD) |  |  | 75 | 75 | [7 empty] | X | X | X | X | X
| Total Contract Funds | 700 | 700 | 850 | 2250
X - REPRESENTS FY QUARTER FOR DELIVERABLE
X - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK
|  | 700 | 700 | 850