## Sheet1
OPERATION OF NLA
(RPD 134)
PROJECTS: |  | WORK TO CONTINUE IN 2016
[7 empty] | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  |  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  | 2014 | 2015 | 2016 | TOTAL
1. New Methods for Calculating Agent Quantities
| Effects of Fuselage Geometry on Fire Behavior Simulation |  |  |  |  | 0
| Development of Advanced Fire Fighting Agent Application Model |  | 100 | 100 | 50 | 250 | X | X | X | X | X | X | X | X | Ä
| Development of ARFF Response and Fire Attack Model |  | 200 | 100 | 150 | 450 | X | X | X | X | X | X | X | X | X | X | Ä
2. Adequacy of ARFF Services and Strategies
| 1/10 Scale Live Fire Testing for Operational Strategies of NLA |  | 100 |  |  | 100 | Ä
| Full-Scale Validation Fire Testing for Operational Strategies of NLA |  | 150 | 200 | 200 | 550 | X | X | X | X | X | X | X | X | X | X | X | Ä
3. Adequacy of Specialized ARFF Vehicles and Equipment
| Identifying the tactical considerations unique to NLA |  | 50 | 50 | 50 | 150 | X | X | X | X | X | X | X | X | X | Ä
| Develop potential strategies or procedures for ARFF personnel |  | 100 | 50 | 50 | 200 | X | X | X | X | X | X | X | X | X | X | X | X
| Identify ARFF Technologies Increasing Effectiveness on NLA Fires |  | 100 | 100 | 100 | 300 | X | X | X | X | X | X | X | X | X | X | X | X
| Total Contract Funds |  | 800 | 600 | 600 | 2000
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK