## Sheet1
National Airport Pavement Test Facility
(RPD 138)
PROJECTS:
[6 empty] | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 2014 | 2015 | 2016 | TOTAL
1. Pre and Post Traffic Testing
| CC 6 Post Traffic Testing | 200 | 0 | 0 |  |  |  |  | Ä | Ä
| CC 7 Pre Traffic Testing | 0 | 200 | 0 |  |  |  | X
| CC7 Post Traffic Testing | 0 | 200 | 200 | [10 empty] | X | Ä
| CC8 Pre Traffic Testing | 0 | 0 | 200 | [7 empty] | Ä
2. Data Processing, Analysis, and Database Management
| Data Processing | 200 | 200 | 200 | 600 | X | X | X | X | X | X | X | X | X | X | X | X
| Data Analysis | 150 | 150 | 125 |  | X | X | X | X | X | X | X | X | X | X | X | X
| Database Management | 100 | 100 | 150 | 350 | X | X | X | X | X | X | X | X | X | X | X | X
3. Maintenance and Equipment
| Test Vehicle Repairs/Maintenance | 200 | 200 | 200 |  | X | X | X | X | X | X | X | X | X | X | X | X
| Test Vehicle Upgrades | 150 | 150 | 125 |  | X | X | X | X | X | X | X | X | X | X | X | X
| Facility Maintenance | 150 | 150 | 125 | 425 | X | X | X | X | X | X | X | X | X | X | X | X
| Facility Upgrades | 170 | 250 | 200 | 620 | X | X | X | x | X | X | X | X | X | X | X | X
4. Pavement Instrumentation
| Sensors and Wiring | 250 | 250 | 250 | 750 | X | X | X | X | X | X | X | X | X | X | X | X
| Data Acquisition Equipment | 150 | 100 | 100 |  | X | X | X | X | X | X | X | X | X | X | X | X
5. Pavement Specifications and Materials Testing
| Specifications | 175 | 100 | 175 |  | X | X | X | X | X | X | X | X | X | X | X | X
| Materials Testing | 225 | 250 | 250 |  | X | X | X | X | X | X | X | X | X | X | X | X
6. Demolition and Reconstruction
| CC6 Demolition | 200 | 0 | 0 |  | X | X | X | Ä
| CC7 Construction | 400 |  | 0 | 0 | X | X | X | Ä | X | Ä
| CC7 Demolition | 0 | 200 | 200 | [11 empty] | X | X
| CC8 Construction | 150 | 400 | 200 |  |  |  |  | X | X | X | Ä |  | X | Ä
| CC8 Demolition |  |  | 200 | [12 empty] | X
| Total Contract Funds | 2870 | 2900 | 2900
Ä REPRESENTS FY QUARTER FOR DELIVERABLE COMPLETION