## Sheet1
COMPOSITE MATERIAL FIRE FIGHTING
(RPD 140)
PROJECTS: |  | WORK TO CONTINUE IN 2016
[7 empty] | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  |  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  | 2014 | 2015 | 2016 | TOTAL
1. Identifying Effective Extinguishing Agents
| Development of a Live Fire Test Protocol |  | 100 | 50 |  | 150 | X | X | X | X | X | Ä
2. Identifying Effective Extinguishing Methods
| Required Forces for Forcible Entry into Composite Aircraft |  | 50 | 50 | 0 | 100 | X | X | X | X | X | Ä
| Evaluate Extinguishing Systems Designed for Composite Fires |  | 100 | 250 | 250 | 600 | X | X | X | X | X | X | X | X | X | X | X | X
3.Determine Quantities of Agent Required
| Live Fire Testing of Composite Materials |  | 150 | 200 | 300 | 650 | X | X | X | X | X | X | X | X | X | X | X | X
4.Identify Hazards Associated with Airborne Fibers
| Analyze air quality samples from forcible entry testing |  |  | 50 | 0 | 50 |  | X | X | X | X | Ä
| Analyze air quality samples from live fire testing |  | 100 | 150 | 200 | 450 | X | X | X | X | X | X | X | X | X | X | X | X
| Total Contract Funds |  | 500 | 750 | 750 | 2000
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK