## Sheet1
AIRCRAFT BRAKING FRICTION (RPD 147)
PROJECTS: |  | WORK TO CONTINUE IN 2017
[7 empty] | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  |  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  | 2014 | 2015 | 2016 | TOTAL
1. Braking Research Aircraft Work
| Aircraft Maintenance/Repair |  | 200 | 140 | 125 | 465 | X | X | X | Ä | X | X | X | Ä | X | X | X | Ä
| Instrumentation of Main Gear and Data Acquisition System |  | 110 |  |  | 110 | X | X | X | Ä
| Main Gear Brake System Modifications |  | 125 |  |  | 125 | X | X | X | Ä
| Manufactured Snow for Testing |  | 80 |  |  | 80 | X | Ä
| Mu-Slip Testing with Nose Gear Brakes |  | 125 |  |  | 125 | X | Ä
| Analysis and Report on Nose Gear Testing |  | 60 |  |  | 60 |  |  | X | Ä
| Procurement/Installation of New Main Gear Brakes |  | 100 |  |  | 100 |  | X | Ä
| Procurement/Installation of Brake Temperature Sensor System |  | 85 |  |  | 85 |  |  | X | Ä
| Upgrade Aircraft Speed Measuring Equipment |  | 65 |  |  | 65 | X | Ä
| Mu-Slip Testing with Main Gear Brakes, Phase 1 |  | 125 | 50 |  | 175 |  |  | X | X | X | Ä
| Analysis and Report on Phase 1 Main Gear Testing |  |  | 60 |  | 60 | [5 empty] | X | Ä
| Mu-Slip Testing with Main Gear Brakes, Phase 2 |  |  | 50 | 75 | 125 | [6 empty] | X | X | X | Ä
| Analysis and Report on Phase 2 Main Gear Testing |  |  |  | 100 | 100 | [9 empty] | X | Ä
2. Anti-Skid Brake System Simulation Lab
| Simulation Lab Design Modifications |  | 80 |  |  | 80 | X | Ä
| Simulation Lab Procurement/Assembly |  | 60 |  |  | 60 |  |  | X | Ä
| Simulation Lab Testing and Analysis |  | 125 | 50 | 50 | 225 |  |  | X | Ä | X | X | X | Ä | X | X | X | Ä
| Integrate Braking Controller into Aircraft |  | 100 |  |  | 100 | X | X | X | Ä
| Development of Main Gear Braking Controller |  | 100 | 50 | 50 | 200 | X | X | X | Ä | X | X | X | Ä | X | X | X | Ä
3. Flight Simulator Work
| Simulator Development |  | 60 | 10 |  | 70 |  |  | X | Ä | X | X | X | Ä
| Simulator Runs |  |  | 40 | 40 | 80 |  |  |  |  | X | X | X | Ä | X | X | X | Ä
| Simulator Run Analysis |  |  | 50 | 60 | 110 |  |  |  |  | X | X | X | Ä | X | X | X | Ä
4. Trapezoidal Shaped Runway Grooving
| Finite Element Modeling |  | 300 |  |  | 300 |  |  | X | Ä | X | X | X | Ä
| Total Contract Funds |  | 1900 | 500 | 500 | 2900
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK