## Sheet1
Surface Operations Technology
(RPD 148)
PROJECTS:
[6 empty] | 2014 |  |  |  | 2015 |  |  |  | 2016
|  | Funds (x 1,000) |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 2014 | 2015 | 2016 | TOTAL
1. Summer Maintenance
| CFME Monthly Maintenance | 15 | 15 | 15 | 45 | X | X | X | X | X | X | X | X | X | X | X | X
| CFME Annual Calibrations | 10 | 10 | 10 | 30 | X | Ä | X | X | X | Ä | X | X | X | Ä | X | X
| Project Test Support | 25 | 25 | 25 | 75 |  | X | X |  |  | X | X |  |  | X | X
2. Winter Operations
| Winter Condition Reporting | 5 | 5 | 40 | 50 | X | X |  |  | X | X |  |  | X | X
| Aircraft Braking Program Support | 40 | 40 | 10 | 90 | X | X | X |  | X | X | X |  | X | X | X
| Project Test Support | 15 | 20 | 20 | 55 | X | X | X | X | X | X | X | X | X | X | X | X
3. Aircraft Arresting Systems
| Other EMAS Concept Evaluation and Testing | 20 | 20 | 20 | 60 |  | X | X |  |  | X | X |  |  | X | X
| EMAS Maintenance Evaluation and Testing | 170 | 165 | 160 | 495 | X | X | X | X | X | X | X | X | X | X | X | X
4. Trapezoidal Groove Hydroplane Tests
| Groove Installation | 0 | 300 | 0 | 300 |  |  |  |  | X | X
| Project Testing Support | 0 | 300 | 100 | 400 |  |  |  |  | X | X | X | X | X | X | X | X
| Test Aircraft Support | 0 | 100 | 200 | 300 | [6 empty] | X | X | X | X | X
| Total Contract Funds | 300 | 1000 | 600 | 900
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK