## Sheet1
AIRPORT SLEEP AND ANNOYANCE/AIRCRAFT NOISE
(RPD 149)
PROJECTS: |  | Funds ($k) |  |  |  | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  | 2014 | 2015 | 2016 | TOTAL | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1. Airport Sleep and Annoyance (Aircraft Noise)
| Development of Test Plan | 0 |  |  | 0
| Airport Selection | 0 |  |  | 0
| Develop Survey Instrument | 75 |  |  | 75 | X
| OMB Approval of Survey Instrument | 75 |  |  | 75 | X | X | X
| Survey Preparation | 100 |  |  | 100 |  | X | X
| Compute Noise Metrics/Contours | 100 |  |  | 100 |  |  | X | X
| Data Collection | 750 | 150 | 150 | 1050 |  |  |  | X | X | X | X
| Analysis of Noise Data and Social Surveys | 400 | 400 | 400 | 1200 |  |  |  |  | X | X | X | X | X | X
| Development of Final Report/Recommendations |  | 200 | 200 | 400 | [8 empty] | X | X | Ä
Total Contract Funds |  | 1500 | 750 | 750 | 3000
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK