## Sheet1
WILDLIFE HAZARDS R&D
(RPD 150)
PROJECTS:
[6 empty] | 2014 |  |  |  | 2015 |  |  |  | 2016
|  | Funds (x 1,000) |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 2014 | 2015 | 2016 | TOTAL
1. Wildlife Hazards Management
| USDA Outreach and Education R&D Tasks | 165 | 100 | 100 | 365 | X | X | X | X | X | X | X | X | X | X | X | X
| USDA Research Tasks (Species Control,Habitat Management) | 500 | 550 | 575 | 1625 | X | X | X | X | X | X | X | X | X | X | X | X
| Use of Radar for Wildlife Hazard Assessments (Anacortes) | 50 | 0 | 0 | 50 | X | Ä
2. Wildlife Detection and Deterrent Technology
| Utility of Avian Detection Radars (Airport Operations) | 425 | 325 | 225 | 975 | X | X | X | X | X | X | X | X | X | X | X | X
| (New Ideas/Emerging Tech.) | 135 | 200 | 300 | 635 | X | X | X | X | X | X | X | X | X | X | X | X
| Lighting Sources for Avian Perception (Aircraft and Airport) | 320 | 200 | 250 | 770 | X | X | X | X | X | X | X | X | X | X | X | X
| Assessment of Thermal/Optical Detection System | 75 | 200 | 175 | 450 | X | X | X | X | X | X | X | X | X | X | X | X
| Directed Energy Systems/Deterrrents (AHD Effects, Other/ADS) | 165 | 115 | 100 | 380 | X | X | X | X | X | X | X | X |  |  | Ä
| Integration of Detection and Deterrents | 0 | 250 | 175 | 425 |  |  |  |  | X | X | X | X | X | X | X | X
| USDA Ops R&D Support of ORD Radar Use | 65 | 0 | 0 | 65 | X
| Gopher Tortoise Mitigation (SFB/Airport Design) | 15 | 0 | 0 | 15 | Ä | X
3. Wildlife Hazard Information Systems
| Website Upgrades and DB Management/Development | 310 | 160 | 150 | 620 | X | X | X | X | X | X | X | X | X | X | X | X
| Wildlife Surveillance Concept (WiSC, aka Bird Radar in ATC) | 275 | 300 | 200 | 775 | X | X | X | X | X | X | X | X | X | X | X | X
| Broad-Based Bird Tracking and Alert System (Civil AHAS) | 0 | 100 | 250 | 350 |  |  |  |  | X | X | X | X | X | X | X | X
4. FAA Strike DB and Analysis
| Annual Report | 25 | 30 | 30 | 85 | X | X |  |  | X |  |  |  | X
| Data Validation | 210 | 215 | 220 | 645 | X | X | X | X | X | X | X | X | X | X | X | X
| Special Analysis WBAT | 30 | 30 | 20 | 80 | X | X | X | X | X | X | X | X | X | X | X | X
5. Species Identification
| Smithsonian Feather and DNA Lab and Annual Report | 150 | 150 | 155 | 455 | X | X | X | X | X | X | X | X | X | X | X | X
| Total WA OPS Funds | 415 | 425 | 425 | 1265
| Total Contract Funds | 2500 | 2500 | 2500 | 7500
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK