## Schedule
Visual Guidance - RPD 151
PROJECTS: | Funds ($k) |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
| 2014 | 2015 | 2016 | TOTAL | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Lighting | 1500 | 1800 | 1800 | 5100
General Aviation |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X
New Technology |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X
Airfield Lighting Infrastructure |  |  |  |  | X | X | X | X | X | X | X | Ä
Linear Light Sources |  |  |  |  | X | X | X | Ä | X
Crash-Test Performance of Frangible Connections |  |  |  |  | X | X | X | Ä | X | X | X | Ä
Rumble Strips | [5 empty] | X | X | X | X | X | Ä
Signs | 800 | 200 | 200 | 1200
Approach Hold/Runway Safety Area signs/markings |  |  |  |  | X | X | X | X | X | Ä
EMAS sign/lighting |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X
Markings | 100 | 100 | 100 | 300
Structured Methylmethacrylate (MMA) Marking |  |  |  |  | X | X | Ä
Vertical Flight | 0 | 300 | 300 | 600
Heliport Touchdown Position Marking |  |  |  |  | Ä
Total Contract Funds | 2400 | 2400 | 2400 | 7200
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK