## Sheet1
IMPROVED RESCUE & FIRE FIGHTING EQUIPMENT and AGENTS | [6 empty] | (RPD 152)
PROJECTS: |  | WORK TO CONTINUE IN 2016
[7 empty] | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  |  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  | 2014 | 2015 | 2016 | TOTAL
1. Alternative Fire Fighting Agents
| Testing of new alternative agents |  | 0 | 50 | 50 | 100 |  |  |  |  | X | X | X | X | X | X | X | X
2. Maintenance & Upgrades of Test Facilities and Vehicles
| L1011 Test Bed |  | 50 | 50 |  | 100 | X | X | X | X | X | X | X | X
| 311A Conversion to an Interior Fire Test Chamber |  | 0 | 50 | 100 | 150 |  |  |  |  | X | X | X | X | X | X | X | X
3.Crash Simulation for Predicting Fuel Release
| Phase I - Modelling of Constellation Test |  |  |  |  | 0
| Phase II - Modelling of A380 |  |  |  |  | 0
| Phase III - Modelling of Additional Aircraft |  | 100 |  |  | 100 | X | Ä
4.New Fire Fighting System Minimum Perf. Baseline
| Develop Test Protocol for Baselining Technologies |  |  |  |  | 0
| Live Fire Validation of Test Protocol for Baselining Technologies |  | 100 | 150 | 150 | 400 | X | X | X | X | X | X | X | X | X | X | Ä
5.Cargo Aircraft Interior Fire Fighting
| Full-Scale Live Fire Testing Of Cargo Aircraft |  | 100 | 100 | 100 | 300 | X | X | X | X | X | X | X | X | X | X | X | X
6. Bio-Fuel Fire Fighting Research
| Small-Scale Fire Tests |  | 150 | 50 | 50 | 250 | X | X | X | X | X | X | X | X | X | X | X | X
| Full-Scale Fire Tests |  |  | 125 | 125 | 250 |  |  |  |  | X | X | X | X | X | X | X | X
7. Full-Scale Fire Testing of New ARFF Technologies
| Full-Scale Fire Tests |  | 200 | 225 | 325 | 750 |  | X | X | X | X | X | X | X | X | X | X | X
| Total Contract Funds |  | 700 | 800 | 900 | 2400
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK