## Sheet1
AIRPORT TECHNOLOGY RESEARCH TAXIWAY
(RPD 153)
PROJECTS: |  | WORK TO CONTINUE IN 2016
[7 empty] | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  |  | Funds | ($k) |  |  | Q1 | Q2 | Q3 | 1 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  | 2014 | 2015 | 2016 | TOTAL
2. Research Runway Construction
| Runway Construction - General Items |  | 1000 | 1000 |  | 2000 |  |  | X | X | X | X | X
| Runway Construction - Electrical Items |  | 350 | 350 |  | 700 |  |  | X | X | X | X | X | X
| Runway Construction - Pavement Items |  | 150 | 150 |  | 300 |  |  | X | X | X | X | X | X
| Construction Package Completion |  |  |  |  | 0 | [5 empty] | X | X | X
2. LED Electrical Architecture Testing
| Circuit Installation and Optimization |  |  |  | 400 | 400 | [8 empty] | X | X | X | X
| Check out equipment and beta testing |  |  |  | 300 | 300 | [8 empty] | X | X | X | Ä
| Pavement Testing Items |  |  |  | 200 | 200 | [8 empty] | X | X | X | Ä
| Total Contract Funds |  | 1500 | 1500 | 900 | 3900
X - REPRESENTS FY QUARTER FOR DELIVERABLE
Ä - REPRESENTS FY QUARTER FOR PLANNED COMPLETION OF TASK