## Sheet1
Heated Pavements
(RPD 155)
PROJECTS:
[7 empty] | 2 | 0 | 1 | 3 | 2 | 0 | 1 | 4 | 2 | 0 | 1 | 5 | 2 | 0 | 1 | 6
|  | Funds ($000) |  |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 2013 | 2014 | 2015 | 2016 | TOTAL
1. Geothermal Demonstration Project (Binghamton Airport)
| Concrete Pavement with Hydronic Piping |  |  |  |  | 0 | Ä
| Geothermal Wells & Mechanical Equipment |  |  |  |  | 0 |  |  |  | X | X | X | Ä
| Data Collection and Analysis | [13 empty] | X | Ä
2. Heated Pavement Research
| Airport Heated Pavement Study | 400 | 400 |  |  | 400 |  |  |  | X | X | X | X | X | Ä
| Advanced Materials Research | 300 | 300 | 250 | 300 | 850 |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | Ä
| Advanced Construction Techniques | 300 | 300 | 250 | 350 | 900 |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | Ä
| Total Contract Funds | 1000 | 1000 | 500 | 650 | 2150
Ä REPRESENTS FY QUARTER FOR DELIVERABLE COMPLETION