## Slide 1: Construction Update

## Slide 2: CC7 Completion of Perpetual Pavement Sections

## Slide 3: Construction Cycle 7
As we last left CC7…
  Winter weather forced shut down of the construction of CC7 by December 20th
  North half of CC7, Perpetual Pavement Test Sections, was completed
  Work Remaining:
    6 inch P-209 Base Course on South half, Overload Test Sections
    3 inch P-401 HMA on South half

## Slide 4: CC7- Resumed April 2014
Proof roll P-154 sub base course
  April 25, 2014
Place and compact P-209 base course
  April 29-30, 2014
Characterization tests on P-209
  May 1-2, 2014
Install Asphalt Strain Gages
  May 5-6, 2014

## Slide 5: CC7- Resumed April 2014
Place 3 inch P-401 HMA
  May 7, 2014
CC7 / CC8 Transition
  June 19 – July 21, 2014
Install Multi Depth Deflectometers
  July 11-17, 2014
Paint Striping
  July 22, 2014

## Slide 6: CC7 - Proof Roll Sub base

## Slide 7: CC7- Place P-209 Base Course

## Slide 8: CC7- Compact Base Course

## Slide 9: CC7 Characterization of P-209

## Slide 10: CC7 – Asphalt Strain Gages

## Slide 11: CC7- Paving Over ASG’s

## Slide 12: CC7 – Final Paving Lane

## Slide 13: CC7- Multi Depth Deflectometers

## Slide 14: CC7 – MDD Installation

## Slide 15: CC7- MDD Installation

## Slide 16: CC7- MDD Installation

## Slide 17: CC7- MDD Installation

## Slide 19: CC7- MDD Installation

## Slide 20: CC7- MDD Installation

## Slide 21: CC7- MDD Installation

## Slide 22: CC7- MDD Installation

## Slide 23: CC7- MDD Installation

## Slide 24: CC7- MDD Installation

## Slide 25: CC7- MDD Installation

## Slide 26: CC7 / CC8 Transition

## Slide 27: CC7 / CC8 Transition

## Slide 28: CC7 / CC8 Transition

## Slide 29: CC7 Striping

## Slide 30: High Temp. Pavement Test Facility and Safety Technology Building

## Slide 31: HTPTF and Safety Technology Bldg.

## Slide 32: HTPTF and Safety Technology Bldg.
10 Mar 2014 - Long cold winter. Base closed multiple time for snow. Project stalled many times for snow and frozen ground. Hopefully winter is about done…
From the FAA Construction Inspector’s Log:

## Slide 33: HTPTF and Safety Technology Bldg.
November 2013 through March 2014:
  Site Clearing and grubbing
  Underground Utilities
    Electric
    Telecom
    Sanitary Sewer
    Storm Water System
    Domestic Water
  Site Grading
  Partial Footers for Tension Membrane Building

## Slide 34: HTPTF and Safety Technology Bldg.
April through August 5
  All underground utilities complete
  Foundations and walls poured for the HTPTF building
  Footers and slab poured for the control building
  Footers and grade beam walls poured for the STB
  Radiant floor heat system installed for STB
  Slab poured for STB
Current Completion Date is Jan 2015

## Slide 35: HTPTF & Control Bldg. Footers

## Slide 36: HTPTF & Control Bldg. Footers

## Slide 37: HTPTF Building Walls

## Slide 38: HTPTF

## Slide 39: Control Bldg. – Prepped for Slab

## Slide 40: HTPTF Control Bldg. Steel

## Slide 41: HTPTF Foundations and Walls

## Slide 42: HTPTF Building Profile

## Slide 43: HTPTF Building Example

## Slide 44: STB – Footers and Grade Beam

## Slide 45: STB – Under Slab Works

## Slide 46
STB – Footers and Grade Beam

## Slide 47
STB – Prepping for Slab

## Slide 48: HTPTF and STB - Site Lighting

## Slide 49: STB Radiant Floor Heat

## Slide 50: HTPTF and STB 8/11/14

## Slide 51
Time Lapse Video
QUESTIONS / COMMENTS?
Murphy.Flynn@faa.gov
609-485-5318